GOVERNMENT OF INDIA

## OUTCOME  BUDGET

2013-2014

MINISTRY OF CONSUMER AFFAIRS, FOOD AND PUBLIC DISTRIBUTION

(DEPARTMENT OF CONSUMER AFFAIRS)

CONTENTS

Page No.

| EXECUTIVE SUMMARY | 1-7 |
| --- | --- |
| CHAPTER-I INTRODUCTION | 8-14 |
| CHAPTER-II FINANCIAL OUTLAYS 2012-13, OUTPUTS AND PROJECTED OUTCOMES | 15-43 |
| CHAPTER-III REFORM MEASURES AND POLICY INITIATIVES | 44-54 |
| CHAPTER-IV REVIEW OF PAST PERFORMANCE | 55-87 |
| CHAPTER-V FINANCIAL REVIEW | 88-95 |
| CHAPTER-VI REVIEW OF PERFORMANCE OF AUTONOMOUS BODY | 96-98 |

# DEPARTMENT OF CONSUMER AFFAIRS

# Executive Summary

A system of performance budgeting by Ministries handling development programmes was introduced in 1969 on the basis of the recommendations of the Administrative Reforms Commission. A need was felt to address certain weaknesses that had crept in the performance budget documents such as lack of clear one-to-one relationship between the financial budget and the performance budget and inadequate target-setting in physical terms for the ensuing year.  There has also been a growing concern about the need to track not just the intermediate physical “outputs” that are more readily measurable but also the “outcomes”, which are the end objectives of State intervention.

In March, 2006, Outcome Budget 2006-07 and Performance Budget 2005-06 were presented in Parliament by Department of Consumer Affairs.  These documents covered plan schemes and significant portion on non-plan expenditure and internal and extra budgetary resources as well.  With effect from the year 2007-08 it has been decided to merge the Performance Budget with the Outcome Budget.  Thus, there is now a single document i.e. Outcome Budget for 2008-09 and onwards.  This document broadly indicates   physical dimensions of the financial budget indicating the actual physical performance in 2011-12, performance  in 2012-13  and targeted  performance  during 2013-2014.  An attempt  has  also  been made to enumerate  the activities  and schemes  of the Department,  their  financial  outlays,  physical  outputs  and the projected  outcomes.

In the long  process of conversion  of outlays  into  outcomes,  there are several  intermediate  stages  and complementary  resources  which  are  also  required  for  achieving  intended  outcomes.  The  cause  and effect  chain  is not  always  direct  and several  factors  come  into play  that  influence  the actual  outcomes,  not  just  the outlays  earmarked.  Outcomes  are  the end  products  and results  of various Government initiatives  and interventions,  including those involving  partnership  with  the State  Governments,  Public  Sector  Undertakings,  Autonomous  Bodies  and the community.  They  involve  much  more than  mere “outputs”, since  they  cover  the quality  and effectiveness of the goods  and services  produced  as  a consequence  of an activity  under  a  scheme or programme.

In the modern industrial society, consumer occupies a pivotal place.  With the advent of globalization, the multi national companies are competing with local companies in the matter of production as well as rendering of services.  There is a need to educate the consumers about their rights and also to put in place a framework to redress consumer grievances and to encourage the organizations which advocate the consumer cause.  A consumer, who is fully aware of her/his rights, is in a position to exert pressure on the producers and suppliers of goods and services to upgrade the quality and standard of the products and services.  This makes the local producers and service providers globally competitive.

The campaign “Jago Grahak Jago” had generated significant awareness amongst public and had become a household name. The emphasis of the Department is an Consumer empowerment and expand the footprints in the every corner of the country.

The Department of Consumer Affairs has initiated a large number of consumer centric schemes based on the following three fundamentals: -

- Consumer should be able  to assert his/her  rights  - for this purpose  he/she  should be aware  of what  to expect  from  the service  providers (including  manufactured  goods).  This calls for increase in consumer awareness. The vehicle for doing  so,  inter alia,  is to promote  consumer movement  so that  it permeates  into  the mindset  and thus  consumer  welfare  becomes  an  integral  part  of public  policy and  functioning  of the government,  public  and private  sectors.

- Standards and conformity Assessment – To enable the  consumer  to assert  his/her  rights  it is necessary  that  he/she  must  be able  to benchmark  his/her  expectations of quality  services or products  against  certain  pre-determined  levels.  That  is where  the installation of a comprehensive  quality  infrastructure  with  state of art  integrated  system  of standards,  legal  metrology  and conformity  assessment  aligned  to the best  international  practices  assumes  a special  significance.

- Should the consumer find  the  quality  of service or goods  deficient  when  benchmarked  with pre-determined  or  prescribed  standards,  he/she  should  have  recourse  to relatively  inexpensive  and quick  method of redressal.  This means that consumer grievance redressal mechanism is an integral ingredient in asserting consumer rights.

The schemes of the Department of Consumer Affairs are woven around the above fabric.

The Outcome Budget 2013-14 is organized in the following chapters.

Chapter I – INTRODUCTION :

Chapter-I gives details of functions, major programmes, schemes and mandate of the Department.  The Department of Consumer Affairs, has been assigned the prime responsibility of consumer education, protection and monitoring the prices and availability of essential commodities. The Department has launched a publicity campaign to create consumer awareness and strengthen the consumer protection mechanism.

The other initiatives taken by the Department include: -

- Computerization and computer networking of consumer fora (CONFONET)

- Strengthening Consumer Fora.

- National Consumer Helpline

- Consumer On-line Research and Empowerment Centre (CORE).

- Gold hallmarking.

- Regulating future markets.

- Setting up of consumer clubs.

- Strengthening of weight & measurement organizations.

- Comparative testing of products.

- Laying down of standards through Bureau of Indian Standards.

### Chapter II –     FINANCIAL OUTLAYS 2013-2014, PROJECTED PHYSICAL OUTPUTS AND PROJECTED OUTCOMES:

Chapter-II gives details of the current schemes and programmes to be pursued in the year 2013-14.  During XIIth Plan, following new schemes have been launched:

- Strengthening of Standardization at National and International level, Registration/self declaration of conformity scheme.

- Consumer Counseling and Mediation.

- Strengthening of Price Monitoring Cell.

### Chapter III – REFORM MEASURES AND POLICY INITIATIVES:

Chapter-III gives details of policy initiatives taken by the Department.

Some of the recent initiatives of the Department relate to:

- Strengthening of Standardization at National and International level;

- Upgradation of WTO-TBT Enquiry Point;

- Establishment of a National System for Conformity Assessment and Compliance;

- Strengthening of Legal Metrology wings of States/UTs in the country.

For further strengthening the legal provisions, the Department of Consumer Affairs has initiated comprehensive amendments in the following Acts in the recent years:-

- Forward Contracts (Regulation) (Amendment) Bill, 2010.

- Consumer Protection (Amendment) Bill, 2011.

- Legal Metrology (Amendment) Bill, 2011.

Chapter IV – REVIEW OF PAST PERFORMANCE :

Chapter-IV highlights the performance of the Department in implementation of various schemes in the following fields during the year 2011-12 and 2012-13.

- Consumer awareness

- Consumer protection

- Consumer education and Training, HRD/Capacity Building.

- Strengthening the infrastructure for redressal of consumer grievances.

- Providing Computer hardware to Consumer Fora and networking thereof.

### Chapter V – FINANCIAL REVIEW:

Chapter-V gives details of expenditure vis-à-vis Budget and Revised Estimates since 2009-10. The importance attached to consumer protection and consumer awareness is evident from the fact that the plan budget allocation of the Department has been steadily increasing.  In the year 2009-10, the plan budget allocation was Rs. 209.00 crore which went upto Rs. 220.00 crore in the year 2010-11, Rs. 225.00 crore in 2011-12 and Rs. 241.00 crore each in 2012-13 and 2013-14.    Expenditure during the year 2009-10 on the plan side was 89.16% of Revised Estimates whereas in 2010-11, it was 94.91% of Revised Estimates, in 2011-12 the same was 94.93% of Revised Estimates.   In the year 2012-13, 72.70% of the Revised Estimates has been utilized upto December 2012.

Chapter VI – REVIEW OF PERFORMANCE OF AUTONOMOUS BODIES:

Chapter-VI details the performance of the autonomous body under the Department, namely Bureau of Indian Standards (BIS).  This body has completed 25 years of its operation in March, 2012.  BIS keeps a close eye on the setting up of standards of various goods and services.

MONITORING OF PROJECTS AND PUBLIC INFORMATION SYSTEM

A system for monitoring and evaluation of projects has been put in place in the Department of Consumer Affairs.  Projects are initially scrutinized and evaluated by  duly constituted Committees.   There is provision for a Standing Committee to monitor and approve projects under Consumer Welfare Fund (CWF). An Inter Ministerial Appraisal Committee has been constituted to evaluate and recommend new projects for consideration of the Standing Committee.  Monthly reports are obtained to keep a watch on the activities carried out.   In the case of the consultancy awarded to IIPA, the Monitoring Committee has been upgraded to the level of Secretary (Consumer Affairs).  Department is in the process of evaluating such projects under CWF, that have completed two years through an independent agency. Over and above this, the accounts of the grantee organizations are open to audit inspection by Comptroller and Accountant General as well as the internal audit.

All information pertaining to the major activities including budget, annual report and Outcome Budget, etc. are also available on the website of the Department: www.fcamin.nic.in. Department has set up a “Facilitation Centre” in Krishi Bhavan where public  can  obtain  any information or approach the Central  Public Information Officer, as envisaged  under Right  to Information Act.  Department has appointed 12 Central Public Information Officers (CPIOs) under the Right to Information Act to provide information to the public.  Department  has  also  set  up  a  “Public  Grievance Cell” which  looks  into  the grievances  of general  public  in respect  of  various  activities  undertaken  by this  Department.

# DEPARTMENT OF CONSUMER AFFAIRS

# CHAPTER-I

## INTRODUCTION

This chapter contains a brief introductory note on the functions of Department of Consumer Affairs, its organizational set up, list of major programmes/schemes implemented by the Department, its mandated goals and policy framework.

Department of Consumer Affairs (DCA) is one of the two Departments under the Ministry of Consumer Affairs, Food & Public Distribution.  It was constituted as a separate Department in June 1997 as it was considered necessary to have a separate Department to give a fillip to the nascent consumer in the country.  The work allocated to the Department, as per the Allocation of Business Rules, 1961, is listed below:-

(i)	 Internal Trade.

(ii)	Inter-State Trade: The Spurious Preparation (Inter-State Trade and Commerce) Control Act, 1955 (39 of 1955).

(iii) 	Control of Future Trading: The Forward Contracts (Regulation) Act, 1952 (74 of 1952).

(iv) 	The Essential Commodities Act, 1955 (10 of 1955) (supply, price and distribution of essential commodities not dealt with specifically by any other Department).

(v) Prevention of Black Marketing and Maintenance of Supplies of Essential Commodities Act, 1980 (7 of 1980), persons subject to detention thereunder.

(vi) 	To regulate weighing and measuring instruments used in trade and transaction, industrial production and for protection of human safety including regulation of packaged commodities.

(vii) Training in Legal Metrology.

(viii) The Emblems and Names (Prevention of Improper Use) Act, 1952 (12 of 1952).

(ix) The Standards of Weights and Measures Act, 1976 (60 of 1976) and the Standards of Weights and Measures (Enforcement) Act, 1985. To regulate weights and measures and commodities in prepackaged form.

(x) The Bureau of Indian Standards Act, 1986 (63 of 1986).

(xi) Laying down specifications, standards and codes and ensuring quality control of bio-fuels for end users.

(xii) Forward Markets Commission.

(xiii) Consumer Cooperatives.

(xiv) Monitoring of prices and availability of essential commodities.

(xv) National Test House.

(xvi) The Consumer Protection Act, 1986 (68 of 1986).

ORGANISATION

Department of Consumer Affairs’ mandate consists of 4 main areas of responsibilities:-

(i) Consumer protection,

(ii) Internal Trade,

(iii) Quality infrastructure and policies consisting of standards and legal metrology,

(iv) Monitoring of prices and availability of essential commodities.

In carrying out its mandate, the Department is assisted by the following organizations:-

(a) Bureau of Indian Standards (BIS)

(b) National Test House (NTH)

(c) National Consumer Disputes Redressal Commission (NCDRC)

(d) National Cooperative Consumers’ Federation (NCCF)

(e) Forward Markets Commission (FMC)

(f) Indian Institute of Legal Metrology (IILM)

(g) Regional Reference Standards Laboratories (RRSLs)

# CONSUMER WELFARE FUND

A Consumer Welfare Fund was created in 1992 with the objective of providing financial assistance to promote and protect the welfare of the consumers, create consumer awareness and strengthen consumer movement in the country, particularly in rural areas.  The Fund set by the Department of Revenue under the Central Excise and Salt Act, 1944, is operated by the Ministry of Consumer Affairs, Food & Public Distribution.  The Central Excise and Salt Act, 1944 was amended in 1991 to enable the Central Government to create the CWF where the money, which is not refundable to the manufacturers, etc.   shall be credited.  Net amount available in CWF as on 31.12.2012 is Rs.82.22 crores

The Consumer Welfare Fund Rules were framed and notified in the Gazette of India in 1992.  Under these rules, any agency/organization engaged in consumer welfare activities for a period of three years and registered under the Companies Act, 1956 or any other law for the time being in force, village/ mandal/ samiti-level cooperatives of consumers, industries, State government etc. are eligible for seeking financial assistance from the Fund.  An inter-Ministerial Standing Committee has been constituted under the Rules to make recommendations for proper utilization of the money credited to the Consumer Welfare Fund for the Welfare of the Consumers.

Guidelines for seeking financial assistance from the Consumer Welfare Fund, had been framed based on the report of a Working Group set up in 1993 for the purpose.  Since the inception of the Fund, a number of schemes viz. consumer awareness scheme, scheme for setting District consumer Information Centres, Jagriti Shivir Yojana, Scheme for infra-structural development of VCOs and Consumer Club scheme have been launched for spreading consumer awareness throughout the country.) The schemes namely District consumer Information Centres, Jagriti Shivir Yojana had been discontinued since 2004.

The Consumer Club scheme has been transferred to the State Governments for which financial assistance is given to the State Governments in proportion to the districts in a State.  Further, in order to promote the consumer movement throughout the country, the State Governments have been impressed upon the need to create their own Consumer Welfare Fund.  For strengthening financial support, the amount of seed money given to the State has been increased from 1:10 to 50:50, the quantum of which has been worked out on the basis of the number of districts in a State.  For special category States the ratio is 90:10. The scheme has been enhanced with a big amount of Rs. 10 crore as Corpus Fund by the Central Govt. as central share in the ratio of 75:25 (Centre: state). In case of special category state the ratio will be 90:10 (centre: state) The scheme was implemented in Madhya Pradesh, Kerala & West Bengal.

The Department of Consumer Affairs has initiated a number of steps to promote a responsible and responsive consumer movement in the country which is in line with the best international practices.  These include setting up of complaint handling counseling guidance mechanism, comparative testing of product and services, schemes for promoting involvement of Research Institution in Consumer Protection, Creation of Chair/Centers of excellence in Institutions/Universities, training programme , and  Information, Education and Communication(IEC) programmes for consumer awareness .

FORWARD MARKETS COMMISSION

Forward Markets Commission is a statutory body set up under the Forward Contracts (Regulation) Act, 1952. The Commission functions under the administrative control of the Ministry of Consumer Affairs, Food & Public Distributions; Department of Consumer Affairs, Govt. of India. The functions of the Forward Markets Commission under the Forward Contracts (Regulation) Act, 1952 include advising Government on grant of / withdrawal of recognition to the exchanges, monitoring and regulating the commodity futures markets and initiating necessary action as assigned in the FCRA, 1952, collecting and publishing market information, making necessary recommendations to the Government of India for the improved functioning of the market and inspection of the commodity exchanges and the members of the exchanges.

The functions of the Forward Markets Commission can be classified as regulatory and developmental functions. Regulatory functions of FMC include interventions for promoting market and financial integrity and customer protection from time to time. Developmental functions include those interventions that aim at facilitating increased and informed participation in the markets and adoption of the best international practices in the market.

Functions of the Forward Markets Commission are carried out by its 9 divisions, viz. Market Division-I, Market Division-II, Monitoring and Surveillance Division, Planning and Coordination Division, Intermediary Registration Division, Vigilance and Enforcement Division, IT Division, Legal Affairs Division, Administration Division.

PUBLICITY MEASURES

The success of consumer movement depends upon the level of awareness in the country amongst the consumers about their rights and responsibilities. Within India, due to its sheer size and diversity, the level of consumer awareness varies from State to State depending upon the level of literacy and the social awareness of the people. Educating more than 120 crores of population comprising various categories particularly those in rural areas where consumers are more susceptible to exploitation on consumers’ interests is a herculean task and has to be undertaken as a sustained national programme with adequate resource availability.  Central Plan Scheme on Consumer Awareness was launched in the 10th Five Year Plan.

The outlay for the 11th Plan is Rs.409.00 crores.

The B.E. allocation and the expenditure status of the five years of 11th Plan  is as below :-

| S.No. | Year | B.E. | Expenditure |
| --- | --- | --- | --- |
| 1 | 2007-08 | Rs. 67.00 crores | Rs. 44.34 crores |
| 2 | 2008-09 | Rs. 75.00 crores | Rs. 80.50 crores |
| 3 | 2009-10 | Rs. 78.00 crores | Rs. 70.60 crores |
| 4 | 2010-11 | Rs. 84.00 crores | Rs. 80.27 crores |
| 5 | 2011-12 | Rs. 87.23 crores | Rs. 85.73 crores |

PRICE MONITORING CELL

- The Price Monitoring Cell (PMC) monitors the prices of 22 essential commodities, Viz, rice, wheat, atta, gram dal, arhar dal, moong dal, urad dal, masoor dal, tea, sugar, salt, potato, onion, tomato, vanaspati, groundnut oil, mustard oil, milk, soya oil, palm oil, sunflower oil and  gur.  The retail and wholesale prices are collected from 55 designated centres on daily basis on the information furnished by the State’s Food and Civil Supplies Departments. The daily commodity prices and other activities of PMC are available in the website of the Department (http://fcamin.nic.in) which is updated regularly. Notes on the measures taken by the Government for ensuring adequate supplies and containing the rise in prices of essential commodities were prepared for Press Information Bureau (PIB) and Chief Economic Adviser, Ministry of Finance on a weekly basis for giving publicity.

- There has been a steady improvement in the inflation situation in India. During 2012-13, the rate of inflation for Primary Food Articles which was 8.32 percent for the month of November, 2011 reached a lower (-) 0.68 percent in the month of January, 2012. It started rising from February, 2012 onwards and was in double digits from March,2012 to July,2012. The rate of inflation   started declining from August, 2012 onwards and stood at 8.50 for the month of November, 2012.The rate of inflation for Combined Food Articles (Primary+ Manufactured), was at 8.99 percent for the month of November, 2012 which was 7.94 percent during the corresponding period of November, 2011.

- The prevailing price situation as well as other factors which have impact on prices, both in domestic and international markets are studied and brought to the notice of high level committees, such as Committee of Secretaries (COS), Cabinet Committee on Prices (CCP), through agenda notes prepared for their meetings, for appropriate action at the policy level. The decisions taken in these meetings are implemented by the concerned Ministry/Department which are charged with the responsibility of the subject matter of the decision. Government has taken several steps which have led to the softening of prices and insulated the vulnerable sections of society from the price rise.

4.     In order to improve the domestic availability of pulses and to protect the vulnerable sections of population, the scheme for import of pulses that was introduced in November, 2008 and had been operating till 30.6.2012, envisaged import of pulses for distribution to BPL households through Public Distribution System (PDS), with a subsidy of Rs.10/- per kg. Government has decided to resume the scheme for subsidized imported pulses through PDS in a varied form with a subsidy element of Rs.20/- per kg per month for the BPL cardholders for the residual part of the current year. The BPL targeted cardholders will be as estimated by the Department of Food & Public Distribution.

CHAPTER II

FINANCIAL OUTLAYS 2013-14 PROJECTED PHYSICAL OUTPUTS AND PROJECTED OUTCOMES

This chapter gives the details of the financial outlays, plan and non plan, for 2013-14, projected physical outputs and projected/budgeted outcomes for non-plan and plan schemes of the Department of Consumer Affairs. Its main objective is to establish a correspondence between financial outlays and projected outcomes.

(Rs. in crores)

| S. No. | Name of the Scheme Programme | Objective/ Outcome | Outlay 2013-14 |  |  | Quantifiable Deliverables/Physical Outputs | Projected Outcomes | Process/ Timeline | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | 2 | 3 | 4 |  |  | 5 | 6 | 7 | 8 |
|  |  |  | 4(i) | 4(ii) | 4(iii) |  |  |  |  |
|  |  |  | Non- Plan (Rs. in crore) | Plan (Rs. in crore) | Complementary Extra- Budgetary Resources |  |  |  |  |
| I a | 3456 Grant-in-aid Awareness Programme including training and education Consumer Online Resource & Empowerment Centre (CORE) set up by Consumer Coordination Council, Noida (UP) | Consumer Online Resource and Empowerment (CORE) Centre project is an initiative taken by the Ministry towards web-based Consumer Awareness &Protection Programme aimed at identification of Consumer problems and their redressal through institutional approach and utilizing the information technology methods. | 15.00 1.10 | -- --- | -- -- | (i) Develop Online Database (ii)Upload and update the consumer related issues on time. (iii) Make the online information available in major local languages for the benefit of a maximum number of consumers | Resolution of complaints will increase from 30%s to 35% | 5 years continuous. | Second phase of the Core Project is under consideration. |
| b. | (i) Indian Institute of Public Administration : IP Estate, Ring Road, New Delhi for Setting up and running a centre for Consumer studies in IIPA. (ii) Consultancy Project under the scheme for promoting involvement of Research Institutions/Universities/Colleges etc. (iii) SCHKRMP (IIPA) | (i) Conduct / facilitate in depth research in the area of consumer protection and consumer welfare. (ii) Network with the other institutions/ organizations nationally and internationally, working for the cause of Consumer Rights protection. (iii) Organize seminars/ workshops/ conference / round tables on the contemporary issues relating to consumer protection. (iv) Create resource center for future research and published books / monographs/ occasional papers to fill up existing knowledge gap. To facilitate and promote better protection of consumer ‘rights, interests and welfare. Organize seminars/workshops/conferences/round tables etc. To develop material for training and dissemination to be used by academic institutions in their activities related to consumer protection and consumer welfare. A project has been sanctioned to IIPA for setting up and running the State Consumer Helpline knowledge Resource Management Portal (SCHKRMP) for Coordination and Monitoring of the Central Plan Scheme of State Consumer Helpline for implementing in 3 years. | 1.83 2.01 1.04 0.45 | -- -- | -- -- | (i). Organized seminar /training workshops / conferences/ round table on the contemporary issues relating to consumer protections. (ii) Sensitize trade and industry and the service providers to the requirements of the consumers. (iii) create resource centre for future research (iv). published books / monographs/ occasional papers to fill up existing knowledge gap. Processing of fresh proposals applications regarding research projects already received and likely to be received from various organizations institutions, colleges, universities and educational institutions. To impart 3 training programmes for research on consumer protection. To identify and disseminate best practices in the field of consumer protection. 1. Development of a resource centre at State level which will be networked with national resource centre. 2. Develop alternate consumer disputes redressal mechanism at State level. 3. Maximum no. of disputes resolved out of court. 4. Early resolution of complaints. 5. Reach out to rural consumers. 6. Capacity building of State VCOs. 7. State level machinery gets experience. 8. Companies and service providers become more active in solving consumer disputes. 9. Provides service in regional language in addition to English language. | To facilitate and promote better protection of consumers rights and interests with special reference to rural India. 1. An average of at least 80% of consumers surveyed indicate that they are either very satisfied or satisfied with the service. 2. Average of at least 50% of consumers surveyed indicate that their problem was fully or partially resolved. 3. A minimum of 70% of all contacts and files monitored by the Knowledge Resource Management Portal are categorized as good. 4. A minimum of 95% of consumers names and addresses used to populate case histories are deemed accurate and 5. All complaints about the SCHs service were acknowledged and answered in due time. All such complaints and answers to them were made available to the Knowledge Resource Management Portal. | 5 years continuous 3 years. |  |
| c. | (i) FICCI Alliance for Consumer Care to facilitate prompt redressal of consumer grievances through interface between Business and the Consumer, (ii)FICCI (MAC) | A project has been sanctioned to FICCI at a cost of Rs.3.55 Crores spread over a period of 3 years. To set up Mediation Advisory Centre (MAC) under PPP model. | 1.14 0.15 | -- | -- | (i) Interface between business and the Consumer (ii) Develop and introduce a voluntary code of conduct for business-consumer relationship etc. 1. Develop and assess an implementable solution for practicing mediation in resolving consumer disputes in India. 2. Offer court annexed Mediation (Delhi State Consumer Court referred cases & cases referred from the identified District forums). 3. Select and train trainers for managing Mediation in Consumer Dispute based on International Best Practices. 4. Train mediators from academics, VCO’s and Industry across India. 5. Organize One National Level Consultation with the stakeholders. 6. Organize awareness programs promoting Mediation in major metros of India. 7. Create a website for promoting the concept of mediation in India and for disseminating the International Best Practices. 8. Conduct action based research and document the feedback of consumers & businesses experienced mediation with MAC. | Better public private relation will be developed and private sector will also become more responsible before consumers. 1. Offer court annexed Mediation (Cases referred by Delhi State Consumer Court and identified District Forums). 2. Mediators Training-20 Trainers and 100 Practitioners (Mediators) 3. Awareness programs for Businesses and Consumer Bodies across major metros in India. 4. One National Level Consultation with the stakeholders. 5. Action research & report on challenges and constraints in implementing Mediation for consumer dispute redressal in India and key areas of policy interventions at the end of the project. 6. Develop website for information sharing. 7. The objective is that at least 1000 consumers will use these facilities in a year from across 6 Mediation centers including Delhi and at least 80% of the cases handled by the mediators are disposed of within a time frame of 30 days. The time frame for mediation session and number of sessions to be offered will be decided by the Project Executive Committee. | 5 years | The project period has been extended up to 31.12.2013. The project period has been extended up to 31.3.2013. |
| d. | Council for Fair Business Practice, Mumbai, Maharashtra (CFBP) (i)for Consumer grievance redressal activity and ii.) upgrading for Ramakrishna Bajaj Consumer Education Testing Centre located at SNDT Women University at Mumbai | i) For Consumer grievance redressal activity by CFBP for 5 years. ii.) For up gradation of Ramakrishna Bajaj Consumer Education Testing Centre located at SNDT Women University at Mumbai | 0.06 | -- | -- | - To resolve maximum number of consumer complaints outside the consumer forum - To take steps to enhance awareness among consumers about the products they use. iii) To provide testing facilities at a reasonable costs & serve as Resource Centre seeking information, guidance and testing. | To create awareness amongst consumers about the product they use and provide various analytical /quality testing facility for the same. Serve as a resource base for consumers seeking information, guidance and testing. | Five years |  |
| e | National Consumer Helpline | i)To service the consumers complaints by giving them appropriate counseling ii) To transmit online complaints relating to companies under convergence platform for their speedy disposal. iii) To develop and migrate the existing website to more technologically superior platform that offers online transmission of complaints and better facilities to the User. iv)To undertake maximum resolution of consumer complaints in shortest possible time v) To enlarge the number of Companies under Convergence platform vi) To undertake measures to publicize about the Helpline in different parts of the country through appropriate means in association with First Party. vii) To render all technical and other consultancy services to set up State Consumer Help lies. viii) To enhance the knowledge of consumers and thereby increase their awareness about their rights as a consumer and the remedies available to redress their grievances. | 1.50 | -- | -- | The Helpline is intendedtodeal with all problems related to products and services including problems related to telecom, courier, banking, insurance, financial services etc | Average complaints are received 10000 in a month out of which around 40% to 45% resolved. | 3 years | Third phase of the project is under consideration. |
| f. | Voice Society 441, Jangpura Mathura Road, New. Delhi-110014 | - Comparable testdata of most selling products forverification of product qualityand performance - Opportunities for manufactures toknow their productperformance compared with their counter parts - Choices forconsumerasbestbuy products sold in the markets - Verification of misleading/claims of their products andprovidinginformationsymmetrybetweenconsumer and producers toenhance and contribute to development of competitive market. | 0.90 | -- | -- | Comparative Testing of 16 Products and 3 services per year | To spread Consumer awareness based on scientific studies of various consumers products and services to make rational choice. To sensitize national standards bodies policy makers on up gradation of national standards/policy changes Opportunity for manufactures to improve upon their products in competitive markets especially on quality ,performance, safety and energy efficiency based on our scientific studies | Three years | (IIIrd year grant) |
| g. | M/s Consumer Education and Research Centre (CERC) ‘Suraksha Sankool’ Sarkhej-Gandinagar Highway, Thaltej, Ahmedabad for upgrading lab. | For up gradation of laboratory with NABL accreditation | 0.50 | -- | -- | - Procure requisite test equipment and to undertake comparative testing of dry cell batteries, storage water heaters/geysers and certain food and pharmaceutical products. - Published the rating and ranking of products tested through their magazine and various print and electronic media - Invite comments feedback on test results from manufactures for improvement in their products in respect of safety and quality | Educate consumers for their buying decision and also protect the consumer’s interest by providing reliable information on safe and quality products which will help them to make them to make an informed choice. |  |  |
| h. | National Law Institute University, Kerwa Dam Road, Bhopal 462044 M.P. | To set-up a Chairin the area of consumer protection and consumer welfare at NLIU Bhopal. The primary objective of the Chair is to act as a “Think Tank “ for the Research and policy related issued on consumer protection and consumer welfare interests. | 0.39 | -- | -- | - Provide necessary expert inputs for formulation of policy /Programmes / schemes of the Department of Consumer Affairs; to identify and disseminate best practices in the field of consumer - Publish, in the form of books, monographs pamphlets to fill up existing knowledge gap and the results of research studies conducted by them; - Sponsor/Organize seminars / workshops / conferences etc. on consumer related issues at national / regional levels; - Develop, host and administer an academic, yet interactive, website from NLSIU to disseminate information to Consumer Affairs; - Undertake at least two specific studies, research or any other activity as may be commissioned by the ministry of Consumer Affairs every year; - Conceive and organize an All India Moot Court Competition on Consumer Affairs and ensure that the competition is conducted with wider participation of law schools and colleges from all over India with a designated prize in cash and kind; - Organize periodically, short term training programmes for the law Teachers, NGOs and others; - The Chair set up may also conceive, plan and execute a Post-Graduate Diploma Course on Consumer Affairs through the Distance Education Department at the NLSIU. | To facilitate and promote better protection of consumers rights and interests | Five years | 2nd installments |
| i. | (i) CONCERT Chennai | Organizing phase III of the training to detect food adulterants in common food items in 13 districts of Tamil Nadu. | 0.13 | -- | -- | - To create awareness about food adulteration among Housewives. - To educate Housewives about health hazards due to adulteration. - To inform them about right choice of food in day-to-day life - To demonstrate method of detection of adulterants using spot test kit - To provide them a spot test kit and a small booklet to describe the Methods of Testing. | As the programme has duration of 22 month, continuous follow up exercise will be undertaken to assess the total reach of the programme and to maintain the database of the trainee network. Each of the trainers is expected to go out and train others to detect adulteration in food products. Reporting formats will be supplied to all the trainees and information’s gathered from all of them on a regular basis. All these reports of the training programmes with the details of the adulteration samples identified will be posted on the website. |  | 2nd installments |
|  | (ii) CONCERT Chennai, for comparative testing of products and services | - Comparable test data of most selling products for verification of product quality and performance - Opportunities for manufactures to know their product performance compared with their counter parts - Choices for consumer as best buy products sold in the markets - Verification of misleading/claims of their products and providing information symmetry between consumer and producers to enhance and contribute to development of competitive market. | 0.97 |  |  | Comparative Testing of 7 Products and 3 services per year | - To spread Consumer awareness based on scientific studies of various consumers products and services to make rational choice. - To sensitize national standards bodies policy makers on up gradation of national standards /policy changes - Opportunity for manufactures to improve upon their products in competitive markets especially on quality ,performance, safety and energy efficiency based on our scientific studies |  | 2nd Phase |
| j. | Paramahans, Dehradun | Consumer Awareness in l consumers of Hill areas of Uttarakhand by empowering them about Consumer rights using innovative consumer awareness program. | 0.50 | -- | -- | 1. Prevention of exploitation of rural consumers of Hill areas of Uttarakhand by empowering them about Consumer rights using innovative consumer awareness program. 2. Conduct survey to get the actual number of senior citizen who qualify for the govt. pension and who are eligible yet not getting the pension and arrange the facility for them to get their right of pension. 3. Conduct survey of below poverty line eligible families and help them in securing the Ration card as per their financial status so that they can get their right of subsidized food grain as well as rice provided by the govt. via PDS. 4. Empowering the consumer on legal matters and their right to get the fair and unbiased trial as well as help. Special drive and awareness program for backward classes and women. |  |  |  |
| k. | Manav Vikas Sewa Sansthan, Luknow | Awareness on consumer right among the rural masses through information in Lucknow | 0.33 |  |  | To impart basic knowledge and generate awareness on consumer right among the rural masses through information, education and communication |  |  |  |
| l | Administrative College of India (ASCI) Hyderabad For setting up of a Centre for Rural Consumer studies | To set-up a Chair in the area of consumer protection and consumer welfare at Administrative College of India (ASCI) Hyderabad | 0.45 |  |  | The primary objective of the Chair is to act as a “Think Tank “ for the Research and policy related issues on consumer protection and consumer welfare interests. |  |  |  |
| m | Kerala State Co-operative Consumer Federation (CONSUMERFED) for procurement of Refrigerated vehicle | To enable consumer’s to reach essential commodities items at theirs door steps | 0.45 | - |  |  | To enable consumer’s to reach essential commodities items at theirs door steps |  |  |
| n | Human resource education society, Nagercoil | For consumer awareness | 0.25 |  |  | To impart basic knowledge and generate awareness on consumer right among the rural masses through information, education and communication |  |  |  |
| o | International Council for Welfare and Development, Jammu | For consumer awareness in rural areas of J&K | 0.10 |  |  | To impart basic knowledge and generate awareness on consumer right among the rural masses through information, education and communication |  |  |  |
| p | Tenak Society, Nagaland | For consumer awareness | 0.10 |  |  | To impart basic knowledge and generate awareness on consumer right among the rural masses through information, education and communication |  |  |  |
| q | Jioroi, Assam | For consumer awareness | 0.10 |  |  | To impart basic knowledge and generate awareness on consumer right among the rural masses through information, education and communication |  |  |  |
| r | Raghavendra Trust, Karnataka | For consumer awareness | 0.10 |  |  | To impart basic knowledge and generate awareness on consumer right among the rural masses through information, education and communication |  |  |  |
| s | Viki Welfare Society Nagaland | For consumer awareness | 0.10 |  |  | To impart basic knowledge and generate awareness on consumer right among the rural masses through information, education and communication |  |  |  |
| t | Ayolta Human Resource, Nagaland | For consumer awareness | 0.15 |  |  | To impart basic knowledge and generate awareness on consumer right among the rural masses through information, education and communication |  |  |  |
| u | Association of Development Society, Nagaland | For consumer awareness | 0.05 |  |  | To impart basic knowledge and generate awareness on consumer right among the rural masses through information, education and communication |  |  |  |
| v | Bhartiya Dalit Vikash Parishad, Aurangabad, Maharashtra | For consumer awareness in rural areas in Aurangabad District | 0.05 |  |  | To impart basic knowledge and generate awareness on consumer right among the rural masses through information, education and communication |  |  |  |
| w | Bhartiya Parivardhan Sanstha, Delhi | For consumer awareness in rural areas in Bihar | 0.10 |  |  | To impart basic knowledge and generate awareness on consumer right among the rural masses through information, education and communication |  |  |  |
| II a. | 3601 Grant-in-aid to State Government Consumer Club | This scheme was launched in 2002, according to which a consumer club shall be set up in each Middle /High/Higher Secondary/Colleges affiliated to a government recognized Board /Universities. A grant of Rs.10, 000/- per consumer club is admissible under this scheme. Main aim of the scheme are to educated children about the rights of the consumer as provided in the Consumer Protection Act, 1986, to mobilize youngsters by instilling in them the spirit of protection of Consumer Rights. | 30.00 1.52 | -- | -- | So far 23 states/ UTs have been covered in these schemes. During 2013-14 remaining 12 states/ UTs will be included in this scheme. | (i) Students will become aware about the consumer rights through consumer clubs set up in school. (ii) Consumer movement will become more strong by setting up of State Consumer Welfare Fund. |  |  |
| b. | Corpus Fund Scheme (introduced a new scheme enhancing the central share as Corpus Fund) | (i) In order to promote the Consumer movement throughout the country the State Govt. have been impressed upon to create their own Consumer Welfare Fund. For encouraging them to do so, the amount of seed money given to the States has recently increased from 1:10 to 50:50 and 90:10 in respect of 13 special category States. | 28.48 | -- | -- | So far 21 numbers of States/ UT have been sanctioned seed money. During 2013-14 remaining 14 states/ UTs will be included in this scheme. | Consumer movement will become stronger by setting up of State Consumer Welfare Fund. | Scheme is going on and will continue till all the state/UTs availed the benefit of the scheme. |  |
|  |  | (ii) In order to create Corpus fund to the tune of Rs. 10 crore in the States/UTs with central contribution 75 % of the total amount and 90% of the central contribution in the case of special category states. |  | -- | -- | So far 3 states have been sanctioned Corpus Fund Four States (Odisha, Bihar, Karnataka, and Nagaland) have been part funded for setting up corpus fund. During 2013-14 remaining 28 State/UT will be included in this scheme | Consumer movement will become stronger by setting up of State Consumer Welfare Fund. | Scheme is going on and will continue till all States /UTs are benefited of the scheme. |  |
| III a. b. | 3602 Grant-in-aid to UT Governments Consumer Clubs Seed Money (introduced a new scheme enhancing the central share as Corpus Fund) | This scheme was launched in 2002, according to which a consumer club shall be set up in each Middle/High/Higher Secondary School/ Colleges affiliated to a government recognized Board/ University. A grant of Rs.10,000/- per consumer club is admissible under this scheme. Main aim of the scheme are to educate children about the rights of the consumers as provided in the Consumer Protection Act, 1986, to mobilize youngsters by instilling in them the spirit of protection of Consumer Rights. In order to promote the consumer movement throughout the country, the State Government have been impressed upon to create their own Consumer Welfare Fund. For encouraging them to do so, the amount of seed money given to the States has recently increased from 1:10 to 50:50 and 90:10 in respect of 13 special category States. | 0.50 | -- | -- | Consumer clubs has been set up in three UT so far. Other UTs will be persuaded to avail the benefits of the scheme in the year 2013-14 | Consumer movement will become stronger by setting up of State Consumer Welfare Fund. | Scheme is going on and will continue till all UTs are benefited of the scheme. |  |
| c | Corpus Fund Scheme | In order to create Corpus fund to the tune of Rs. 10 crores in the States/UTs with central contribution 75 % of the total amount and 90% of the central contribution in the case of special category states. |  |  |  |  | Consumer movement will become stronger by setting up of State Consumer Welfare Fund. |  |  |
| IV | 3601-Grant-in-Aid to States Govts 03-Grants for Central Plan Schemes 361-Civil Supplies Schemes 04-Consumer Helpline 04.00.31-Grant-in-Aid | (To guide and counsel the Consumer to resolve their grievances.) |  | 2.50 | -- | - Develop alternate complaints redressal mechanism at State level. - Maximum No. of Disputes to be resolved out of court. - Early resolution of complaints. - Reach out to rural consumers. - Capacity building of state level VCOs. - State level machinery gets experience. - Companies and service providers become more active in solving consumer disputes. - Provide service in regional language in addition to English language. | More no of complaints will be resolved out of court. | The project is for 5 years after that States will continue the project from their sources. | In has been decided to continue the scheme during the 12th plan period and the proposal has been submitted to planning commission for approval through plan document. |
| V | 3602 Grant-in –aid to UTs. Govts. 03-Grant for Central Plan Scheme 361-Civil Supplies schemes 06-Consumer helpline 06.00.31- Grant-in –Aid | To guide and counsel the Consumers to resolve their grievances. |  | 0.50 | -- | - Develop alternate complaints redressal mechanism at State level. - Maximum No. of Disputes to be resolved out of court. - Early resolution of complaints. - Reach out to rural consumers. - Capacity building of state level VCOs. - State level machinery gets experience. - Companies and service providers become more active in solving consumer disputes. - Provide service in regional language in addition to English language. | More No of complaints will resolved out of court. | For 5 years. After that UTs will continue the project from their own sources. | In has been decided to continue the scheme during the 12th plan period and the proposal has been submitted to planning commission for approval through plan document. |
| 2. | (i) Strengthening Legal Metrology Infrastructure of States/ UTs | To Strengthen the Legal Metrology Wing of the States and Union Territories so that they may ensure correct measurement in commercial transaction and may protect the interest of consumers. This objective will be met through Supply of equipments viz. smaller Mobile Kit for testing of weigh bridges, CNG/LPG kits, Working/ secondary standards Weights and working standards capacity measures etc. to various states/UTs. Grant in aid for the construction of laboratory buildings will also be given for the said purpose. |  | 60 Cr. |  | (i) Supply of equipments viz. weighbridge testing kit, CNG/LPG kit etc. (ii) Construction of Standard Laboratory Buildings. (iii) Training In India and abroad. | - To ensure better accuracy by proper calibration of weighing and measuring instruments used in -Trade and transaction -Protection of human health and safety; - To ensure accurate standards for calibration of commercial scales and weighment by state agencies and - To ensure better enforcement | During XII five year plan |  |
|  | (ii) Strengthening RRSLs & IILM Ranchi | To strengthen the existing infrastructure of RRSLs/ IILM and to create new testing facility in to modernize testing/ training facilities at RRSLs and IILM, Ranchi |  | 4.00 |  | (i) To purchase testing equipments for RRSLs and IILM (ii) Creation of new testing facility (iii) Renovation work at RRSL & IILM, Ranchi to make it as centre of excellence. | To ensure better accuracy by proper calibration of weighing and measuring instruments used in trade Transaction & protection. | During XII five year plan |  |
| 3. (i) | Consumer Protection Cell | The Consumer Protection Cell renders secretarial assistance to the Department in administering the Consumer Protection Act, 1986 and related activities. | 0.18 | 0.41 | NIL | For holding one meeting of the Central Consumer Protection Council (CCPC) during 2013-14. | - | Continuous and ongoing scheme. | - |
| (ii) | Computerization and Computer Networking of Consumer Fora (CONFONET) | The project is being implemented by the National Informatics Centre (NIC) on a turnkey basis. Under the project all Consumer Fora in the country are to be computerized. The project would enable consumers to access various types of information relating to their complaints. | NIL | 6.60 | NIL | Software application development upgradation. Support cell and Project Management at NIC. Supply of new hardware at District Fora. | The system would be operationalized fully. | By 31.3.2014 | - |
| (iii) | Strengthening Consumer Fora and Consumer Counselling & Mediation | The scheme seeks to broadly continue with the objective of the earlier Integrated Project on Consumer Protection (IPCP) scheme to further strengthen the infrastructure of the consumer fora so that minimum level of facilities are provided at each consumer forum in the country, which are required for their effective functioning. | NIL | 5.39 | NIL | To complete the infrastructure of those Consumer Fora, which were not covered under the scheme so far. | Better facilities at Consumer Fora would help in quicker disposal of complaints and more consumer friendly interface. | 31.3.2014 | - |
| 4 | Strengthening of FMC |  |  | 16.20 |  |  |  |  |  |
| i) | Upgradation of IT facilities | i) Developing market monitoring and surveillance software, ii) Purchase of computer and hardware, iii) IT related assistance to 16 regional Exchanges to upgrade to online trading system and provide for audit trail. |  | 1.75 |  | i) Subscription for Commodity Market related data from 3 agencies and high speed data connectivity from one service provider. ii) Purchase of Hardware & software for IT enhancement, development of software for automated intermediary registration iii) Developing the IT capacity of Regional Exchanges iv) Outsourcing of IT related activities | Better Surveillance of the market and the Exchanges and the trading activities of the Exchanges and their members and other intermediaries. | 31.03.2014 |  |
| ii) | Capacity Building/ Training/ Consultancies | i) Training of FMC officials, officials of the Exchanges, Government officers and other stakeholder organizations in the commodity derivative market; ii) Conducting studies and awarding consultancies in the area of commodity derivative market; supporting pilots / innovative ideas in this field; iii) Conducting audit of Books of accounts of Exchanges and their members |  | 6.25 |  | i) 125 Capacity Building programmes ii) 500 Inspection of books of accounts of commodity Exchanges and members of the Exchanges iii) Consultancy assignment as per requirement | i) Building capabilities of the Govt. officers, Exchange functionaries and various categories of the stakeholders for creating efficiency in the market. ii) Sensitizing the policy makers about the utility of the futures markets in providing policy inputs and to make use of them for timely and appropriate policy changes. iii) Ensuring proper functioning of the market constituents. | 31.03.2014 |  |
| iii) | Awareness and Development Programmes | i) Conduct of awareness programmes every year in association with the Exchanges across the country covering farmers and other stakeholders. ii) Release of publicity material on benefits of commodity futures trading and also for client awareness through print and electronic media. iii) Interactions/ meeting with various stakeholders in the commodity futures markets to understand their difficulties, problems and their needs so as to align/design policies to meet feasible/ desirable objectives. iv) Coordinating with international regulatory bodies for increased adoption of best practices. |  | 4.00 |  | i) 600 awareness programmes, ii) Advertisements in National/Regional Dailies iii) 20 stakeholders’ meet iv) MOUs with Regulatory Bodies of other countries as per the requirement | i) Spreading awareness of the commodity futures market so as to enhance the understanding of and participation in the market. ii) Increasing interaction with the market stakeholders to facilitate better regulation of the market. iii) Increasing interaction with international regulatory bodies to facilitate better regulation of the market. | 31.03.2014 |  |
| iv) | Price Dissemination Project | Installing price ticker boards at identified locations with heavy farmer footfall to disseminate spot and futures prices on real time basis to farmers. |  | 3.65 |  | 2000 | Better dissemination of spot and future prices of commodities to centers accessible to farmers so as to empower them with price information and increase their bargaining power for better price realization. | 31.03.2014 |  |
| v) | Upgradation of the office infrastructure | Upgrading office infrastructure etc |  | 0.45 |  | Not Quantifiable | Better infrastructure to facilitate the strengthening of the staff of FMC. | 31.03.2014 |  |
| vi) | Purchase of Land/ Purchase/construction of Office Building for FMC | Purchase of Land/ Purchase/construction of Office Building for FMC |  | 0.10 |  | Not Quantifiable | Better infrastructure to facilitate strengthening of FMC | 31.03.2014 |  |
| 5. | Hallmarking | To protect Consumers against cheating by unscrupulous jewellers and to boost export of jewellery |  | 0.60 |  | Setting up and recognition of Assaying & Hallmarking centres. Organization of training Programmes for artisans Organization of Training Programmes for personnel of A & H Centres Organization of Training Programmes on Auditing of A&H Centres for BIS officers | 4 A&H Centres 10 Training Programmes 4 Training programmes 1 Training programme | 2013-14 | a) Financial viability of an Assaying and Hallmarking Centre is the main consideration for the private entrepreneur who intends to set up an A&H centre in different location. b) Policy decision on making of hallmarking mandatory for Gold jewellery/articles will largely determine the demand under this scheme. |
| ii) | Strengthening Standardization at National level | Enhanced participation from different stakeholders in standards setting process to ensure Indian standards stay abreast with current status of technology. |  | 0.70 |  | Organization of Training Programme for Standard developing organizations in India The Indian Standards so prepared/revised will be based on scientific study taking into consideration the situations prevailed in the country. If Indian standards are different from corresponding international standards, the scientific study will help in justifying in deviating from the International Standards. Participation of technical committee members for attending respective BIS technical committees. | 5 Training programmes 2 R&D Projects 130 technical committee members | 2013-14 | Process of award of R&D work requires thorough scrutiny at various levels of Technical Committees of BIS. Organizations not coming forward R&D projects are normally of minimum two years duration, and their continuity in terms of funding and the project leader are necessary. Enhanced participation of stakeholders in national standardization process would facilitate evolving comprehensive Indian Standards |
| iii) | Strengthening Standardization at International level | To emphatically project views/ concerns of India at relevant international and regional standards bodies to ensure that the international (ISO/IEC) standards or regional standards are relevant to Indian requirements and needs. To promote bilateral and multilateral cooperation in standardization and conformity assessment to promote exports and for consumer protection |  | 1.65 |  | Participation of 32 Technical committee members in ISO/IEC meetings, Organising 3 ISO/IEC/ other Regional Meeting in India Visit of 6 delegates to different countries for lobbying on standardization issues Participation 6 delegates in international workshops / Conferences | This would safeguard national trade and consumer interest in addition to facilitating the process of harmonizing Indian standards with International standard. | 2012-13 |  |
| iv) | Registration for Self Declaration of Conformity Scheme | Operation of additional conformity assessment scheme for protection of consumers from sub standards products/ imports), particularly in the areas of emerging technologies, |  | 2.33 |  | Scheme is yet to be approved but BE Provision is made on expectation of approval. |  |  |  |
| 6. | Consumer Awareness Campaign | Empowerment of consumer by dissemination of information through multi media publicity campaign “Jago Grahak Jago”. |  | 75.00 | 55.69 | - Increased focused on new areas of major consumer concern, Number of insertions in print, electronic and Outdoor media. | 1 lakh insertions all-inclusive | Target Achieved |  |
| 7. | National Test House | To implement 12th Plan proposed objectives as submitted to Planning Commission through DoCA i) Creation of New Test, Quality Evaluation & Calibration Facilities annually as per the proposed year-wise outlay ii) Strengthening of NTH regional laboratories through procurement of new Machinery & Equipments commensurate to the requirements iii) Infrastructural Development for creation of more laboratory space through construction of new building and extension of existing building | 28.29 | 18.75 | Nil | i) 10 % increase of revenue generation w.r.t previous year(2012-13) by providing NTH services ii) Utilization of Plan fund in accordance with the objectives laid down iii) Completion of on-going construction of NTH, Guwahati Building iii) Initiation of new building of NTH, Mumbai & extension of NTH, Jaipur | i) Anticipated revenue generation Rs.17.00 ii) Earmarked Machinery & Equipments costing Rs. 2.50 (as per RE)will be procured iii) Rs. 8.00 under Major Works as per Plan proposal (as per RE) | By the end of the year 2013-14 | i)Increase of revenue entirely depends on Clients and customers ii)Utilization of fund under Major Works depend on CPWD |

# CHAPTER- III

REFORM MEASURES AND POLICY INITIATIVES

1. 	CONSUMER WELFARE FUND

I   Setting up of Complaint handling/Counseling /guidance mechanisms

i) 	National Consumer Helpline (NCH)

The Department has launched National Consumer Helpline in coordination with Delhi University Department of Commerce. Consumers from all over the country can access the toll-free number 1800-11-4000 and seek telephonic counseling for problems that they face as consumers relating to various sectors such as telecom, courier, banking, insurance, financial services etc. The Helpline has been formally launched on 15th March 2005, on, World Consumer Rights Day. The total cost of project in Phase-I was Rs. 3.13 crores. The service is available in English and Hindi. Average complaints received are roughly 10,000 in a month and resolved is 40-45%. Project has been extended for further three years in Phase-II at a cost of Rs. 3.78 crores.

ii)	Consumer Online Research and Empowerment (CORE) Centre

Consumer Online Research and Empowerment (CORE) Centre project is an initiative taken by the Ministry towards web based consumer awareness & protection programme aimed at identification of consumer problems and their redressal through institutional approach and utilizing the vibrant information technology methods.  The project is being executed through Consumer Coordination Council (CCC), - a national coalition of more than 50 leading consumer organizations in the country and member of Consumers International – CI, (U.K.).

The main objectives of the CORE Center Project are:-

- Development of National information gathering mechanisms on consumer related issues;

- Dissemination of information on important consumer issues;

- Establishment of a Research & Documentation Centre on various consumer issues;

- Providing information and analysis of consumer related Laws and Judgments; and

- Providing online support and pursuing consumer complaints;

The project has been sanctioned with a total Budgetary outlay of Rs.3.50 crore spread over a period of five years out of which Rs.3.44cr. have been released so far.  The CORE Centre is located in the premises of the National Institute of Standardization of BIS (Bureau of Indian Standards) at NOIDA (UP).  A total of more than 137 Thousand Complaints were received from 15th April 2005 to 31st December 2012 out of which 59006 have been resolved and 33042 transferred to FICCI Alliance on Consumer Care. The second phase of the project is under consideration.

iii)	  Council for Fair Business Practice, Mumbai, Maharashtra (CFBP)

As part of new initiatives to enhance the levels and reach of consumer protection and welfare activities, the Department has considered and approved a project by Council for Fair Business Practice, Mumbai, Maharashtra (CFBP) This project is for consumer complaint handling by CFBP. Rs.6 lakhs is sanctioned for complaint handling per years for 5 years. IIIrd   year grant of Rs 6 lakhs has been released to CFBP.

(iv)	Indian Institute of Public Administration (IIPA) a project proposal for State Consumer Helpline Knowledge Resource Management Portal (SCHKRMP) for coordination and Monitoring of Scheme on State Consumer Helpline at a cost of Rs. 1,72,26,500 for a period three years in May 2011.  The second Year grant is yet to be released.

(v)	Federation of Indian Chamber of Commerce and Industry (FICCI) New Delhi, for setting up of FICCI Alliance for Consumer Care (FACC) for providing platform for facilitating prompt redressal of consumer complaint through voluntary self-regulation of consumer education at a cost of Rs. 3.10 crore.  An amount of Rs. 1.96 crore released so far and a balance Rs. 1.14 crore is to be released.   Project period extended upto 31.12.2013.

(vi)	Federation of Indian Chamber of Commerce and Industry (FICCI) New Delhi,  has been sanctioned a project for setting up of Mediation Advisory Centre (MAC) under PPP Model with the support of Department of Consumer Affairs, GIZ and FICCI at a cost of    Rs. 10,52,6000 for 15 months Department Contribution is Rs. 58,30,000.  Out of the sanctioned amount, Rs. 0.44 Crore released and Rs. 0.143 crore is to be released.

II Setting up of consumer Product Testing Laboratories

i)	Centre for Comparative Testing of Products and Services(Voice Society)

VOICE Society, New Delhi has been sanctioned a project for Comparative Testing of Consumer Products with the objective of ensuring product quality and safety.  The total approved cost of the project is Rs.2.25 cores, for a period of two years.  Total cost of the project has already been   released.  Under this project 16 products and 3 services have been tested and the reports have been published. The project has been evaluated recently.  Voice Society, New Delhi has been sanctioned an amount of Rs. 2.70 crore for IInd phase of the project.

The focus of the projects is as under

- Utilizing existing NABL accredited laboratories in India for comparative testing of various categories of products.

- Publishing and popularizing consumer magazine containing consumer related subjects in English, Hindi & other regional languages to create informed consumers.

- To facilitate in developing & up-gradation of National Standards based on scientific data and consumer preferences.

- An amount of Rs. 1.80 crore has been released so far and a balance of Rs. 0.90 crore as 3rd year grant to be released.

(ii)	CONCERT Trust Chennai has been sanctioned a project for undertaking Comparative Testing of 7 Products and 3 services per year for a period of Two years at a cost of Rs. 300.33 Lakh.  Project is in final stage and 2nd phase under consideration.

(iii)	M/s Consumer Education and Research Centre (CERC) ‘Suraksha Sankool’Sarkhej-Gandinagar Highway, Thaltej, Ahmadabad has been sanctioned an amount of Rs. 2.18 crore for up gradation of laboratory with NABL Accreditation and the amount released.   An amount of Rs. 1.25 Crore has now been sanctioned as operating cost over a period of 5 years.

III   Scheme for promoting involvement of Research Institutions/Universities /Colleges etc. in Consumer Protection and    Consumer Welfare

This scheme has been launched in 2004 with a view to sponsor research and evaluation studies in the field of consumer welfare to provide solution to the practical problems being faced by the consumers, to sponsor seminars/workshops/conferences on the consumer related topics, and to have necessary inputs for the formulation of policy/programme/scheme for protection and welfare of the consumers.  The Indian Institute of Public Administration, New Delhi, has been identified as the nodal organization to administer the scheme at a cost of Rs. 2.98 crore. 1st year and 2nd year grant released and 3rd year grant of Rs. 1.04 crore is to be released.

IV    Creation of Chair/Centers of excellence in Institutions/Universities

- Chair on Consumer Law an(d Practice in National Law School of India University (NLSUI), Bangalore:- A Chair on Consumer Law and Practice was sanctioned  in 2007-08 to National  Law School of India University (NLSUI), Bangalore at a cost of (Rs.90,00,000/- as an endowment grant. Rs. 15, 00,000/- was released for first year expenditure).  Total amount of grant of Rs. 1, 05, 00,000/- has been released. The primary objectives of the Chair  is to act as a ‘’Think Tank” for the Research and Policy related issues on consumer law and Practice and also develop Consumer Affairs as a district subject of study both at Under Graduate and Post Graduate levels.

ii)     Centre of Consumer Studies in IIPA: - A Centre for Consumer Studies was sanctioned in 2007-08 to Indian Institute of Public Administration, New Delhi at an estimated cost of Rs. 850.77 lakhs spread over a period of five years for in-depth action research in the areas of consumer protection, training of personnel engaged in administration and adjudication of consumer justice in the country and the elected representatives of the local bodies etc. An amount of Rs. 3,00,19,000/- for the   first and Second year grant has been released so far.

- IIPA has been sanctioned a Consultancy project on Consumer Protection and Consumer Welfare to sponsor research and evaluation studies in the field of consumer welfare to provide solution to the practical problem being faced by the consumer to sponsor seminars/workshops/ conferences on the consumers and to have necessary inputs for formulation of policy/ programme/scheme for the protection and welfare of consumers. Indian Institute of Public Administration has been appointed as consultant under the scheme to the Department of Consumer Affairs. A total grant of Rs. 381 lakhs have been sanctioned and released to IIPA for disbursement to 228 applicant organizations and institutions so far undertaking such projects. The scheme granted to IIPA was evaluated by a impendent the scheme was evaluated by a independent agency recently. The study has concluded that the scheme of creating awareness among institutions/colleges through a premier institute like IIPA is successful.

(iv)     A project has been approved by Standing Committee to Administrative Staff College of India, Hyderabad at a cost of Rs. 1.50 crores for setting up of a centre for Rural Consumer Studies at (ASCI) campus for a period three years

(v)	A Project proposal from National Law Institute University, Kerwa Dam Road, Bhopal, M.P. for Chair on Professorship in Consumer Protection  and Consumer welfare at the cost of Rs 94.45 lakhs  has been sanctioned.

- A project has been sanctioned to Tamil Nadu Dr. Ambedkar Law University, Chennai for Chair of Excellence on Consumer Law and Jurisprudence. At a cost of Rs. 94.45 lakhs in three installment spread over a period of 5 years. Out of the sanctioned amount of Rs. 94.45 lakh Department will provide Rs. 85.01 lakh as grant-in-aid and balance amount of Rs. 9.44 lakh (10% of total cost) will be borne by Dr. Ambedkar Law University as their own contribution the grant for 2 years shall be released as 1st installment and for next two years in the second installment and for one year as final installment. An amount of Rs. 34.01 lakhs has been released.

- A project has been sanctioned to National Law School of India University Bangalore for chair of Excellence on Consumer Law and Jurisprudence at a cost of Rs. 1,05,00,000. An additional amount of Rs. 8.00 lakhs has been sanctioned for undertaking additional activities.

V  Training Programmes

(i)	A project proposal for organizing Workshop-Cum-training programme for housewives for on the spot test to detect common adulterants in foods in  eight districts of Chennai in Tamilnadu at a cost of Rs, 29,74,000/-.  was sanctioned to CONCERT. On the recommendation of the evaluation report of the pilot project carried out by Tamilnadu Government, a second phase of the project for another 11 districts VIZ, Madurai, Vellore, Villipuram, Cuddalore, Tuticorin. Tanjore Kaurur, Tiruvallu, Salem, Perambalur and Tiruvannamalai in Phase-II at a cost of Rs. 33,77, 664/- has also been sanctioned. Third phase of project in the remaining parts of Tamil Nadu was sanctioned at a cost of Rs. 59.02 lakhs.

- Administrative Staff College of India, (ASCI) Hyderabad has been sanctioned an amount of Rs. 10 lakhs for conducting a week’s  training programme for members of consumers disputes redressal bodies.

VI     Information, Education and Communication programmes for consumer awareness

- A project has been sanctioned to M/s Lakshya-A Relif Organisation, New Delhi for implementing a project on consumer awareness in Kerala, UP and Haryana for a period of three years at a cost of Rs. 75 lakhs for a period of 3 years.

- A project has been sanctioned to M/s Paramhans Sanstha, Dehradun for consumer awareness activities in rural areas of Uttrakhand State at a cost of Rs. 111.11 lakhs for a period of 2 years.

- A project has been sanctioned to Ayolta Human Resource Society, Longleng District, and Nagaland at a cost of Rs. 49.50 lakhs for 3 years for consumer awareness programme.

- A project has been sanctioned to M/s Manav Vikas Sewa Sansthan, Luknow at cost Rs.  0.33 crore for consumer awareness activities in rural areas of Lucknow.

- A project has been sanctioned to M/s Kerala State Co-operative Consumer Federation (CONSUMERFED)at cost Rs. 0.45 crore for procurement of Refrigerated vehicle To enable consumer’s to reach essential commodities items at theirs door steps.

2	FORWARD MARKETS COMMISSION

Reform measures/policy initiatives taken by the Forward Markets Commission during 2012-13 (up to December 2012)

A.        Regulatory Initiatives taken by the Forward Markets Commission

To strengthen and broad base the market, the Forward Markets Commission  (FMC), the regulator of the commodity futures trading under the provisions of the Forward Contracts (Regulation) Act, 1952, undertook various regulatory initiatives as well as developmental activities. On the regulatory front, the FMC has taken various initiatives to improve market integrity, increase transparency, strengthen investor protection and curb excessive volatility. Investor Protection Fund (IPF) has been operationalised in all national exchanges and an amount of Rs.64.67 crores has been transferred to IPF by the exchanges. To bring in greater transparency and discipline in the dealings between the clients and the Member, the members of the National Commodity Exchanges have been directed to settle accounts of their clients every quarter. The Exchanges have been directed to communicate the details of the trades executed on their platform to the concerned clients, at the end of each trading day, through SMS and E-mail alerts.

FMC has introduced staggered delivery in most agricultural commodities in the near month futures contracts paving the way for credible threat of deliveries and better alignment with the physical markets. It has taken several other steps to curb excessive speculation.  FMC decided not to permit contracts in the lean season of the commodities and increased minimum initial margin to 10% of the value of the contract or VaR (Value at Risk) based margin whichever is higher in 7 essential commodities. The exchanges have reduced the FED (Final Expiry Date) in several commodities thereby preventing holding of stock for longer periods in the Exchange warehouses. FMC has undertaken the exercise of comprehensive review of futures contract design to align the futures market with physical market practices. To ensure transparency in the trading practices, the Exchanges were asked to display members data, trading activity during life cycle of a contract, details of percentage of proprietary/client trading including details of HFT and Algo trading on their websites. FMC also decided not to allow Algo/High Frequency Trade in mini and micro contracts with effect from 1st January 2013. Exchanges were asked to be pro-active in clients’ grievances redressal and to train their regional officers in mediation for this purpose. All these measures have contributed to significant reduction in price volatility of agricultural contracts traded on futures exchanges.

B. 	Developmental Activities

- FMC in association with Exchanges organized awareness program for various stakeholder groups, with primary focus on farmers. During 2012-13,  609 Awareness programmes have been conducted till December, 2012, out of which 360 programmes were conducted for farmers.

- FMC has tied up with various institutions for conducting training for various segments of the market and other stake holders. During 2012-13, till 31st December 2012, 74 capacity building programmes were conducted.

- Till December 2012, seven (7) meetings with the stakeholders were organized.

- The thrust of FMC has been not only to create awareness among farmers and cooperatives but also to make available both spot and futures prices to the farmers, through the installation of electronic price ticker boards under the Price Dissemination Project. Till December 2012, Price ticker boards have been installed at 409 (April to December, 2012). locations which include Agricultural Produce Market Committees (APMCs), Krishi Vikas Kendras (KVKs) and other locations with heavy farmer footfall.

3	NATIONAL TEST HOUSE

National Test House(NTH)- a subordinate office- under the Department of Consumer Affairs(DOCA), Government of India and a Scientific and Technological(S&T) Organization has been rendering its services to the nation in the field of Test, Quality Evaluation and issuing of Test Certificates on the conformity of practically all sorts of engineering products( except Drugs, Pharmaceuticals, Arms and Ammunitions) as per national, international and customer specified standards since the year 1912. NTH has a network of six regional laboratories situated at Kolkata, Mumbai, Chennai, Ghaziabad, Jaipur and Guwahati administering by the Office of the Director General, NTH at Salt Lake, Kolkata

Over the years apart from test and quality evaluation of engineering products in six major engineering disciplines ( viz. Chemical, Mechanical, Electrical, Metallurgy/ Non-Destructive Testing(NDT), Civil and Rubber, Plastic, Paper & Textile(RPPT), NTH has diversified itself in the area of providing Calibration Services, Training in Test Methodologies, Consultation for product up-gradation, Welder Certification under Indian Boiler Regulation Act (IBR) Act, 1950 and related S&T services. Besides, the Scientists of NTH assists BIS in formulation, framing and developing Indian Standards as members of various Technical Committees. The Scientists of NTH also carry out R&D activities in respect of development and modification of test methodologies which are being incorporated in the Indian Standards after necessary validation. All the NTH regional laboratories have been duly accredited by National Accreditation Board for Testing & Calibration(NABL) in the field of Test & Calibration services.

NTH extends its valuable services to the nations by assisting Custodians of law of the country , Judiciary and Vigilance Departments as a referral laboratory by testing and evaluation of contentious products.

NTH render its services to industries( Private, PSU, Autonomous Bodies & Govt. Departments ( both State and Central), Scientific Research Institutions like DRDO, Indira Gandhi Atomic Research Center, Kalpakkam, IIT etc.,  different Consumer Forums and even individuals.

Thus the vision and objective of NTH as envisaged is to provide Consumer Protection in respect of assuring quality products to the nation as a whole.

Functions of National Test House(NTH) at a glance :

► Test, Quality Evaluation of industrial and consumer products (except Drugs, Arms and Ammunition) and issuing of test certificates as per national/international standards or consumers requirements

► Calibration of artifacts

► Imparting training on test methodologies to industrial profesionals and students from academic and technological institutions

► Provide consultancy for up-gradation of products

► Development and modification of test methods

► Provide assistance to BIS for framing and modification of Indian Standard as Chairman/ Member of Technical Committees

► Services through six regional laboratories(Kolkata, Mumbai, Chennai, Ghaziabad, Jaipur and Guwahati

► Assisting NABL in its laboratory Accreditation Program

In view of strengthening, modernizing , infrastructure expansion and development and also to increase its stake especially in the area of Test and Quality Evaluation of varied engineering products to satisfy , NTH was allocated fund to the tune of Rs. 74.84 crore during the current(11th ) Five Year Plan Period.

National Test House (NTH) during 12th Plan Period has submitted Plan Proposal to the tune of Rs. 163.03 Crore to Planning Commission through Department of Consumer Affairs, Govt. of India for implementing the following objectives

a) To fill up the gap of major test areas in respect of high value industrial and consumer

products across the country, like test for Solar energy appliances, Impulse voltage test facilities for transformer, EMI/EMC test facilities for electronic gadgets, automobile tyre testing, test facilities for Light Emitting Diode(LED) lamp etc.

b) To develop a coherent bond on sharing scientific and technological services between NTH and

BIS for providing adequate service in consumer protection

c) Strengthening of NTH regional laboratories in order to widen its scope of test activities by procuring advanced technological Machinery & Equipments

d) To make NTH self-sufficient during the 12th Five Year Plan

e) To provide improved & rapid service delivery to the customers and clients through web based computer network (MIS system)

f) To impart training to Professionals and students from engineering colleges on Test methodologies

g) Infrastructural development by construction of new /additional building / additional floor depending on the requirements with a view to enlarging the existing laboratory space of different NTH Regions.

4		CONSUMER PROTECTION UNIT

Major policy initiatives taken concerning the ConsumerProtectionUnit (CPU) are as under:

(1)	Computerisation and Computer Networking of Consumer Fora in the Country (CONFONET):

To enhance transparency and efficiency in the functioning of consumer dispute redressal agencies (Consumer Fora) established under the Consumer Protection Act, 1986, the ‘CONFONET’ project is being implemented through the National Informatics Centre (NIC) on turnkey basis. The project would provide for computerization of all Consumer Fora in the country. This project would enable consumers & other concerned to access information.

(2)	Strengthening Consumer Fora:

The scheme is an extension of the Tenth Plan scheme ‘Integrated Project on Consumer Protection (IPCP)’ in the Eleventh Plan period. The scheme would further strengthen the infrastructure of the ConsumerFora so as to provide the minimum level of facilities required to make these Fora fully functional. Under this scheme, assistance would primarily be extended to States to complete the infrastructure in those Consumer Fora which were not covered under the IPCP scheme.

5		PUBLICITY

In the initial years of the Plan Scheme, Department has focused on core areas of its functioning i.e. Standards such as ISI and Hallmarking, provisions of Weights & Measures Act and Consumer Protection Act. However, there are a large number of consumer issues in the fast growing and emerging sectors of telecom, banking, insurance, medicines, education, travel etc.

In association with other Ministries such as Department of Chemical & Fertilizers, National Pharmaceutical Products Authority (NPPA), Bureau of Energy Efficiency (BEE), Ministry of Urban Development, Ministry of Human Resources Development, Ministry of Health and Family Welfare, Reserve Bank of India etc., Department of Consumer Affairs has released various advertisements on the specific related consumer issues to educate consumers through print media as well as electronic media. on the new emerging areas of consumer interest such as telecom, real estate, credit cards, financial products, pharmaceuticals, public distribution system, travel services, mediation, C.P.A. etc. The Department is utilizing the extensive network of Post offices and Railways, keeping in view the mandate to educate all sections of the society with special focus on the disadvantaged ones.

One major initiative taken by the Department is in the field of Misleading Advertisements.  Keeping in view its growing menace, the Department is looking at ways and means to evolve a coordinated, workable and consensual approach to tackle this.  All the stakeholders, including Consumers Groups, Central and State Governments, Business Bodies, Media and others have been involved.

6		LEGAL METROLOGY DIVISION

New Legislative Proposal

The Legal Metrology Act, 2009 (1 of 2010) was published in the official Gazette of India on 14.1.2010 and was implemented w.e.f. 1st April, 2011, with all rules made there under, after replacing the Acts namely Standards of weights and measures Act, 1976 and Standards of Weights and Measures (Enforcement) Act,1985. This Act will make uniform enforcement across the country.

CHAPTER IV

# REVIEW OF PAST PERFORMANCE

Consumer Welfare Fund  (Non-Plan )

A Consumer Welfare Fund (CWF) was created in 1992 with the objective of providing financial assistance to promote and protect the welfare of the consumers, create consumer awareness and strength consumer movement in the country, particularly in rural areas.  The State Governments and Union Territory Administrations have been impressed upon to create their own Consumer Welfare Fund.

The Other activities under the Consumer Welfare Fund relates to establishment of consumer clubs promoting involvement of Research Institutions/Universities/Colleges etc. under consumer protection and welfare.

During the 2011-12 Standing Committee approved following project-

1.	An amount of Rs. 1,53,480 has been sanctioned Himachal Pradesh for procurement of Computers to enable them to monitor and dally reporting of prices of commodities.

2.	An amount of Rs. 29.00 lakhs has been sanctioned to National Consumer Disputes Redressal Commission (NCDRC) for setting up of complaint handling & infrastructure development.

3(i).	An amount of Rs. 10 lakhs has been sanctioned to Administrative Staff College of India, Hyderabad for conducting one week training programme for official and members of Consumer Disputes Redressal bodies.

3 (ii)  Standing Committee approved a proposal of Administrative Staff College of India  for setting up of a Centre for Rural Consumer Studies at a cost of Rs. 0.50 crore per year over a period of 3 years.

4.	A project has been sanctioned to M/s Gowthami Foundation Prakasam District Andhra Pradesh for spreading Consumer Education and empowerment initiative in375 rural and tribal villages of Andhra Pradesh at a cost of Rs. 1.00 crore out of which Department contribution is Rs. 90.00 lakh.

5.	A project has been sanctioned to M/s Ayolta Human Resource Society, Orangkong Village, Longleng at a cost of Rs. 49.50 lakhs for three years for consumer awareness programme out of which Department contribution will be Rs. 45.00 lakhs.

6   	A Project has been sanctioned to M/s Sunrise Mission Home, Wokha Nagaland at a cost of Rs. 11.12 lakhs for one year for Consumer Awareness programme out of which Department contribution will be  Rs. 10.00 lakhs for two year. An amount of Rs. 5.00 lakhs has already been released as Ist installment of Grant-in-aid.

7. 	A project has been sanctioned to M/s Association for Development of Society, Kohima, Nagaland for Consumer Awareness Programme at a cost of Rs. 16.50 lakhs to be provided in 3 installments spread over 3 years out of which Department contribution will be Rs. 15.00 lakhs. An amount of Rs. 5.00 lakhs has already been released as Ist installment of Grant-in-aid.

8.	A project has been sanctioned to M/s Nari Mangal Mahila Samity, District Puri, Orissa for Consumer Awareness Programme at a cost of Rs. 16.50 lakhs to be provided in 3 installments spread over 3 years out of which Department contribution will be Rs. 15.00 lakhs. An amount of Rs. 5.00 lakhs has already been released as Ist installment of Grant-in-aid.

9.	A project has been sanctioned to V. Khikki Welfare Society, Kohima District, Nagaland at a cost of Rs. 33.00 lakhs for three years for Consumer Awareness programme out of which Rs. 30 lakhs will be Department contribution. An amount of Rs. 10.00 lakhs already been released as first installment of Grant-in-aid.

10.	A project has been sanctioned to M/s Consumer Unity and Trust Society (CUTS) for their project Indian Consumers in the New Age and to address the concerns of Common Man in 4 states viz. Tripura, Jharkhand, Karnataka and Haryana at a cost of Rs. 1 crores out of which Department will provide Rs. 90.00 lakhs as grant-in-aid.  An amount of Rs. 45.00 lakhs has been released as first installment of Grant-in-aid.

11.	A project has been sanctioned to M/s Bhartiya Dalit Vikas Parishad, Aurangabad Maharashtra at a cost of Rs. 11.00 lakhs for two year for consumer awareness programme out of which Department will provide Rs. 10.00 lakhs in two installment. An amount of Rs. 5.00 lakhs has been released as first installment of grant-in-aid.

12.	Sanctioned an amount of Rs. 40.00  Lakhs towards operational cost to Consumer Education and Research Centre, Ahmedabad on the upgraded Laboratory under CWF.

13.	An amount of Rs. 225,00,000 to Kerala State Cooperative Consumer Federation Ltd. (CONSUMERFED), Kochi for procurement of 10 Mobile Triveni Stores in 10 Districts of Kerala 2 Floating Triveni Stores in isolated areas surrounded with water, for strengthening the distribution of Consumer article and for consumer awareness campaign. Out of the approved project Department contribution is Rs. 2,02,50,000 as grant in aid.

14.	A project has been sanctioned to M/s Lakshya-A Relif Organization, New Delhi for implementing a project on consumer awareness in Kerala UP and Haryana at a cost of Rs. 75.00 lakhs for a period a three year out of which Department will provide 67.5 lakhs as grant in aid. An amount of Rs. 11.25 lakhs has been released as first installment of first year grant for implementing a project in Kerala.

15.	A project has been sanctioned to M/s Paramhans Sanstha, Dehradun, Uttarakhandat a cost of Rs. 1.11 crores for Consumer Awareness Programme in rural areas of Uttarakhand State for a period of two years out of which Department will contribute Rs. 1 crores. An amount of Rs. 50.00 lakhs has been sanctioned as first installment of grant-in-aid.

STATE  CONSUMER  HELPLINE  SCHEME (PLAN) :-

State Consumer Helpline is a new plan scheme to set up State consumer Helpline on similar lines as National Consumer Help line which will be a partnership effort between State and active VCOs of the States. These help lines will extend service in the regional language of State concerned and in Hindi and English. Eventually these State Help lines can be networked with National Consumer Helpline so as to make use of the data base and experience already available. So far 28 states/UTs have been sanctioned funds to set up Consumer Help lines. It has been decided to continue the scheme during 12th Plan.

OBJECTIVE OF THE SCHEME

State Consumer Helpline is proposed to be established with the following objective.

- Development of a resource center at States/UTs level which will be networked with national resource center.

- Develop Alternate Consumer Disputes Redressal mechanism at States/UTs level

- Maximum no. of dispute resolved out of court

- Early resolution of complaints

- Reach out to rural consumers

- Capacity building  of State/UTs level VCOs

- States/UTs level machinery gets experience

- Companies and service providers become more active in solving consumer disputes

- Provide service in regional language in addition to English language.

CONSUMER WELFARE FUND

Statement of Outlays/Outcomes/Targets 2011-12 and Actual Achievement 2011-12

NON-PLAN

(In crores of Rs.)

| S.No. |  | Name of the Scheme Programme | Objective/Outcome | Outlay* 2011-12 | Expenditure 2011-12 | Deliverables/Physical Outputs | Achievement w.r.t (Col-5) | Reason for variation |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 |  | 2 | 3 | 4 | 5 | 6 | 7 | 8 |
| I a |  | 0.4.01 Awareness Programme including training and education. 04.01.31 Grant-in-aid general. 4.01.35 Grants for capital assets. Consumer Online Resource & Empowerment Centre (CORE) set up by Consumer Coordination Council, Noida (UP) | Consumer Online Resource and Empowerment (CORE) Centre project is an initiative taken by the Ministry towards web-based Consumer Awareness & Protection Programme aimed at identification of Consumer problems and their redressal through institutional approach and utilizing the information technology methods. | BE = 10.00 RE = 15.00 14.00 1.00 0.50 | 9.74 1.00 0.48 | (i)Develop in Online Database (ii) Upload and update the consumer related issues on time. (iii) Make the online information available in major local languages for the benefit of a maximum number of consumers | Total complaints received 81362 and out of which 25034 and 33042 transferred to FICCI, Alliance & Consumer Care. |  |
| b. |  | - (i) Indian Institute of Public Administration on : IP Estate, Ring Road, New Delhi (ii) Indian Institute of Public Administration on : IP Estate, Ring Road, New Delhi | Setting up and running a Centre for Consumer studies in IIPA. (i) Conduct/facilitate in depth research in the area of consumer protection and consumer welfare. Consultancy project on Consumer Protection and Consumer Welfare To facilitate and promote better protection of consumer ‘rights, interests and welfare. Organize seminars/workshops/conferences/round tables etc. To develop material for training and dissemination to be used by academic institutions in their activities related to consumer protection and consumer welfare. | 1.38 1.29 | 1.38 0.99 | i) Organize seminar/training workshops/conferences/round table on the contemporary issues relating to consumer protections. ii)Sensitize trade and industry and the Net Processing of fresh proposals applications regarding research projects already received and likely to be received from various organizations institutions, colleges, universities and educational institutions. To impart 3 training programmes for research an consumer protection. To identify and disseminate best practices in the field of consumer protection. | 71Organiza- tions have been sanctioned grant for undertaking research study. |  |
| c. |  | National Consumer Helpline | The National Consumer Helpline (NCH) is a landmark project set up in collaboration with the Delhi University at a cost of Rs.3,12,89,420/- spread over a period of three years. Consumers from anywhere in the country can dial the toll number 1800-11-4000 from any BSNL/MTNL telephone line and seek advice in all areas of consumer interest and sort out their grievances. The service is available in English and Hindi. NCH 2nd phase was sanctioned at a cost of 3.78 crores spread over a period of 3 years | 1.33 | 1.03 | NCH is continuously doing efforts by forwarding the complaints to respective companies as well as by organizing discussions with officials of the companies so that the complaints get resolved before going the same to consumer courts. New guideline regarding credit cards issued by RBI is a major achievement of NCH. | Average numbers of complaints received is 10,000 in a month out of which around 30% resolved. |  |
| d. e. |  | Comparative Testing Project. Voice Society. Consumer Education & Research Centre Ahmadabad. | IInd phase of the Comparative Testing of Products and services sanctioned at a cost of Rs. 2.70 crore spread over of pried of three years. Aim of the project is to spread Consumer Awareness based on scientific studies of various consumer products to make national choices. CERC has been sanctioned an amount of Rs. 1.82 crores for up gradation of testing laboratory with NABL accreditation. | 0.90 0.95 | 0.90 0.95 | - Scientific data to empower consumers on national choices of the products based on their overall performance. - Choices of best buy products available in the competitive retail markets. - Test data for NSB to verify products compliance to national standards. - Verification of claims of various manufacturers for their claims on product performance, quality, safety energy consumption/efficiency, environment & consumer friendliness Steps to enhance awareness among consumer about the products they use & serve as Resource Centre for consumers seeking information guidance and testing. | Testing of 10 products viz. Chili Powders , Potato Chips, Disinfectant Fluid, Jams, Health drinks, Lipsticks, Mosquito repellant, Mono Pump set, Juicer Mixer grinder & Color TV and Two services viz. Insurance and Banking have been done and reports have also been published in Consumer Voice magazine Yet to be received |  |
| f. |  | (i) CONCERT TRUST, 4/386, Singaraillam Ram | Training programme for detection of adulteration in Common Food Items-1st 2nd and II phase | 0.50 | 0.39 |  |  |  |
| g. |  | Dr. Ambedkar Law University, Chennai | Establishing chair of excellence on consumer law and jurisprudence. | 0.50 | 0.34 |  |  |  |
| h. |  | Consumer Unity and Trust Society, Jaipur | For gross root reach-out and networking in India though consumer action in 12 districts of Rajasthan, etc | 1.23 | 0.68 |  |  |  |
| i. |  | NCDRC, New Delhi. | Purchase of Mobile van. | 0.54 | 0.54 |  |  |  |
| j. |  | Gowthami Foundation. | Consumer awareness in rural areas of Prakasham District of Andhra Pradesh. | 0.45 | 0.45 |  |  |  |
| k. |  | Kerala state Cooperative consumer federation. (Consumerfed) | For procuring mobile van and fluting mobile stores. | 3.00 | 2.02 |  |  |  |
| l. |  | Bharatiya dalit vikas parishad, Aurangabad. | Consumer awareness programme | 0.05 | 0.05 |  |  |  |
| m. |  | Lakshya Relief Organisation, Delhi | Consumer awareness programme in Kerala State | 0.75 | 0.11 |  |  |  |
| n. |  | Pramhans sanstha, Dehradun | Consumer awareness programme in Uttrakhand | 0.50 | 0.50 |  |  |  |
| o. |  | (i) FICCI Alliance for Consumer Care to facilitate prompt redressal of consumer grievances through interface between Business and the Consumer, (ii) FICCI (MAC) | A project has been sanctioned to FICCI at a cost of Rs.3.55 Crores spread over a period of 3 years. To set up Mediation Advisory Centre (MAC) under PPP model. | 1.14 0.58 | -- | -- | (i) Interface between business and the Consumer (ii) Develop and introduce a voluntary code of conduct for business-consumer relationship etc. 1. Develop and assess an implementable solution for practicing mediation in resolving consumer disputes in India. 2. Offer court annexed Mediation (Delhi State Consumer Court referred cases & cases referred from the identified District forums). 3. Select and train trainers for managing Mediation in Consumer Dispute based on International Best Practices. 4. Train mediators from academics, VCO’s and Industry across India. 5. Organize One National Level Consultation with the stakeholders. 6. Organize awareness programs promoting Mediation in major metros of India. 7. Create a website for promoting the concept of mediation in India and for disseminating the International Best Practices. 8. Conduct action based research and document the feedback of consumers &businesses experienced mediation with MAC. |  |
| P |  | Others (miscellaneous and other expenditure below 0.50 Crore) | Consumer awareness programme | 1.82 | 1.72 |  |  |  |
| II |  | 04.02 Testing including comparative testing & research programme. 4.02.31 Grant-in-aid general. 04.02.35 Grants for Creation of capital assets. |  | 2.28 0.50 | 2.28 - |  |  |  |
| a b |  | Comparative Testing Project. Voice Society. Consumer Education & Research Centre Ahmadabad. | IInd phase of the Comparative Testing of Products and services sanctioned at a cost of Rs. 2.70 crore spread over of pried of three years. Aim of the project is to spread Consumer Awareness based on scientific studies of various consumer products to make national choices. CERC has been sanctioned an amount of Rs. 1.82 crores for up gradation of testing laboratory with NABL accreditation. | 0.90 0.95 | 0.90 0.95 | - Scientific data to empower consumers on national choices of the products based on their overall performance. - (ii) Choices of best buy products available in the competitive retail markets. - Test data for NSB to verify products compliance to national standards. - Verification of claims of various manufacturers for their claims on product performance, quality, safety energy consumption/efficiency, environment & consumer friendliness Steps to enhance awareness among consumer about the products they use & serve as Resource Centre for consumers seeking information guidance and testing. | Testing of 10 products viz. Chili Powders , Potato Chips, Disinfectant Fluid, Jams, Health drinks, Lipsticks, Mosquito repellant, Mono Pump set, Juicer Mixer grinder & Color TV and Two services viz. Insurance and Banking have been done and reports have also been published in Consumer Voice magazine Yet to be received |  |
| c |  | CONCERT TRUST, 4/386, Singaraillam Ram | Comparative Testing of Products and Services. | 0.73 | 0.43 |  |  |  |
| III |  | 04.04 Establishment Expenses of Consumer Welfare Fund. |  | 0.26 | 0.26 |  |  |  |
| II a. |  | 3601 Grant-in-aid to State Government Consumer Club | This scheme was launched in 2002, according to which a consumer club shall be set up in each Middle/High/Higher Secondary /Colleges affiliated to a government recognized Board/ Universities. A grant of Rs.10,000/- per consumer club is admissible under this scheme. Main aim of the scheme are to educated children about the rights of the consumer as provided in the Consumer Protection Act, 1986, to mobilize youngsters by instilling in them the spirit of protection of Consumer Rights. | 13.00 0.37 | 13.00 0.37 | A baseline study for rapid appraisal of level of awareness on consumer right and laws for understanding existing mechanism for consumer education and redresses of grievances at district level | Children are getting awareness about the consumer rights by consumer clubs set up in the school. | State Govt. /Uts have not applied for the fund Reminder has been sent Grant-in-aid of Rs. 37.00 lakhs has been sanctioned to Nagaland |
| b. c |  | Seed Money (introduced a new scheme enhancing the central share as Corpus Fund) Corpus fund Scheme | In order to promote the Consumer movement throughout the country the State Govt. have been impressed upon to create their own Consumer Welfare Fund. For encouraging them to do so, the amount of seed money given to the States has recently increased from 1:10 to 50:50 and 90:10 in respect of 13 special category States. In order to create Corpus fund to the tune of Rs. 10 crores in the States/UTs with central contribution 75 % of the total amount and 90% of the central contribution in the case of special category states. | -- 12.63 | -- 12.63 | State Consumer Welfare has been set up in 20 States so far. During 2009-10 remaining 15 states /UTs will be included in this scheme. The sanctioned amount will be utilized by the respective states for strengthening consumer awareness activities to NGOs/VCOs. | Consumer movement will become stronger by setting up of State Consumer Welfare Fund. Corpus fund has been setup in Madhya Pradesh, Kerala & West Bengal. | Proposal yet to be received from State despite of repeated reminders. |
| III a. |  | 3602 Grant-in-aid to UT Governments 01.00.31 Consumer Clubs | This scheme was launched in 2002, according to which a consumer club shall be set up in each Middle/High/Higher Secondary School/Colleges affiliated to a government recognized Board/University. A grant of Rs.10,000/- per consumer club is admissible under this scheme. Main aim of the scheme are to educate children about the rights of the consumers as provided in the Consumer Protection Act, 1986, to mobilize youngsters by instilling in them the spirit of protection of Consumer Rights. | -- -- | -- -- | 50 consumer clubs has been set up on one UT i.e. Govt. of Chandigarh UT | Children are getting aware about the consumer rights by consumer clubs set up in the school | Proposal yet to be received from State despite of repeated reminders issued. |
| ## b. c |  | ## Seed Money (introduced a new scheme enhancing the central share as Corpus Fund) Corpus Fund | ## In order to promote the consumer movement throughout the country, the State Government have been impressed upon to create their own Consumer Welfare Fund. For encouraging them to do so, the amount of seed money given to the States has recently increased from 1:10 to 50:50 and 90:10 in respect of 13 special category States. In order to create Corpus fund to the tune of Rs. 10 crores in the States/UTs with central contribution 75 % of the total amount and 90% of the central contribution in the case of special category states. | -- -- | ## --- -- | ## State Consumer Welfare has been set up in three UTs Government so far. -- | ## Consumer movement will become stronger by setting up of State Consumer Welfare Fund. -- | ## Proposal not received from State despite of repeated reminders -- |
| * Only major projects are included PLAN SCHEME |  |  |  |  |  |  |  |  |
| ## 1 ## (a) | ## 3601- Grant-in-aid to States Govts. 03- Grants for Central Plan Schemes 04- Consumer Helpline 04.00.31- Grant-in-aid. |  | ## To guide and counsel the consumer to resolve their grievances. | 1.00 | ## 0.94 | ## 1. Develop alternate complaints redressal mechanism at State level. 2. Maximum No. of Disputes to be resolved out of court. 3. Early resolution of complaints. 4. Reach out rural consumers. 5. Capacity building of state level VCOs. 6. State level machinery gets experience. 7. Companies and service providers become more active in solving consumer disputes. 8. Provide service in regional language in addition to English language. | ## More No. of complaints will be resolved out of court. | ## The project is for 5 years after that states will continue the project form their sources. ## Grant-in-aid has been sanctioned to Dadar & Nagar Haveli, Puducherry, Uttrakhand for setting up of State Consumer Helpline. Recurring grant in aid were also released to Gujarat, Sikkim, Tamil Nadu. |
| ## (b) | ## 3602 Grants-in-aid to UTs. Govts. 03-Grant for Central Plan Schemes 04- Consumer Helpline 04.00.31- Grant-in-aid. |  | ## To guide and counsel the consumers to resolve their grievances. | -- | ## -- | ## 1. Develop alternate complaints redressal mechanism at State level. 2. Maximum No. of Disputes to be resolved out of court. 3. Early resolution of complaints. 4. Reach out rural consumers. 5. Capacity building of state level VCOs. 6. State level machinery gets experience. 7. Companies and service providers become more active in solving consumer disputes. 8. Provide service in regional language in addition to English language. | ## More No. of complaints will be resolved out of court. | ## The project is for 5 years after that states will continue the project form their sources. ## Grant in aid were sanctioned to Dadar & Nagar Haveli & Puducherry |

Regional Reference Standards Laboratories (RRSLs)

The Central Government has established five Regional Reference Standards Laboratories at Ahmadabad, Bangalore, Bhubaneswar, Faridabad and Guwahati to check periodically the legal standards of weights and measures of State Government laboratories as well as to carry out calibration and testing of weights and measures of industries of the region.

The basic objectives of establishment RRSLs are as follows:-

- Periodic verification of legal standards of weights or measures of States/UTs in the region.

- To conduct model approval tests of weighing and measuring instruments covered under Legal Metrology.

- Calibration of measuring instruments used by industries.

- Liaison with States weights and measures Dept., and to conduct surveys to check effective implementation of laws in various sectors of economy.

- To conduct need based training seminars for enforcement officials of the region.

Scheme

The Department of Consumer Affairs, Government of India has formulated two Schemes during XI Plan, namely Strengthening Weights and Measures Infrastructure of States/UTs and Strengthening of Regional Reference Standards Laboratories (RRSLs) and Indian Institute of Legal Metrology (IILM), Ranchi.

1. Scheme “Strengthening Weights and Measures Infrastructure of States/UTs”.

The objective of the scheme is augmentation of State’s Legal Metrology infrastructure in holistic way by construction of laboratory building, supply of equipments and capacity building of enforcement officials for effective implementation of weights and measures laws.

A new scheme with an outlay of Rs. 143.286 crore was implemented during 2009-12 to strengthen the State enforcement machinery in a holistic way.  Under this scheme during 2010-11 Grant in Aid of amount Rs. 16.90 crore was given to States/UTs for the construction of Secondary/Working Standard Laboratories/ tank lorry calibration units and taxi meter testing units and Rs. 32.44 crores were given to DGS&D & India Government, Mumbai for supply of equipments to States/UTs.  Under this scheme during 2011-12 Grant in Aid of amount Rs. 18.69 crore was given to States/UTs for the construction of Secondary/Working Standard Laboratories/ tank lorry calibration units and taxi meter testing units and Rs. 21.95 crores were given to DGS&D for supply of equipments to States/UTs.  An amount of Rs. 49.0 lakh was spent for the training of Legal metrology Officers of States/ UTs / Govt. of India.

During 2012-13 (upto December, 2012) letter of authority for Rs. 23.0 crore was given to DGS&D for supply of equipments to States/UTs.  Rs. 3.50 crore grant in aid has already been given to States/UTs.   An amount of Rs. 6.75 lakh has been spent for the training of Legal metrology Officers of States/ UTs / Govt. of India.

2. Strengthening of Regional Reference Standards Laboratory (RRSLs) and Indian Institute of Legal Metrology (IILM), Ranchi.

The objective of scheme is to strengthen RRSLs and IILM by complimenting the existing facility in mass, volume and length measurement.  The total outlay of the scheme was 23.1 crore.  The scheme aims at providing better testing facilities in force, torque and flow measurement for better consumer protection.

During 2010-11 Rs. 4.3 crore for major works of RRSLs/IILM and 6.3 crore for Machinery & Equipments to RRSLs were spent.

During 2011-12 Rs. 3.83 crore for major works of RRSLs/IILM and 2.5 crore for Machinery & Equipments to RRSLs were spent.

During 2012-13 (upto December, 2012) Rs. 1.43 crore for major works of RRSLs/IILM were spent.

The Highlights of the schemes, objectives and achievement during the year 2011-12 are as follows:

(Rs. In crore)

| S. No. | Name of Scheme/ Programme | Objective/Outcome | Outlay 2011-12 |  |  | Actual Expenditure |  | Quantifiable Deliverables/Physical Outputs | Achievements w.r.t col.6 | Reasons for variation |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | 2 | 3 | 4 |  |  | 5 |  | 6 | 7 | 8 |
|  |  |  | 4 (i) | 4(ii) | 4(iii) |  |  |  |  |  |
|  |  |  | Non-plan Budget | Plan Budget | Complementary Extra-Budgetary Resources | Non-Plan | Plan |  |  |  |
| 1 | Strengthening of Weights & Measures Infrastructure In states/UTs | To strengthen the infrastructure of legal Metrology in States for better enforcement of weights & measures Laws. |  | 59.20 |  |  | 40.95 | Supply of mobile Kits for testing weighbridges, Supply of Working/ Secondary Standard Weights Capacity Measures, Check Measures to various States/UTs. | ----Secondary Standard/Working Standard Weights Capacity Measures, Check Measures to various States/UTs. |  |
| 2 | Strengthening Of RRSL & IILM Ranchi | To strengthen Infrastructures Basis better Consumer Protection |  | 5.24 |  |  | 4.91 | Creation of new Testing facility like Flow measurement etc and to provide testing Equipment for Conducting Electrical testing Equipments. | Renovation work of IILM and Flow Measurement Facility at RRSL |  |

The Highlights of the schemes, objectives and achievement during the year 2012-13 (upto December, 2012) are as follows:

(Rs. In crore)

| S. No. | Name of Scheme/ Programme | Objective/Outcome | Outlay 2012-13 |  |  | Actual Expenditure |  | Quantifiable Deliverables/Physical Outputs | Achievements w.r.t col.6 | Reasons for variation |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | 2 | 3 | 4 |  |  | 5 |  | 6 | 7 | 8 |
|  |  |  | 4 (i) | 4(ii) | 4(iii) |  |  |  |  |  |
|  |  |  | Non-plan Budget | Plan Budget | Complementary Extra-Budgetary Resources | Non-Plan | Plan |  |  |  |
| 1 | Strengthening of Weights & Measures Infrastructure In states/UTs | To strengthen the infrastructure of legal Metrology in States for better enforcement of weights & measures Laws. |  | 52.50 |  |  | 26.62 | Supply of mobile Kits for testing weighbridges, CNG/ LPG testing kits to various States/UTs. | 100 LPG/ CNG kits Supplied, |  |
| 2 | Strengthening Of RRSL & IILM Ranchi | To strengthen Infrastructures Basis better Consumer Protection |  | 5.50 |  |  | 1.43 | Creation of new Testing facility like Flow measurement etc . | Renovation work of IILM and Flow Measurement Facility at RRSL |  |

CONSUMER PROTECTION UNIT

REVIEW OF PAST PERFORMANCE

Review of 2011-12

(Rs. in Crores)

| Sl. No. | Name of the Scheme/ Programme | Objective/ Outcome | Outlay 2011-12 | Actual Expen-diture (31.03.12) | Quantifiable Deliverables | Achievements w.r.t Col (6) (31.03.2012) | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- |
| (1) | (2) | (3) | (4) | (5) | (6) | (7) | (8) |
| 1. | Consumer Protection Cell | The Consumer Protection Cell renders secretarial assistance to the Department in administering the Consumer Protection Act, 1986 and related activities. | 0.50 | 0.2491 | One meeting of the Central Consumer Protection Council (CCPC) held during 2011-12. | CCPC has been reconstituted. | - |
| 2. | Strengthening infrastructure of new NCDRC Building | To provide necessary infrastructural facilities for effective functioning of NCDRC; so as to create consumer friendly environment. | 2.39 | 2.39 | Provision of office modules asper requirement. | Sanction of Rs. 2.39 crore to CPWD has been issued and requisite work has been completed by CPWD. | - |
| 3. | Computerization and computer networking of Consumer Fora (CONFONET) | The project is being implemented through the National Informatics Centre (NIC) on a turnkey basis. Under the project all Consumer Fora in the country are to be computerized. The project would enable consumers to access various types of information relating to their complaints. | 9.59 | 0.53 | Reduction of TSP to one-third. E-learning sessions of new TSPs to be conducted. Staff members of consumer fora to be trained. | The number of TSPs has been reduced to one-third. 50 e-learning sessions have been held for TSPs. Around 1245 staff members of consumer fora have been trained on use of CONFONET application. | - |
| 4. | Strengthening Consumer Fora | The scheme seeks to broadly continue with the objective of the earlier Integrated Project on Consumer Protection (IPCP) scheme to further strengthen the infrastructure of the consumer fora so that minimum level of facilities are provided at each consumer forum in the country, which are required for their effective functioning. | 19.00 | 6.7716 | To complete the infrastructure of those Consumer Fora in 21 States, which were not covered under the IPCP scheme. | Rs. 6.77 crore has been sanctioned under the scheme covering the States of Kerala, Sikkim, Nagaland, Tamil Nadu, Punjab& West Bengal. | -- |
| 5. | National Trade Practices Regulatory Authority (NTPRA) | To create an authority to address the gap in legislation on account of repeal of the Monopolies and Restrictive Trade Practices Act and the Competition Act, 2002 into force. It would also perform important functions of taking proactive measures for protection of consumer interests through training and innovative programmes | 0.01 | NIL | The proposed allocation in respect NTPRA has been deleted as the Legislative Department, Ministry of Law and Justice have turned down the proposed Legislation in view its various provisions overlapping with Competition Act, 2002. |  |  |
|  |  | Grand Total : | 31.49 | 9.9407 |  |  |  |

Review of performance in 2012-13

(Rs. in Crores)

| Sl. No. | Name of the Scheme/ Programme | Objective/ Outcome | Outlay 2012-13 | Actual Expenditure (31.12.12) | Quantifiable Deliverables | Achievements w.r.t Col (6) (31.12.2012) | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- |
| (1) | (2) | (3) | (4) | (5) | (6) | (7) | (8) |
| 1. | Consumer Protection Cell | The Consumer Protection Cell renders secretarial assistance to the Deptt. in administering the Consumer Protection Act, 1986 and related activities. | 0.50 | 0.21 | One meeting of the Central Consumer Protection Council (CCPC) held during 2012-13. | CCPC Meeting has been held on 16.11.2012 at Kochi (Kerala). | - |
| 2. | Computerization and computer networking of Consumer Fora (CONFONET) | The project is being implemented through the National Informatics Centre (NIC) on turnkey basis, which would provide for computerization of all Consumer Fora in the country. The project would allow consumers & others concerned to access information. | 10.10 | 6.60 | Software application development upgradation. Support cell and Project Management at NIC. Supply of new hardware at District Fora. | Rs. 6.60 crore have been released to NIC for carrying out activities under the scheme. | - |
| 3. | Strengthening Consumer Fora | The scheme would further strengthen the infrastructure of the ConsumerFora so as to provide the minimum level of facilities required to make these Fora fully functional. The assistance to all the eligible States/UTs will strengthen the infrastructure of the Consumer Fora for their effective functioning. | 25.00 | 3.84 | To complete the infrastructure of those Consumer Fora, which were not covered under the scheme so far. | Rs. 3.84 crore has been sanctioned under the scheme covering the States of Mizoram, Punjab, West Bengal and Tamil Nadu. |  |
|  |  | Grand Total : | 35.60 | 10.65 |  |  |  |

A review of performance of Plan Scheme “Strengthening of FMC” during 2011-12

Statement of Outlays & Outcomes/Targets (2011-12) (As per the Outcome Budget 2011-12) and Actual Achievement as on 31st March 2012

(Rs. In crore)

| S. No | Name of the Scheme | Objectives/Outcome | Outlays 2011-12* | Quantifiable Deliverables | Process/ Timelines | Achievements w.r.t Col. 5 as on 31st March, 2012 |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Strengthening of FMC |  | 10.00 |  |  |  |
|  | Upgradation of IT facilities | i. Developing market monitoring and surveillance software, ii. Purchase of computer and hardware, iii. IT related assistance to 16 regional Exchanges to upgrade to online trading system and provide for audit trail. | 0.85 | i) Subscription for Commodity Market related data from 3 agencies and high speed data connectivity from one service provider. ii. ii) Purchase of Hardware & software for IT enhancement, development of software for automated intermediary registration iii) Developing the IT capacity of Regional Exchanges iv. Outsourcing of IT related activities | 31.03.2012 | Subscribed for Commodity Market related data from 3 agencies and high speed data connectivity from one service provider. Purchase of Hardware & software for IT enhancement, hiring of outsource staff for IT related work. |
|  | Capacity Building/Training/Consultancies | i. Training of FMC officials, officials of the Exchanges, Government officers and other stakeholder organizations in the commodity derivative market; ii. conducting studies and awarding consultancies in the area of commodity derivative market; supporting pilots / innovative ideas in this field; iii. conducting audit of Exchanges and their members | 4.11 | 100 Capacity Building Programmes 350 Audits of the Books of Accounts of Exchanges and their members | 31.03.2012 | 100 Capacity Building Programmes and 325 Audits of the Books of Accounts of Exchanges and their members |
|  | Awareness and Development Programmes | i. Conduct of awareness programmes every year in association with the Exchanges across the country covering farmers and other stakeholders. ii. Release of publicity material on benefits of commodity futures trading and also for client awareness through print and electronic media. iii. Interactions/ meeting with various stakeholders in the commodity futures markets to understand their difficulties, problems and their needs so as to align/design policies to meet feasible/ desirable objectives. iv. Coordinating with international regulatory bodies for increased adoption of best practices. | 3.16 | 400 awareness programmes, Advertisements in National/ Regional Dailies and 10 stakeholders meet | 31.03.2012 | 818 awareness programmes, 6 advertisements published in 126 Newspapers of Hindi, English, Marathi, Gujarati, Malyalam, Tamil, Telugu, Kannada, Bengali, Assamese and 10 stakeholders meet were organized. |
|  | Price Dissemination Project | Installing price ticker boards at various locations across the country where farmer footfall is high to disseminate spot and futures prices on real time basis to farmers. | 1.34 | 1500 | 31.03.2012 | 670** |
|  | Upgradation of the office infrastructure | Hiring office accommodation, upgrading office infrastructure etc | 0.54 | Not Quantifiable | 31.03.2012 | Not quantifiable |

*Represents RE 2011-12

** Due to shift from conventional price ticker boards to GPRS enabled ticker boards and long time taken in revised tendering process thereof during the current year the installation of price ticker boards has been slow and there has been a shortfall in achievement of physical target.

A review of performance of Plan Scheme “Strengthening of FMC” during 2012-13

Statement of Outlays & Outcomes/Targets (2012-13) (As per the Outcome Budget 2012-13) and Actual Achievement

(Rs. in crore)

| S. No | Name of the Scheme | Objectives/Outcome | Outlays 2012-13* | Quantifiable Deliverables | Process/ Timelines | Achievements w.r.t Col. 5 as on 31st December, 2012 |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Strengthening of FMC |  | 15.00 |  |  |  |
|  | Upgradation of IT facilities | i. Developing market monitoring and surveillance software, ii. Purchase of computer and hardware, ii. IT related assistance to 16 regional Exchanges to upgrade to online trading system and provide for audit trail. | 1.40 | i. Subscription for Commodity Market related data from 3 agencies and high speed data connectivity from one service provider. ii. Purchase of Hardware & software for IT enhancement, development of software for automated intermediary registration iii. IT related assistance to 3 Exchanges | 31.03.2013 | Subscribed for high speed data connectivity from one service provider. Purchase of Hardware & software for IT enhancement. |
|  | Capacity Building/Training/Consultancies | i. Organising capacity building programmes for policy makers and training programmes for the staff of FMC and the Exchanges , participation in foreign trainings and meetings on commodity futures markets ii. Conducting audits of Exchanges and their members iii. Awarding consultancies/ studies in area of concern to the FMC and the commodity futures market and engaging professionals in necessary areas | 4.90 | i. 100 Capacity Building programmes ii. 400 Inspection of books of accounts of commodity Exchanges and members of the Exchanges iii. Consultancy assignment as per requirement | 31.03.2013 | i.74 Capacity Building programmes ii .368 Inspection of Books of Accounts of commodity Exchanges and members of Exchanges iii. Consultancy for Technical Audit of Price Ticker Boards awarded to NABCONS and consultancy for evaluation study for 11th year plan scheme Strengthening of FMC awarded to SANTEK consultants Pvt. Ltd. |
|  | Awareness and Development Programmes | i. Conduct of awareness programmes every year in association with the Exchanges and other partner organizations across the country covering farmers and other stakeholders. ii. Release of publicity material on benefits of commodity futures trading and also for client awareness through print and electronic media. iii. Interactions/ meeting with various stakeholders in the commodity futures markets to understand their difficulties, problems and their needs so as to align/design policies to meet feasible/ desirable objectives. iv. Coordinating with international regulatory bodies for increased adoption of best practices. | 3.20 | i. 500 Awareness Programmes ii. 15 Stakeholders’ meets iii. Advertisements in National/ regional Dailies | 31.03.2013 | 609 Awareness programmes and 7 stakeholders meetings organized. |
|  | Price Dissemination Project | Installing price ticker boards at identified locations with heavy farmer footfall to disseminate spot and futures prices on real time basis to farmers. | 4.90 | 1000 | 31.03.2013 | 409 price ticker boards were installed at various locations during the period from April to December, 2012. |
|  | Upgradation of the office infrastructure | Hiring office accommodation, upgrading office infrastructure etc | 0.60 | Not Quantifiable | 31.03.2013 | Not Quantifiable |

*Represents BE 2012-13

Review of Past Performance of NTH

NTH Plan Scheme:

NTH has been implementing a Plan Scheme for providing services to the industries in the field of testing, calibration and quality evaluation of materials and products of all engineering  branches except pharmaceuticals, arms and ammunition. The objective of the NTH XIth  Plan Scheme is to render assistance for improving the quality of Indian engineering products so as to meet the national / international standards for their acceptability in the global market in order to keep pace with the tremendous technological changes taking place worldwide.

Achievements w.r.t. Outcome Budget 2011-12 & 2012-13( up to December'2012) in respect of NTH Plan Scheme are given in Annexures I & II.

Annexure I

Review of Past Performances of NTH

Objectives of NTH Plan Scheme, Targets and Achievements during 2011-12

(Rs. in Crore)

| Sl. no. | Name of the scheme/Programme | Objective/Outcome | Outlay 2011-12 | Actual Expenditure incurred | Quantifiable Deliverables | Achievements w.r.t column 6 | Reasons for variation in achievements |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 |
|  | National Test House | To provide services to the industries in the field of testing and quality evaluation of engineering materials and products of all engineering branches except drugs, arms & ammunition | BE—21.22 ( Break up Revenue—3.00 Capital—18.22 RE—18.00 ( Break up Revenue—2.38 Capital—15.62 | 16.86 ( Break up Revenue—2.02 Capital—14.84) | Revenue Head i) Recurring Expenditure including Information Technology Capital Head i) Procurement of new Machinery & Equipments ii) Major Works ( Land & Building) | Revenue Head 84.87 % of RE Capital Head i) 95.01% of RE | Revenue Head Less achievements as Domestic travel Expenditure and Foreign Travel Expenditure kept restrained as austerity measure Capital Head Less achievements in utilization of major works due to estimated demand from CPWD was less under the head Major Works |

Annexure II

Objectives of NTH Plan Scheme, Targets and Achievements during 2012-13( up to December'2012)

(Rs. in Crore)

| Sl. No. | Name of the Scheme/ Programme | Objective/Outcome | Outlay 2012-13 (Plan) | Actual Expdtr. Incurred | Quantifiable Deliverables | Achievements w.r.t. Col 6 | Reasons for variation in achievements w.r.t. Col 6 |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | National Test House | To provide services to the industries in the field of testing and quality evaluation of engineering materials and products of all engineering branches except drugs, arms 7 ammunition | BE—18.00 ( Break up Revenue—3.30 Capital—14.70) RE-13.00 (Break up Revenue-2.50 Capital-10.50 | 8.31 ( Break up Revenue—1.61 Capital—6.70 ) | Revenue Head i) Recurring Expenditure including Information Technology Capital Head i) Procurement of new Machinery & Equipments ii) Major Works( Land & Building) | Revenue Head 64.40% of RE on the basis of 9 months Capital Head i) 56 % against RE under the head ME( Actual RE—2.50, Actual expenditure-1.40 ii) 66 % against RE under the head Major Works ( Land & Building) ( Actual RE—8.00 Authorized to CPWD-5.30) |  |

CONSUMER AWARENESS SCHEME

Annexure

The highlighting covering objectives, targets and achievements in the field of consumer awareness during the year 2011-12 are tabulated as under:-

(Rs. in crore)

| S. No. | Name of the Scheme /Programme | Objective/ Outcome | Outlay 2011-12 | Expenditure during 2011-12 | Quantifiable Deliverables | Achievements w.r.t. (Col 6) | Reason for variation |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 |
| 1 | Consumer Awareness | Empowerment of consumer by dissemination of information regarding consumer rights and responsibilities through multi media publicity campaign “Jago Grahak Jago | 87.23 | 85.73 | i) Print advertisements through national and regional newspapers. ii) Release of audio spots through AIR and Private FM Channel - Release of TV spots through DD Network, Private C&S channels - Outdoor Publicity by banners, hoardings etc. - Participation in Trade Fairs/Exhibitions | Target achieved | N.A. |

CONSUMER AWARENESS SCHEME

Annexure

The highlighting covering objectives, targets and achievements in the field of consumer awareness during the year 2012-13 are tabulated as under:-

(Rs. in crore)

| S. No. | Name of the Scheme /Programme | Objective/ Outcome | Outlay 2012-13 | Expenditure during 2012-13 upto Dec. 2012 | Quantifiable Deliverables | Achievements w.r.t. (Col 6) | Reason for variation |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 |
| 1 | Consumer Awareness | Empowerment of consumer by dissemination of information regarding consumer rights and responsibilities through multimedia publicity campaign “Jago Grahak Jago” | 89.00 | 55.69 | - Print advertisements through national and regional newspapers - Release of audio spots through AIR and Private FM Channels - Release of TV spots through DD Network,, ,Private C&S channels - Outdoor Publicity by banners, hoardings etc. - Participation in Trade Fairs/Exhibitions. - Development of Consumer Awareness Index. | Target achieved | N.A. |

| # CHAPTER - V |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| # FINANCIAL REVIEW |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| This chapter on financial review covers overall trends in expenditure viz-a-viz Budget Estimates and Revised Estimates since 2009-10. Data has been segregated scheme wise. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| TRENDS IN EXPENDITURE VIZ-A-VIZ BUDGET ESTIMATES/REVISED ESTIMATES IN RECENT YEARS. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| PLAN |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  | ( Rs. in Crore ) |  |  |  |
| No. | Scheme | Budget Estimates |  |  |  |  | Revised Estimates |  |  |  | Actual Expenditure |  |  |  |  |
|  |  | 2009-2010 | 2010-2011 | 2011-2012 | 2012-2013 | 2013-2014 | 2009-2010 | 2010-2011 | 2011-2012 | 2012-2013 | 2009-2010 | 2010-2011 | 2011-2012 | 2012-2013 (up to 31.12.2012) |  |
| 1 | Consumer Protection and Consumer Education, Training/ HRD/Capacity Building and Consumer Awareness | 83.47 | 84.23 | 89.18 | 86.69 | 80.06 | 74.62 | 79.38 | 81.31 | 55.86 | 76.35 | 87.75 | 88.94 | 60.59 |  |
| 2 | National Test House | 13.50 | 15.45 | 19.00 | 16.20 | 16.87 | 12.95 | 15.45 | 15.98 | 11.40 | 13.47 | 15.67 | 16.86 | 8.30 |  |
| 3 | Consumer Disputes Redressal Commission | 9.90 | 3.44 | 0.00 | 0.00 | 0.00 | 9.90 | 2.39 | 2.39 | 0.00 | 9.80 | 0.00 | 2.39 | 0.00 |  |
| 4 | Strengthening Price Monitoring Cell | -- | -- | -- | 2.70 | 1.65 | -- | -- | -- | 0.68 | -- | -- | -- | -- |  |
| 5 | Strengthening Consumer Fora, Consumer Help line etc. | 16.21 | 20.14 | 21.65 | 36.61 | 41.38 | 10.50 | 14.94 | 11.00 | 9.57 | 11.72 | 14.35 | 10.21 | 7.03 |  |
| 6 | Setting up of Gold Hallmarking and Assaying Centres in India/ Standardization & Quality Control | 14.62 | 2.74 | 2.17 | 9.00 | 4.74 | 1.33 | 1.32 | 2.07 | 1.80 | 1.21 | 1.53 | 2.28 | 0.60 |  |
| 7 | Weights & Measures | 34.20 | 56.25 | 58.00 | 52.20 | 57.51 | 30.20 | 54.75 | 43.56 | 48.26 | 26.89 | 59.45 | 45.86 | 27.54 |  |
| 8 | Regulation of Markets | 16.20 | 15.75 | 12.50 | 13.50 | 14.58 | 8.10 | 9.68 | 9.00 | 7.20 | 6.79 | 9.17 | 9.08 | 4.99 |  |
| 9 | Lump sum provision for schemes in NE | 20.90 | 22.00 | 22.50 | 24.10 | 24.21 | 16.40 | 20.09 | 19.69 | 15.23 | * | * | * | * |  |
|  | Total | 209.00 | 220.00 | 225.00 | 241.00 | 241.00 | 164.00 | 198.00 | 185.00 | 150.00 | 146.23 | 187.92 | 175.62 | 109.05 |  |

*Expenditure is included in relevant Functional Heads.

Note: - 1. Expenditure for the year 2012-13(upto 31.12.2012) includes amount of Rs. 53.95 crores authorized in favour of other Ministries/Departments.

2. Expenditure during 2012-13 (upto 31.12.2012) is as booked by Principal Accounts Office.

TRENDS IN EXPENDITURE VIS-A-VIS BUDGET ESTIMATES/REVISED ESTIMATES DURING 2012-13

## PLAN

During the financial year 2012-13 a total allocation of Rs. 241.00 crore was made in BE 2012-13 which was subsequently reduced to Rs.150.00   crore at RE stage. The actual expenditure as on 31.12.2012 is Rs. 109.05 crore which constitutes 72.70% of RE of Rs. 150.00 crores during 2012-13. The schemes wise and major head wise allocation and expenditure is given below.

(Rs. in Crore)

| Sr.No. | Scheme etc. | Major Head | B.E. 2012-2013 | RE 2012-2013 | Actual expenditure 2012-13 upto Dec. 12 | B.E. 2013-2014 |
| --- | --- | --- | --- | --- | --- | --- |
| 1. | Consumer Protection, Consumer Awareness and State Consumer Helpine. | 3456 3601 3602 | 86.91 34.48 1.91 | 56.08 8.78 0.57 | 60.81 6.73 0.08 | 80.06 38.98 2.40 |
| 2. | Strengthening Price Monitoring Cell | 3456 3601 3602 | 1.65 1.03 0.02 | 0.40 0.24 0.04 | -- -- -- | 0.85 0.54 0.26 |
| 3. | Weights & Measures, Establishment of Laboratories | 5475 3475 3601 3602 | 4.20 22.50 25.00 0.50 | 1.67 21.59 24.50 0.50 | 1.43 23.11 3.00 -- | 3.00 35.01 19.25 0.25 |
| 4. | National Test House | 3425 5425 | 3.30 12.90 | 2.50 8.90 | 1.59 6.71 | 2.50 14.37 |
| 5. | Forward Markets Commission | 3475 | 13.50 | 7.20 | 4.99 | 14.58 |
| 6. | Lumpsum provision for North East project/Scheme for the benefit of North East Region | 2552* 4552* | 21.50 2.60 | 13.63 1.60 | * * | 21.83 2.38 |
| 7. | Setting up of Gold Hall Marking/ Assaying Centres in India, Standardization & Quality Control | 2852 | 9.00 | 1.80 | 0.60 | 4.74 |
|  |  |  | 241.00 | 150.00 | 109.05 | 241.00 |

*Expenditure on NER Schemes including Sikkim is included in various functional heads.

Notes: - Expenditure of Rs.  109.05 crores during 2012-13 (upto 31.12.2012) as reported by Principal Accounts office includes amount of Rs. 53.95 crores authorized in favour of other Ministries/Departments.

### NON-PLAN

During the financial year 2012-13 an allocation of Rs. 361.29 crore was made in BE 2012-13 which was subsequently reduced to Rs. 331.30 crore at RE stage. The actual expenditure as on 31.12.2012 is Rs. 266.43 crore (net) which constitutes 80.42% of total allocation of RE of 2012-13. The scheme wise and major head wise allocation and expenditure is given below.

(Rs. in Crore)

| Sr.No. | Scheme | Major Head | B.E. 2012-2013 | RE 2012-2013 | Actual expenditure* 2012-13 upto Dec. 12 | B.E. 2013-2014 |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Secretariat Economic Services | 3451 | 16.86 | 15.83 | 12.78 | 17.31 |
| 2 | National Test House | 3425 | 25.72 | 26.19 | 21.73 | 28.29 |
| 3 | Subsidies | 2408 | 300.00 | 270.00 | 217.48 | 250.00 |
| 4 | Consumer Protection | 3456 | 7.59 | 8.53 | 6.38 | 8.82 |
| 5 | Regulation of Weights & Measures | 3475 | 4.63 | 4.52 | 3.60 | 4.89 |
| 6 | International Cooperation | 3475 | 0.11 | 0.11 | -- | 0.15 |
| 7 | Regulation of Markets | 3475 | 6.38 | 6.12 | 4.46 | 6.44 |
| 8 | Project under Consumer Welfare Fund | 3456 3601 3602 | 18.30 3.00 0.50 | 13.30 18.00 0.50 | 5.77 17.50 -- | 15.30 30.00 0.50 |
| 9 | Deduct Refund* |  | (-)21.80 | (-) 31.80 | (-) 23.27 | (-) 45.80 |
|  | Total |  | 361.29 | 331.30 | 266.43 | 315.90 |

*The deduct entry represents the budgetary provision made under Consumer Welfare Fund which is being met out of  Reserve Fund created for this purpose. The receipt is being accounted for under Major Head 8229- Development and Welfare Funds, 123 - Consumer Welfare Fund.

Scheme-wise, Major Head-wise Financial Requirements/ Budgetary Outlay

(Rs. in Crore)

| Programme |  | BE 2011-12 |  |  | RE 2011-2012 |  |  | BE 2012-2013 |  |  | RE 2012-2013 |  |  | BE 2013-2014 |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Major Head | Plan | Non-Plan | Total | Plan | Non-Plan | Total | Plan | Non-Plan | Total | Plan | Non-Plan | Total | Plan | Non-Plan | Total |
| 1. Secretariat Economic Services | 3451 | -- | 16.42 | 16.42 | -- | 15.27 | 15.27 | -- | 16.86 | 16.86 | -- | 15.83 | 15.83 | -- | 17.31 | 17.31 |
| 2. .Lump sum provision for projects /Schemes for North Eastern Region (Revenue Section) | 2552 | 20.04 | -- | 20.04 | 17.67 | -- | 17.67 | 21.50 | -- | 21.50 | 13.63 | -- | 13.63 | 21.83 | -- | 21.83 |
| 3. National Test House | 3425 | 3.00 | 22.26 | 25.26 | 2.38 | 23.84 | 26.22 | 3.30 | 25.72 | 29.02 | 2.50 | 26.19 | 28.69 | 2.50 | 28.29 | 30.79 |
| 4. Consumer Industries Bureau of Indian Standards | 2852 | 2.17 | -- | 2.17 | 2.07 | -- | 2.07 | 9.00 |  | 9.00 | 1.80 | -- | 1.80 | 4.74 | -- | 4.74 |
| 5. Subsidy for meeting losses on import of pulses | 2408 | -- | 300.00 | 300.00 | -- | 250.00 | 250.00 | -- | 300.00 | 300.00 | -- | 270.00 | 270.00 | - | 250.00 | 250.00 |
| 6. Consumer Protection, Consumer Awarness. etc. | 3456 3601 3602 | 89.18 19.15 0.50 | 6.57 -- -- | 95.75 19.15 0.50 | 81.31 9.50 0.50 | 6.97 -- -- | 88.28 9.50 0.50 | 86.69 32.98 1.63 | 7.59 -- -- | 94.28 32.98 1.63 | 55.86 7.73 0.35 | 8.53 -- -- | 64.39 7.73 0.35 | 80.06 36.48 1.90 | 8.82 -- -- | 88.88 36.48 1.90 |
| 7. Strengthening Price Monitoring cell | 3456 3601 3602 | -- -- -- | -- -- -- | -- -- -- | -- -- -- | -- -- -- | -- -- -- | 1.65 1.03 0.02 | -- -- -- | 1.65 1.03 0.02 | 0.40 0.24 0.04 | -- -- -- | 0.40 0.24 0.04 | 0.85 0.54 0.26 | -- -- -- | 0.85 0.54 0.26 |
| 8. Regulation of Weights & Measures | 3475 3601 3602 | 35.74 16.76 0.50 | 4.02 -- -- | 39.76 16.76 0.50 | 19.43 16.76 -- | 4.26 -- -- | 23.69 16.76 -- | 22.50 25.00 0.50 | 4.63 -- -- | 27.13 25.00 0.50 | 21.59 24.50 0.50 | 4.52 -- -- | 26.11 24.50 0.50 | 35.01 19.25 0.25 | 4.89 -- -- | 39.90 19.25 0.25 |
| 9. International Cooperation | 3475 | -- | 0.10 | 0.10 | -- | 0.10 | 0.10 | -- | 0.11 | 0.11 | -- | 0.11 | 0.11 | -- | 0.15 | 0.15 |
| 10. Regulation of Markets | 3475 | 12.50 | 6.19 | 18.69 | 9.00 | 5.87 | 14.87 | 13.50 | 6.38 | 19.88 | 7.20 | 6.12 | 13.32 | 14.58 | 6.44 | 21.02 |
| 11. Capital outlay on General Economic services (W&M) | 5475 | 5.00 | -- | 5.00 | 7.37 | -- | 7.37 | 4.20 | -- | 4.20 | 1.67 | -- | 1.67 | 3.00 | -- | 3.00 |
| 12. Capital outlay on scientific & other Environmental Research (NTH) | 5425 | 16.00 | -- | 16.00 | 13.60 | -- | 13.60 | 12.90 | -- | 12.90 | 8.90 | -- | 8.90 | 14.37 | -- | 14.37 |
| 13. Lump sum provision for Projects/ scheme for North Eastern Region (Capital Section) | 4552 | 2.46 | -- | 2.46 | 2.02 | -- | 2.02 | 2.60 | -- | 2.60 | 1.60 | -- | 1.60 | 2.38 | -- | 2.38 |
| 14. Project under Consumer Welfare Fund | 3456 3601 3602 | -- -- -- | 16.30 3.00 0.50 | 16.30 3.00 0.50 | -- -- -- | 18.30 12.50 0.50 | 18.30 12.50 0.50 | -- -- -- | 18.30 3.00 0.50 | 18.30 3.00 0.50 | -- -- -- | 13.30 18.00 0.50 | 13.30 18.00 0.50 | -- -- -- | 15.30 30.00 0.50 | 15.30 30.00 0.50 |
| Deduct Refund | 3456 3601 3602 | -- -- -- | -16.30 -3.00 -0.50 | -16.30 -3.00 -0.50 | -- -- -- | -18.30 -12.50 --0.50 | -18.30 -12.50 -0.50 | -- -- -- | -18.30 -3.00 -0.50 | -18.30 -3.00 -0.50 | -- -- -- | -13.30 -18.00 -0.50 | -13.30 -18.00 -0.50 | -- -- -- | -15.30 -30.00 -0.50 | -15.30 -30.00 -0.50 |
| 15. Construction of building of NCDRC | 5475 | -- | -- | -- | 2.39 | -- | 2.39 | -- | -- | -- | -- | -- | -- | -- | -- | -- |
| 16. Consumer Helpline | 3456 3601 3602 | 1.60 0.40 | -- -- | 1.60 0.40 | 1.00 -- | -- -- | 1.00 -- | 0.27 1.45 0.28 | -- -- -- | 0.27 1.45 0.28 | 0.22 1.05 0.22 | -- -- -- | 0.22 1.05 0.22 | -- 2.50 0.50 | -- -- -- | -- 2.50 0.50 |
| Total |  | 225.00 | 355.56 | 580.56 | 185.00 | 306.31 | 491.31 | 241.00 | 361.29 | 602.29 | 150.00 | 331.30 | 481.30 | 241.00 | 315.90 | 556.90 |

Object head-wise Classification

(Rs. in lakh)

| REVENUE SECTION | BE 2011-12 |  |  | RE 2011-12 |  |  | BE 2012-13 |  |  | RE 2012-13 |  |  | BE 2013-14 |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Plan | Non-Plan | Total | Plan | Non-Plan | Total | Plan | Non-Plan | Total | Plan | Non-Plan | Total | Plan | Non-Plan | Total |
| Salaries | -- | 4494.00 | 4494.00 | -- | 4569.00 | 4569.00 | 20.00 | 4935.00 | 4955.00 | -- | 5001.00 | 5001.00 | -- | 5402.00 | 5402.00 |
| Medical Treatment | -- | 91.00 | 91.00 | -- | 91.70 | 91.70 | -- | 97.30 | 97.30 | -- | 81.17 | 81.17 | -- | 84.39 | 84.39 |
| OTA | -- | 11.25 | 11.25 | -- | 10.05 | 10.05 | -- | 11.24 | 11.24 | -- | 9.54 | 9.54 | -- | 10.48 | 10.48 |
| Wages | -- | 8.06 | 8.06 | -- | 38.06 | 38.06 | -- | 67.25 | 67.25 | -- | 58.98 | 58.98 | -- | 72.61 | 72.61 |
| Office Expenses | 250.50 | 616.40 | 866.90 | 188.00 | 592.70 | 780.70 | 428.00 | 647.40 | 1075.40 | 241.00 | 632.87 | 873.87 | 256.50 | 678.60 | 935.10 |
| Rent Rates & Taxes | 10.00 | 10.00 | 20.00 | 10.00 | 10.00 | 20.00 | 5.00 | 11.00 | 16.00 | 0.50 | 10.00 | 10.50 | 9.00 | 11.00 | 20.00 |
| Domestic Travel Expenses | 135.00 | 99.78 | 234.78 | 86.17 | 98.03 | 184.20 | 102.00 | 100.77 | 202.77 | 73.50 | 76.12 | 149.62 | 94.00 | 94.50 | 188.50 |
| Foreign Travel Expenses | 105.00 | 50.30 | 155.30 | 100.00 | 44.00 | 144.00 | 122.00 | 65.00 | 187.00 | 44.00 | 58.70 | 102.70 | 113.00 | 63.42 | 176.42 |
| Publication | -- | 11.32 | 11.32 | -- | 11.32 | 11.32 | -- | 12.45 | 12.45 | -- | 9.12 | 9.12 | -- | 13.60 | 13.60 |
| Grant-in-aid General | 733.00 | 1748.10 | 2481.10 | 648.78 | 2948.10 | 3596.88 | 2498.25 | 1998.10 | 4496.35 | 707.20 | 3049.13 | 3756.33 | 3477.25 | 4349.10 | 7826.35 |
| Grants for creation of Capital Assets | 4160.00 | 202.00 | 4362.00 | 2896.55 | 152.00 | 3048.55 | 5966.75 | 152.00 | 6118.75 | 3483.81 | 152.00 | 3635.81 | 4083.75 | 201.00 | 4284.75 |
| Subsidy | -- | 30000.00 | 30000.00 | -- | 25000.00 | 25000.00 | -- | 30000.00 | 30000.00 | -- | 27000.00 | 27000.00 | -- | 25000.00 | 25000.00 |
| Contribution | 10.00 | 30.00 | 40.00 | 11.00 | 30.00 | 41.00 | 15.00 | 31.00 | 46.00 | 15.00 | 22.00 | 37.00 | 17.00 | 32.69 | 49.69 |
| Other charges | 939.00 | 31.93 | 970.93 | 684.00 | 30.93 | 714.93 | 465.00 | 32.12 | 497.12 | 312.00 | 31.41 | 343.41 | 425.00 | 32.05 | 457.05 |
| Other Administrative Expenses | 30.00 | 16.37 | 46.37 | 25.00 | 20.12 | 45.12 | 28.00 | 23.50 | 51.50 | 18.50 | 17.19 | 35.69 | 27.00 | 21.72 | 48.72 |
| Supply & Material | -- | 15.50 | 15.50 | -- | 15.00 | 15.00 | -- | 15.50 | 15.50 | -- | 11.00 | 11.00 | -- | 12.10 | 12.10 |
| Advertising and Publicity | 8598.00 | 5.00 | 8603.00 | 8722.50 | 5.00 | 8727.50 | 8650.00 | 5.00 | 8655.00 | 5720.99 | 1.00 | 5721.99 | 7042.00 | 1.10 | 7043.10 |
| Professional Services | 240.50 | 26.38 | 266.88 | 155.00 | 26.38 | 181.38 | 340.00 | 29.50 | 369.50 | 127.50 | 28.36 | 155.86 | 215.50 | 35.55 | 251.05 |
| Secret Service Expenditure | -- | 1.00 | 1.00 | -- | 1.00 | 1.00 | -- | 0.90 | 0.90 | -- | 0.90 | 0.90 | -- | 0.90 | 0.90 |
| Machinery and Equipment | 3774.00 | 7.50 | 3781.50 | 2195.00 | 7.50 | 2202.50 | 2300.00 | 7.80 | 2307.80 | 2300.00 | 5.09 | 2305.09 | 3775.00 | 5.60 | 3780.60 |
| Minor Works | -- | 37.57 | 37.57 | -- | 37.57 | 37.57 | -- | 41.35 | 41.35 | -- | 30.80 | 30.80 | -- | 29.84 | 29.84 |
| Information Technology i) Office Expenses ii) Professional Services | 1159.00 10.00 | 22.54 -- | 1181.54 10.00 | 230.00 10.00 | 22.54 -- | 252.54 10.00 | 1180.00 10.00 | 24.82 | 1204.82 10.00 | 735.00 4.00 | 23.75 -- | 758.75 4.00 | 2576.00 14.00 | 17.75 -- | 2593.75 14.00 |
| Deduct Refund | -- | -1980.00 | -1980.00 | -- | (-)3130.00 | (-)3130.00 | - | (-)2180.00 | (-)2180.00 | -- | (-) 3180.00 | (-) 3180.00 |  | (-)4580.00 | (-)4580.00 |
| Total Revenue Section | 20154.00 | 35556.00 | 55710.00 | 15962.00 | 30631.00 | 46593.00 | 22130.00 | 36129.00 | 58259.00 | 13783.00 | 33130.13 | 46913.13 | 22125.00 | 31590.00 | 53715.00 |
| CAPITAL SECTION |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Machinery and Equipments | 794.00 | -- | 794.00 | 710.00 | -- | 710.00 | 700.00 | -- | 700.00 | 250.00 | -- | 250.00 | 600.00 | -- | 600.00 |
| Major Works | 1552.00 | -- | 1552.00 | 1828.00 | -- | 1828.00 | 1270.00 | -- | 1270.00 | 967.00 | -- | 967.00 | 1375.00 | -- | 1375.00 |
| Total Capital Section | 2346.00 | -- | 2346.00 | 2538.00 | -- | 2538.00 | 1970.00 | -- | 1970.00 | 1217.00 | -- | 1217.00 | 1975.00 | -- | 1975.00 |
| Grand Total | 22500.00 | 35556.00 | 58056.00 | 18500.00 | 30631.00 | 49131.00 | 24100.00 | 36129.00 | 60229.00 | 15000.00 | 33130.13 | 48130.13 | 24100.00 | 31590.00 | 55690.00 |

Department of Consumer Affairs

Ministry of Consumer Affairs, food and Public Distribution

UTILIZATION CERTIFICATES (U.Cs) OUTSTANDING IN RESPECT OF GRANTS/LOANS RELEASED UP TO 31ST MARCH 2011 (AS ON 31STDECEMBER, 2012 IN RESPECT OF CONSUMER WELFARE FUND

| Year | No. of UC.s outstanding in respect of grants released up to March 2011 | Amount involved (in Rs. ) | No. of U.C.s received | Amount involved in respect of U.C.s received | No. of U.C.s outstanding as on 31.12.2012 | Amount involved on outstanding U.C.s (In Rs.) |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | 2 | 3 | 4 | 5 | 6 | 7 |
| 1996-97 | 8 | 3,23,500 | - | - | 8 | 3,23,500 |
| 1997-98 | 5 | 1,66,500 | - | - | 5 | 1,66,500 |
| 1998-99 | 4 | 1,35,000 | - | - | 4 | 1,35,000 |
| 1999-2000 | 1 | 22,500 | - | - | 1 | 22,500 |
| 2000-01 | 3 | 86,400 | - | - | 3 | 8,6,400 |
| 2001-02 | 2 | 90,000 | - | - | 2 | 90,000 |
| 2002-03 | - | - | - | - | - | - |
| 2003-04 | 2 | 2,79,000 | - | - | 2 | 2,79,000 |
| 2004-05 | 4 | 6,66,000 | - | - | 4 | 6,66,000 |
| 2005-06 | - | - | - | - | - | - |
| 2006-07 | 11 | 24,00,000 | 2 | 5,00,000 | 9 | 19,00,000 |
| 2007-08 | 2 | 45,8,900 | 1 | 2,08900 | 1 | 2,50,000 |
| 2008-09 | - | - | - | - | - | - |
| 2009-10 | 28 | 9,38,40,258 | 26 | 9,34,92,258 | 2 | 3,48,000 |
| 2010-11 | 27 | 89899620 | 25 | 84855620 | 2 | 5044000 |
| Total | 97 | 188367678 | 54 | 179056778 | 43 | 9310900 |

## CHAPTER VI

# REVIEW OF PERFORMANCE OF AUTONOMOUS BODY

This chapter reviews the performance of the autonomous body under the administrative control of Department of Consumer Affairs. There is only one autonomous body under the Department of Consumer Affairs namely Bureau of Indian Standards (BIS). BIS was set up on 01st April 1987 as a statutory body taking over the function of the erstwhile Indian Standards Institution (ISI). The Bureau has completed twenty five years of operation on 31st March 2012.

Performance of Bureau of Indian Standards (BIS)

As on 30 November 2012, as many as 18859--standards representing specifications, methods of test, definitions of technical terms, codes of practice, etc., covering various sectors in the industrial and agricultural fields, were in force.

Certification Marking Scheme continued to progress and as on 30 November 2012, as many as 25816 licences were in operation. The actual income through Product Certification during 2012-13 (upto 30th November 2012) is given in Table 1.

BIS is also operating the following Management System Certification Schemes.  The Schemes have progressed during the year.  The number of licenses in operation under each Scheme as on 30 November 2012 is shown against each:

| i) | Quality Management System Certification as per ISIISO 9001 | -- | 945 |
| --- | --- | --- | --- |
| ii) | Environmental Management Systems Certification as per IS/ISO 14001 | -- | 171 |
| iii) | Occupational Health and Safety Management System Certification as per IS 18001 | -- | 66 |
| iv) | The Hazard Analysis and Critical Control Point (HACCP) integrated with Quality Management System certification for food safety | -- | 48 |
| v) | Food Safety Management Systems as per IS/ISO 22000 | -- | 7 |
| vi) | Service Quality Management Systems as per IS 15700 | -- | 5 |

The actual income through Management System Certification during 2012-13 (upto 30 November 2012) is given in Table 1.

BIS also operates a Hallmarking (Gold/Silver/artifacts) Certification scheme. As on 30 November 2012, as many as 10778 licences (Gold – 10115 & Silver – 663) were in operation under the Hallmarking scheme.  The number of BIS recognized assaying and hallmarking centres has increased to 197 as on 30 November 2012.  The income from Hallmarking activity for 2012-13 (upto 30 November 2012) is given in Table 1.

A Small Scale Industries Facilitation Centre helps in dissemination of information relating to BIS activities in various fields, in particular the Product and Quality System Certification Schemes. This service has received appreciation of the small scale industrial units and entrepreneurs

The physical targets and achievements of BIS during 2011-12 and 2012-13 are as given below:-

| S.No. |  | Targets 2011-12 | Achievement 2011-12 | Targets 2012-13 (upto 31 Dec 2012) | Achievement 2012-13 (upto 30th Nov. 2012) |
| --- | --- | --- | --- | --- | --- |
| i) | Standards Formulated | 330 | 410 | 200 | 320 |
| ii) | Grant of New Licence |  |  |  |  |
| a. | Product Certification | 2800 | 3099 | 2230 | 1782 |
| b. | System Certification | 200 | 150 | 150 | 54 |
| c. | Hallmarking of Jewellery | 1500 | 1811 | 1050 | 1213 |

Earnings during the year: - The Income generated by BIS during the year (upto 30th November, 2012) from various activities is as given below.

Table - 1

FINANCIAL TERMS

(Rupees in lakhs)

| S. No. |  | Targets 2012-13 | Achievements 2012-13 (upto 30/11/12) |
| --- | --- | --- | --- |
| (i) | Sale of Indian Standards | 958.32 | 856.80 |
| (ii) | Certification Marks Income |  |  |
| (a) | Product Certification | 21270.60 | 15236.57 |
| (b) | System Certification | 280.50 | 158.76 |
| (.c) | Hallmarking of Gold Jewellery | 1150.00 | 947.19 |
| (d) | Conference, Consultancy and Training Fee | 135.00 | 61.85 |
| (e) | Miscellaneous | 295.00 | 158.64 |
| (f) | Interest Income | 1000.00 | NIL* |

* To be finalized in the year ended Annual Accounts since it is calculated on accrual basis

The financial position of BIS for the financial year 2011-12 and for the period from 01st April 2012 to 30th November 2012 is indicated below:

(Rupees in lakhs)

| S. No. |  | 2011-12 | Achievements 2012-13 (upto 30/11/12) |
| --- | --- | --- | --- |
| 1 | Income | 26327.67 | 17419.81 |
| 2 | Expenditure | 16970.32 | 10907.09 |
| 2.1 | Operational Expenditure |  |  |
| 3 | Surplus | 9357.35 | 6512.72 |