# DEPARTMENT OF CONSUMER AFFAIRS

# Executive Summary

A system of performance budgeting by Ministries handling development programmes was introduced in 1969 on the basis of the recommendations of the Administrative Reforms Commission. A need was felt to address certain weaknesses that had crept in the performance budget documents such as lack of clear one-to-one relationship between the financial budget and the performance budget and inadequate target-setting in physical terms for the ensuing year.  There has also been a growing concern about the need to track not just the intermediate physical “outputs” that are more readily measurable but also the “outcomes”, which are the end objectives of State intervention.

In March, 2006, Outcome Budget 2006-07 and Performance Budget 2005-06 were presented in Parliament by Department of Consumer Affairs.  These documents covered plan schemes and significant portion on non-plan expenditure and internal and extra budgetary resources as well.  With effect from the year 2007-08 it has been decided to merge the Performance Budget with the Outcome Budget.  Thus, there is now a single document i.e. Outcome Budget for 2008-09 and onwards.  This document broadly indicates   physical dimensions of the financial budget indicating the actual physical performance in 2009-10, performance  in 2010-11  and targeted  performance  during 2011-12.  An attempt  has  also  been made to enumerate  the activities  and schemes  of the Department,  their  financial  outlays,  physical  outputs  and the projected  outcomes.

In the long  process of conversion  of outlays  into  outcomes,  there are several  intermediate  stages  and complementary  resources  which  are  also  required  for  achieving  intended  outcomes.  The  cause  and effect  chain  is not  always  direct  and several  factors  come  into play  that  influence  the actual  outcomes,  not  just  the outlays  earmarked.  Outcomes  are  the end  products  and results  of various Government initiatives  and interventions,  including those involving  partnership  with  the State  Governments,  Public  Sector  Undertaking,  Autonomous  Bodies  and the community.  They  involve  much  more than  mere “outputs”, since  they  cover  the quality  and effectiveness of the goods  and services  produced  as  a consequence  of an activity  under  a  scheme or programme.

In the modern industrial society, consumer occupies a pivotal place.  With the advent of globalization, the multi national companies are competing with local companies in the matter of production as well as rendering of services.  There is a need to educate the consumers about their rights and also to put in place a framework  to redress consumer grievances and to encourage  the organizations which advocate the consumer cause.  A consumer, who is fully aware of her/his rights, is in a position to exert pressure on the producers and suppliers of goods and services to upgrade the quality and standard of the products and services.  This makes the local producers and service providers globally competitive.

The Department of Consumer Affairs has initiated a large number of consumer centric schemes based on the following three fundamentals: -

- Consumer should be able  to assert his/her  rights  - for this purpose  he/she  should be aware  of what  to expect  from  the service  providers (including  manufactured  goods).  This calls  for increase  in consumer awareness. The vehicle for doing  so,  inter alia,  is to promote  consumer movement  so that  it permeates  into  the mindset  and thus  consumer  welfare  becomes  an  integral  part  of public  policy and  functioning  of the government,  public  and private  sectors.

- Standards and conformity Assessment – To enable the  consumer  to assert  his/her  rights  it is necessary  that  he/she  must  be able  to benchmark  his/her  expectations of quality  services or products  against  certain  pre-determined  levels.  That  is where  the installation of a comprehensive  quality  infrastructure  with  state of art  integrated  system  of standards,  legal  metrology  and conformity  assessment  aligned  to the best  international  practices  assumes  a special  significance.

- Should the consumer find  the  quality  of service or goods  deficient  when  benchmarked  with pre-determined  or  prescribed  standards,  he/she  should  have  recourse  to relatively  inexpensive  and quick  method of redressal.  This  means that  consumer  grievance redressal mechanism  is an integral  ingredient in asserting  consumer rights.

The schemes of the Department of Consumer Affairs are woven around the above fabric.

The Outcome Budget 2011-12 is organized in the following chapters.

Chapter I – INTRODUCTION :

Chapter-I gives details of functions, major programmes, schemes and mandate of the Department.  The Department of Consumer Affairs, has been assigned the prime responsibility of consumer education, protection and monitoring the prices and availability of essential commodities. The Department has launched a publicity campaign to create consumer awareness and strengthen the consumer protection mechanism.

The other initiatives taken by the Department include: -

- Computerization and computer networking of consumer fora (CONFONET)

- Strengthening Consumer Fora.

- National Consumer Helpline

- Consumer On-line Research and Empowerment Centre (CORE).

- Gold hallmarking.

- Regulating future markets.

- Setting up of consumer clubs.

- Strengthening of weight & measurement organizations.

- Comparative testing of products.

- Laying down of standards through Bureau of Indian Standards.

### Chapter II –     FINANCIAL OUTLAYS 2011-12, PROJECTED PHYSICAL OUTPUTS AND PROJECTED OUTCOMES:

Chapter-II gives details of the current schemes and programmes to be pursued in the year 2011-12.  During 2011-12, following new schemes are proposed to be launched. These schemes are:

- Strengthening the Infrastructure of New NCDRC Building.

- Setting up of National Trade Practices Regulation Authority (NTPRA)

### Chapter III – REFORM MEASURES AND POLICY INITIATIVES:

Chapter-III gives details of policy initiatives taken by the Department.

Some of the recent initiatives of the Department relate to:

- Establishment of a National System for Standardization;

- Upgradation of WTO-TBT Enquiry Point;

- Establishment of a National System for Conformity Assessment and Compliance;

- Strengthening of Legal Metrology wings of States/UTs in the country.

For further strengthening the legal provisions, the Department of Consumer Affairs has initiated comprehensive amendments in the following Acts during the year 2007-08 and 2008-09:-

- Standards of Weights and Measures Act, 1976;

- Standards of Weights and Measures (Enforcement) Act, 1985;

- Consumer Protection Act, 1986;

- Forward Contracts (Regulation) Act, 1952

The Legal Metrology Act 2009 has since been enacted to replace the Acts mentioned at (a) and (b) above.

Chapter IV – REVIEW OF PAST PERFORMANCE :

Chapter-IV highlights the performance of the Department in the implementation of various schemes in the following fields during the year 2009-10 and 2010-11.

- Consumer awareness

- Consumer protection

- Consumer education and Training, HRD/Capacity Building.

- Strengthening the infrastructure for redressal of consumer grievances.

### Chapter V – FINANCIAL REVIEW :

Chapter-V gives details of expenditure vis-à-vis Budget and Revised Estimates since 2007-08. The importance attached to consumer protection and consumer awareness is evident from the fact that the plan budget allocation of the Department has been steadily increasing except a slight decrease in the years 2008-09 and 2009-10.  In the year 2007-08, the plan budget allocation was Rs. 213.00 crore which went down slightly to Rs. 209.000 crore each in 2008-09 and 2009-10 and went upto Rs. 220.00 crore in the year 2010-11.    As regards expenditure during the year 2008-09, the expenditure on the plan side was 88.96% of Revised Estimates whereas in 2009-10, it was 89.16% of Revised Estimates.   In the year 2010-11, 71-33% of the Revised Estimates have been utilized upto December 2010.

### Chapter VI – REVIEW OF PERFORMANCE OF AUTONOMOUS BODIES:

Chapter-VI details the performance of the autonomous body under the Department, namely Bureau of Indian Standards (BIS).  This body has completed 23 years of its operation in March, 2010.  BIS keeps a close eye on the setting up of standards of various goods and services.

MONITORING OF PROJECTS AND PUBLIC INFORMATION SYSTEM

A system for monitoring and evaluation of projects has been put in place in the Department of Consumer Affairs.  Projects are initially scrutinized and evaluated by  duly constituted Committees.   There is  provision for a Standing Committee to monitor and approve projects under Consumer Welfare Fund (CWF). An Inter Ministerial Appraisal Committee has been constituted to evaluate and recommend new projects for consideration of the Standing Committee.  Monthly reports are obtained to keep a watch on the activities carried out.   In the case of the consultancy awarded to IIPA, the Monitoring Committee has been upgraded to the level of Secretary (Consumer Affairs).  Department is in the process of evaluating such projects under CWF, that have completed one year through an independent agency. Over and above this, the accounts of the grantee organizations are open to audit inspection by Comptroller and Accountant General as well as the internal audit.

All information pertaining to the major activities including budget, annual report, etc. are also available on the website of the Department: www.fcamin.nic.in. Department has set up a “Facilitation Centre” in Krishi Bhavan where public  can  obtain  any information or approach the Central  Public Information Officer, as envisaged  under Right  to Information Act.  Department has appointed 12 Central Public Information Officers (CPIOs) under the Right to Information Act to provide information to the public.  Department  has  also  set  up  a  “Public  Grievance Cell” which  looks  into  the grievances  of general  public  in respect  of  various  activities  undertaken  by this  Department.

# DEPARTMENT OF CONSUMER AFFAIRS

# CHAPTER-I

## INTRODUCTION

This chapter contains a brief introductory note on the functions of Department of Consumer Affairs, its organizational set up, list of major programmes/schemes implemented by the Department, its mandated goals and policy framework.

Department of Consumer Affairs (DCA) is one of the two Departments under the Ministry of Consumer Affairs, Food & Public Distribution.  It was constituted as a separate Department in June 1997 as it was considered necessary to have a separate Department to give a fillip to the nascent consumer in the country.  The work allocated to the Department, as per the Allocation of Business Rules, 1961, is listed below:-

(i)	 Internal Trade.

(ii)	Inter-State Trade: The Spurious Preparation (Inter-State Trade and Commerce) Control Act, 1955 (39 of 1955).

(iii) 	Control of Future Trading: The Forward Contracts (Regulation) Act, 1952 (74 of 1952).

(iv) 	The Essential Commodities Act, 1955 (10 of 1955) (supply, price and distribution of essential commodities not dealt with specifically by any other Department).

(v) Prevention of Black Marketing and Maintenance of Supplies of Essential Commodities Act, 1980 (7 of 1980), persons subject to detention thereunder.

(vi) 	To regulate weighing and measuring instruments used in trade and transaction, industrial production and for protection of human safety including regulation of packaged commodities.

(vii) Training in Legal Metrology.

(viii) The Emblems and Names (Prevention of Improper Use) Act, 1952 (12 of 1952).

(ix) The Standards of Weights and Measures Act, 1976 (60 of 1976) and the Standards of Weights and Measures (Enforcement) Act, 1985. To regulate weights and measures and commodities in prepackaged form.

(x) The Bureau of Indian Standards Act, 1986 (63 of 1986).

(xi) Laying down specifications, standards and codes and ensuring quality control of bio-fuels for end users.

(xii) Forward Markets Commission.

(xiii) Consumer Cooperatives.

(xiv) Monitoring of prices and availability of essential commodities.

(xv) National Test House.

(xvi) The Consumer Protection Act, 1986 (68 of 1986).

ORGANISATION

Department of Consumer Affairs’ mandate consists of 4 main areas of responsibilities:-

(i) Consumer protection,

(ii) Internal Trade,

(iii) Quality infrastructure and policies consisting of standards and legal metrology,

(iv) Monitoring of prices and availability of essential commodities.

In carrying out its mandate, the Department is assisted by the following organizations:-

(a) Bureau of Indian Standards (BIS)

(b) National Test House (NTH)

(c) National Consumer Disputes Redressal Commission (NCDRC)

(d) National Cooperative Consumers’ Federation (NCCF)

(e) Forward Markets Commission (FMC)

(f) Indian Institute of Legal Metrology (IILM)

(g) Regional Reference Standards Laboratories (RRSLs)

# CONSUMER WELFARE FUND

A Consumer Welfare Fund was created in 1992 with the objective of providing financial assistance to promote and protect the welfare of the consumers, create consumer awareness and strengthen consumer movement in the country, particularly in rural areas.  The Fund set by the Department of Revenue under the Central Excise and Salt Act, 1944, is operated by the Ministry of Consumer Affairs, Food & Public Distribution.  The Central Excise and Salt Act, 1944 was amended in 1991 to enable the Central Government to create the CWF where the money, which is not refundable to the manufacturers, etc   shall be credited.  Net amount available in CWF as on 31.12.2010 is Rs.121.00 crores

The Consumer Welfare Fund Rules were framed and notified in the Gazette of India in 1992.  Under these rules, any agency/organization engaged in consumer welfare activities for a period of three years and registered under the Companies Act, 1956 or any other law for the time being in force, village/ mandal/ samiti-level cooperatives of consumers, industries, State government etc. are eligible for seeking financial assistance from the Fund.  An inter-Ministerial Standing Committee has been constituted under the Rules to make recommendations for proper utilization of the money credited to the Consumer Welfare Fund for the Welfare of the Consumers.

Guidelines for seeking financial assistance from the Consumer Welfare Fund, had been framed based on the report of a Working Group set up in 1993 for the purpose.  Since the inception of the Fund, a number of schemes viz. consumer awareness scheme, scheme for setting District consumer Information Centres, Jagriti Shivir Yojana Scheme for infra-structural development of VCOs and Consumer Club scheme have been launched for spreading consumer awareness throughout the country.

In order to assess the impact of the schemes, an evaluation of the Jagriti Shivir Yojana, DCIC   and the general consumer awareness schemes was carried out and on the basis of the report it was decided with the approval of the Standing Committee to do away with the Jagriti Shivir Yojana, DCIC and the general consumer awareness scheme.  The Consumer Club scheme has been transferred to the State Governments for which financial assistance is given to the State Governments in proportion to the districts in a State.  Further, in order to promote the consumer movement throughout the country, the State Governments have been impressed upon the need to create their own Consumer Welfare Fund.  For strengthening financial support, the amount of seed money given to the State has been increased from 1:10 to 50:50, the quantum of which has been worked out on the basis of the number of districts in a State.  For special category States the ratio is 90:10.

Department has recently revised the guidelines in detail for sanctioning funds from Consumer Welfare Fund.

The Department of Consumer Affairs has initiated a number of steps to promote a responsible and responsive consumer movement in the country which are in line with the best international practices.  These include, setting up of the Consumer Online Resource & Empowerment (CORE) Centre Project, the National Consumer Helpline Project, Consultancy Project, a project for Comparative Testing of products and services, Creation of Chair/Centers of excellence in Institutions/Universities and  Information, Education and Communication programmes for consumer awareness.

THE COOPERATIVE STORE LIMITED, DELHI

The Cooperative Store Ltd. (Super Bazar), Delhi was set up in 1966 with the objective to undertake wholesale/retail distribution of consumer goods and essential commodities. The Super Bazar was registered under the Multi State Cooperative Societies Act (MSCS Act) on 22.1.1996. The Super Bazar redeemed the Government’s share contribution of Rs.1.16 crores (73.49%). The order for winding up of Super Bazar was issued on 05.07.2002 under the Multi-State Cooperative Societies Act, 1984 by the Central Registrar of Cooperative Societies.

In order to protect the welfare of the employees the Government of India has released a financial assistance of Rs. 38.00 crores, after the winding up of Super Bazar, to pay the arrears of salary and terminal benefits to the outgoing employees of Super Bazar. While all the employees totaling, 1943 had availed of arrears of salary up to 15.5.2003, only 914 employees had availed the benefits under the Voluntary Separation Scheme. The remaining employees did not respond to the notice issued in this regard and took recourse to courts of law against the Government and the Official Liquidator (OL).

The Employees Unions of Super Bazar jointly/severally filed number of Writ Petitions in Delhi High Court challenging the winding up order of Super Bazar. The High Court of Delhi upheld the winding up order. Thereafter an SLP No. 8389-8399/2005 was filed by Super Bazar Karmachari Dalit Sangh Vs Union of India in Supreme Court. The aforesaid SLP was finally disposed off by the Supreme Court on 26-02-2009. On 13.8.2010, the Hon’ble Supreme Court directed the Administrators to hold the election of the Board of Directors within ninety days. Accordingly, the election of the Board of Directors was held and six Directors elected. Under the provision of the Multi-State Cooperative Societies Act, 2002, the Government of India has also nominated one Director on the Board of Super Bazar.

FORWARD MARKETS COMMISSION

The Forward Markets Commission is a statutory body set up under the Forward Contracts (Regulation) Act, 1952.  The Commission functions under the administrative control of the Ministry of Consumer Affairs, Food & Public Distributions; Dept. of Consumer Affairs, Govt. of India. The functions of the Forward Markets Commission under the Forward Contracts (Regulation) Act, 1952 include advising Government on grant of /withdrawal of recognition to the exchanges, monitoring and regulating  the commodity futures markets and initiating necessary action as assigned in the FCRA, 1952, collecting and publishing market information, making necessary recommendations to the Government of India for the improving functioning of the market and inspection of the commodity exchanges and the members of the exchanges.

The functions of the Forward Markets commission can be classified as regulatory and developmental functions. Regulatory functions of FMC include interventions for promoting market and financial integrity and customer protection from time to time. Developmental functions include those interventions that aim at facilitating increased and informed participation in the markets and adoption of the best international practices in the market.

Functions of the Forward Markets Commission are carried out by its 5 divisions, viz; Markets, Trading and Development (Market Division), Market Intelligence, Monitoring and Surveillance (M & S Division), Awareness, Training and Intermediary Registration (IR Division), Investigation, Vigilance and Legal Affairs Division) and Commission Secretariat including HR, Administration, Finance and Grievances (Administration Division)

NATIONAL COOPERATIVE CONSUMER FEDERATION LIMITED, NEW DELHI

The Consumer Cooperative structure in the country is a four-tier one.  It comprises the National Cooperative Consumers Federation of India Ltd. at the National level, the State Cooperative Consumers Federation at the State level, the Central/Wholesale Consumer Cooperatives at the District level and Primary Consumer Cooperative Societies at the Primary level.  The  NCCF undertakes procurement and distribution of consumer articles through its own Branches and Cooperative Stores functioning in the country.  The commercial operations a of the NCCF are undertaken through 22 Branches and 10 Sub-Branch offices located in different parts of the country.  It also runs Dal Processing Unit at Bhiwani (Haryana).  The sales turnover achieved by NCCF during the year 2009-10 was Rs. 1322.39 crores as against the sales of Rs.855.28 crores   achieved during 2008-09.  These sales figures include sales through Associate Shippers.  The notable feature is that the NCCGF could achieve a net profit amounting to Rs. 11.17 crores (after tax Rs. 8.33 crores) for the year 2009-10 as compared to a profit of Rs. 1.95 crores (after tax Rs. 1.58 crores) for the previous year.  During the year, the NCCF wiped off the entire accumulated losses incurred during the previous year and declared a dividend @ 5% after a period of over 18 years.

The membership of the NCCF as on 31st March, 2010 was 136.

The present strength of the Board of Directors of the NCCF after its election/reconstitution on 7.8.2010 is 11 including Managing Director.

The authorized share capital of the NCCF is RSS. 50.00 crores.  The position of the paid up Share Capital as on 31.12.2010 is as under :

(Fig. in crores of Rs.)

Particulars						Position as on 31.12.2010

Govt. of India							10.74

Others								  3.06

Total		:		13.80

PUBLICITY MEASURES

The consumer is slowly gaining ground in our country. It is still in its infancy as the success of consumer movement mainly depends upon the level of consumer awareness generated in the country by educating the consumers about their rights and responsibilities. Within India, the level of consumer awareness varies from State to State depending upon the level of literacy and the social awareness of the people. Educating more than 100 crores people of various categories of population particularly those in rural areas where consumers are more susceptible to exploitation, on various subject matters on consumers interests which are being dealt by different Ministries/ Departments, is a herculean task that can not be undertaken as a sustained national programme without adequate funds made available for the purpose. Central Plan Scheme on Consumer Awareness was launched in the 10th Five Year Plan with a total outlay of 15 crores with annual average allocation of around Rs. 3 crores during the first three year of the plan. However, following persistent representations from consumer groups to step up our efforts for the creation of consumer awareness in the country and the strong recommendations of the Parliamentary Standing Committee attached to the Ministry, the outlay for remaining two years of the 10th Plan i.e. 2005-06 and 2006-07 was stepped up to Rs. 69.40 crore each year by the Planning Commission for creating consumer awareness. The outlay proposed for the 11th Five Year Plan is Rs. 409.00 crores. The outlay for Annual Plan of the following years and its expenditure status is as under:-

| S.No. | Year | B.E. | Expenditure |
| --- | --- | --- | --- |
| 1 | 2007-08 | Rs. 67.00 crores | Rs. 44.34 crores |
| 2 | 2008-09 | Rs. 75.00 crores | Rs. 80.50 crores |
| 3 | 2009-10 | Rs. 78.00 crores | Rs. 70.60 crores |
| 4 | 2010-11 | Rs. 84.02 crores | Rs. 67.36 crores As on 31/12/2010 |

PRICE MONITORING CELL

1.1 The Price Monitoring Cell (PMC) monitors the prices of 21 essential commodities viz. rice, wheat, atta, gram dal, arhar dal, moong dal, urad dal, masoor dal, tea, sugar, salt, potato, onion, vanaspati, groundnut oil, mustard oil, milk , soya oil, palmoil, sunflower oil, gur. The retail prices and wholesale prices are collected from 50 centers on daily basis based on the information furnished by the State Food and Civil Supplies Departments. The daily and weekly commodity prices and other activities of PMC are available in the web site of the Department (http://fcamin.nic.in) which is updated regularly. The prices and availability of most essential commodities have generally remained within reasonable levels barring some variation in prices of rice, wheat, sugar, edible oils, onion etc over the last three months in 4 Metros viz. Delhi, Mumbai, Chennai and Kolkata.

2.	In the wake of the rise in prices of essential commodities, meetings of the Committee of Secretaries (CoS), Cabinet Committee on Prices (CCP), Cabinet Committee on Economic Affairs (CCEA), High Powered Price Monitoring Board (HPPMB) on Prices of essential commodities are generally being held to review the prices of essential commodities.  Analytical notes on latest price situation and availability of essential commodities were prepared, based on the WPI numbers, wholesale/retail prices, production, procurement and export/imports of select essential commodities, for consideration of the high level meetings.  Notes on the measures taken by the Government for ensuring adequate supplies and containing the rise in prices of essential commodities were prepared and given to Press Information Bureau (PIB) and Chief Economic Adviser, Ministry of Finance on a weekly basis for giving publicity.

CHAPTER II

FINANCIAL OUTLAYS   2011-12, PROJECTED PHYSICAL OUTPUTS AND PROJECTED OUTCOMES

This chapter gives the details of the financial outlays,  plan  and non plan,  for 2011-12, projected physical  outputs  and projected/budgeted  outcomes  for non-plan and plan  schemes of the  Department of Consumer Affairs.  Its main objective is to establish a correspondence between financial outlays and projected outcomes.

(Rs. in crores)

| S.No. | Name of the Scheme Programme | Objective/ Outcome | Outlay 2011-12 |  |  | Quantifiable Deliverables/Physical Outputs | Projected Outcomes | Process/ Timeline | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | 2 | 3 | 4 |  |  | 5 | 6 | 7 | 8 |
|  |  |  | 4(i) | 4(ii) | 4 (iii) |  |  |  |  |
|  |  |  | Non-Plan | Plan | Complementary Extra-Budgetary Resources |  |  |  |  |
| 1.a | Grant-in-aid Awareness Programme including training and education Consumer Online Resource & Empowerment Centre (CORE) set up by Consumer Coordination Council, Noida (UP) | Consumer Online Resource and Empowerment (CORE) Centre project is an initiative taken by the Ministry towards web-based Consumer Awareness & Protection Programme aimed at identification of Consumer problems and their redressal through institutional approach and utilizing the information technology methods. | 10.00 0.45 | -- --- | -- -- | (i) Develop Online Database (ii)Upload and update the consumer related issues on time. (iii) Make the online information available in major local languages for the benefit of a maximum number of consumers | Resolution of complaints will increase from 30 to 35% | 5 years continuous. |  |
| b. (i) (ii) | Indian Institute of Public Administration: IP Estate, Ring Road, New Delhi for Setting up and running a centre for Consumer studies in IIPA. Consultancy Project under the scheme for promoting involvement of Research Institutions/ Universities/Colleges etc. | (i) Conduct/ facilitate in depth research in the area of consumer protection and consumer welfare. (ii) Network with the other institutions/ organizations nationally and internationally, working for the cause of Consumer Rights protection. (iii) Organize seminars/ workshops/ conference / round tables on the contemporary issues relating to consumer protection. (iv) Create resource centre for future research and published books / monographs/ occasional papers to fill up existing knowledge gap. To facilitate and promote better protection of consumer ‘rights, interests and welfare. Organize seminars/workshops/conferences/round tables etc. To develop material for training and dissemination to be used by academic institutions in their activities related to consumer protection and consumer welfare. | 2.44 1.04 | -- | -- | (i). Organized seminar/training workshops / conferences/ round table on the contemporary issues relating to consumer protections. (ii) Sensitize trade and industry and the service providers to the requirements of the consumers. (iii) create resource centre for future research (iv). published books / monographs/ occasional papers to fill up existing knowledge gap. Processing of fresh proposals applications regarding research projects already received and likely to be received from various organizations institutions, colleges, universities and educational institutions. To impart 3 training programmes for research on consumer protection. To identify and disseminate best practices in the field of consumer protection. | To facilitate and promote better protection of consumers rights and interests with special reference to rural India. | 5 years continuous | To undertake activities to fulfill the objectives under guidance of the monitoring committee headed by Secretary (CA |
| c. | FICCI Alliance for Consumer Care to facilitate prompt redressal of consumer grievances through interface between Business and the Consumer, | A project has been sanctioned to FICCI at a cost of Rs.3.55 Crores spread over a period of 3 years. | 0.57 | -- | -- | - Interface between business and the Consumer - Develop and introduce a voluntary code of conduct for business-consumer relationship etc. | Better public private relation will be developed and private sector will also become more responsible before consumers. | 5 years |  |
| d. | Council for Fair Business Practice, Mumbai, Maharashtra (CFBP) (i) for Consumer grievance redressal activity and ii) upgrading for Ramakrishna Bajaj Consumer Education Testing Centre located at SNDT Women University at Mumbai | i) For Consumer grievance redressal activity by CFBP for 5 years. ii.) For upgradation of Ramakrishna Bajaj Consumer Education Testing Centre located at SNDT Women University at Mumbai | 0.06 | -- | -- | - To resolve maximum number of consumer complaints outside the consumer forum ii) To take steps to enhance awareness among consumers about the products they use. iii) To provide testing facilities at a reasonable costs & serve as Resource Centre seeking information, guidance and testing. | To create awareness amongst consumers about the product they use and provide various analytical /quality testing facility for the same. Serve as a resource base for consumers seeking information, guidance and testing. | Five years |  |
| e. | National Consumer Helpline | i)To service the consumers complaints by giving them appropriate counseling ii) To transmit online complaints relating to companies under convergence platform for their speedy disposal. iii) To develop and migrate the existing website to more technologically superior platform that offers online transmission of complaints and better facilities to the User. iv)To undertake maximum resolution of consumer complaints in shortest possible time v) To enlarge the number of Companies under Convergence platform vi) To undertake measures to publicize about the Helpline in different parts of the country through appropriate means in association with First Party. vii) To render all technical and other consultancy services to set up State Consumer Help lines. viii) To enhance the knowledge of consumers and thereby increase their awareness about their rights as a consumer and the remedies available to redress their grievances. | 1.23 | -- | -- | The Helpline is intended to deal with all problems related to products and services including problems related to telecom, courier, banking, insurance, financial services etc | Average complaints received are 5000 in a month out of which around 30% resolved. | 3 years |  |
| f. | Voice Society 441, Jangpura Mathura Road, New. Delhi 1100 14 | - Comparable test data of most selling products for verification of product quality and performance - Opportunities for manufacturers to know their product performance compared with their counter parts - Choices for consumer as best buy products sold in the markets - Verification of misleading/claims of their products and providing information symmetry between consumer and producers to enhance and contribute to development of competitive market. | 0.90 | -- | -- | Comparative Testing of 16 Products and 3 services per year | i) To spread Consumer awareness based on scientific studies of various consumers products and services to make rational choice. ii) To sensitize national standards bodies policy makers on upgradation of national standards/policy changes Opportunity for manufactures to improve upon their products in competitive markets especially on quality ,performance, safety and energy efficiency based on our scientific studies | Three years |  |
| g. | M/s Consumer Education and Research Centre (CERC) ‘Suraksha Sankool’Sarkhej-Gandinagar Highway, Thaltej, Ahmedabad for upgrading lab. | For up gradation of laboratory with NABL accreditation | 0.55 | -- | -- | - Procured requisite test equipment to under take comparative testing of dry cell batteries, storage water heaters/geysers and certain food and pharmaceutical products. - Published the rating and ranking of products tested through their magazine and various print and electronic media - Invited comments feedback on test results from manufactures for improvement in their products in respect of safety and quality | Educate consumers for their buying decision and also protect the consumer’s interest by providing reliable information on safe and quality products which will help them to make them to make an informed choice. | 5 years |  |
| h. | M/s Centre for Consumer unity and trust society (CUTS) D-217, Bhaskar Marg , Bani Park Jaipur- 302016 | For Grassroots Reach out & Networking in India through Consumer action in 12 districts of Rajasthan through Consumer Action (GRANICA) | 0.22 | -- | -- | i) To understand the consumer protection issues and status of redressal ii) To ensure and enhance strong consumer movement at the grassroots in the seven divisions of the state by way of ensuring an enabling environment for protecting consumer interest. CUTS will train Civil Society organizations in each of 12 districts which will be empowered in analyzing, articulating and advocating on relevant emerging consumer issues and also capable of playing a watch-dog role in their respective areas. | - People in all the 12 districts will be empowered as assertive consumers to uphold their rights and fight for justice. - Two CSOs capable of playing a “watchdog” role in their respective district. - Better service delivery areas related to basic needs and efficient redressal mechanism in place, particularly in rural areas and the targeted division. - Protecting consumer interest in all the 12 districts, which will ultimately create an enabling environment towards protecting the state interest. - In turn, the program will contribute towards achieving the MDGs at the state level. - The program will result in a model of empowering consumers through networking and thus offer a model for further expansion in the identified district and elsewhere. | Three years |  |
| i. | National Law Institute University , Kerwa Dam Road, Bhopal 462 044 M.P. | To set-up a Chair in the area of consumer protection and consumer welfare at NLIU Bhopal. The primary objective of the Chair is to act as a “Think Tank “ for the Research and policy related issued on consumer protection and consumer welfare interests. | 0.26 | -- | -- | i) provide necessary expert inputs for formulation of policy /Programmes/schemes of the Department of Consumer Affairs. Programmes / schemes of the Department of Consumer Affairs; b. To Identify and disseminate best practices in the field of consumer ii) Identify and disseminate best practices in the field of consumer protection Laws and Practice; iii) publish, in the form of books, monographs pamphlets to fill up existing knowledge gap and the results of research studies conducted by them; iv) Sponsor/Organize seminars/workshops/ conferences etc. on consumer related issues at national / regional levels; v) Develop, host and administer an academic, yet interactive, website from NLSIU to disseminate information to Consumer Affairs; vi) Undertake at least two specific studies, research or any other activity as may be commissioned by the ministry of Consumer Affairs every year; vii) Conceive and organize an All India Moot Court Competition on Consumer Affairs and ensure that the competition is conducted with wider participation of law schools and colleges from all over India with a designated prize in cash and kind; viii) Organize periodically, short term training programmes for the law Teachers, NGOs and others; The Chair set up may also conceive, plan and execute a Post-Graduate Diploma Course on Consumer Affairs through the Distance Education Department at the NLSIU. | To facilitate and promote better protection of consumers rights and interests | Five years |  |
| j. | CONCERT Chennai | CONCERT Chennai has been sanctioned an amount of Rs. 3.34 crores for a period of 2 years for undertaking comparative testing of products & services | 2.04 |  |  | i) To further develop the existing website of the second party to more technologically superior platform that offers better facilities to the user. ii) To decimate the test reports in four south Indian languages viz. Tamil, Kannada, Malayalam and Telugu besides Hindi and English and thereby increase awareness among consumers about the product they use. |  |  |  |
| k. | MOUNDA Dhunpur Kaliyan Samiti Uttarkashi |  | 0.10 |  |  | - Prevention of exploitation of rural consumers of Hill areas of Uttarakhand by empowering them about Consumer rights using innovative consumer awareness program. - Conduct survey to get the actual number of senior citizens who qualify for the govt. pension and who are eligible yet not getting the pension and arrange the facility for them to get their right of pension. - Conduct survey of below poverty line eligible families and help them in securing the Ration card as per their financial status so that they can get their right of subsidized food grain as well as rice provided by the govt. via PDS. iv) Empowering the consumer on legal matters and their right to get the fair and unbiased trial as well as help. Special drive and awareness program for backward classes and women. |  |  | First Installment released. |
| 2 a. | 3601 Grant-in-aid to State Government Consumer Club | This scheme was launched in 2002, according to which a consumer club shall be set up in each Middle /High/Higher Secondary/Colleges affiliated to a government recognized Board/Universities. A grant of Rs.10,000/- per consumer club is admissible under this scheme. Main aim of the scheme is to educated children about the rights of the consumer as provided in the Consumer Protection Act, 1986, and to mobilize youngsters by instilling in them the spirit of protection of Consumer Rights. | 1.30 (for Consumer Club & seed money both) | -- | 1.00 | So far 23 states/ UTs have been covered in these schemes. During 2010-11 remaining 13 states/ UTs will be included in this scheme | (i) students will become aware about the consumer rights through consumer clubs set up in schools. (ii) Consumer movement will become more storng by setting up of State Consumer Welfare Fund. |  | *Rs 3.00 crores has been proposed in this head Rs 1.50 crores has been earmarked each for Consumer club & seed money |
| b. | Seed Money to State (CWF) | In order to promote the Consumer movement throughout the country, the State Govt. have been impressed upon to create their own Consumer Welfare Fund. For encouraging them to do so, the amount of seed money given to the States has recently been increased from 1:10 to 50:50 and 90:10 in respect of 13 special category States. | 0.30 |  |  | So far 20 numbers of States/ UT have been sanctioned seed money. During 2011-12 remaining 14 states/ UTs will be included in this scheme.. | Consumer movement will become stronger by setting up of State Consumer Welfare Fund. | Scheme is going on and will continue till all the state/UTs availed the benefit of the scheme | *Rs 3.00 crores has been proposed in this head Rs 1.50 crores has been earmarked each of for C.C. S.M |
| 3. a. b. | 3602 Grant-in-aid to UT Governments Consumer Clubs Seed Money | This scheme was launched in 2002, according to which a consumer club shall be set up in each Middle/High/Higher Secondary School/Colleges affiliated to a government recognized Board/University. A grant of Rs.10,000/- per consumer club is admissible under this scheme. Main aim of the scheme is to educate children about the rights of the consumers as provided in the Consumer Protection Act, 1986, and to mobilize youngsters by instilling in them the spirit of protection of Consumer Rights. In order to promote the consumer movement throughout the country, the State Governments have been impressed upon to create their own Consumer Welfare Fund. For encouraging them to do so, the amount of seed money given to the States has recently increased from 1:10 to 50:50 and 90:10 in respect of 13 special category States | 0.175 |  |  | Consumer clubs has been set up in three UT so far. Other UTs will be persuaded to avail the benefits of the scheme of the year during 2011-12. | Consumer movement will become stronger by setting up of State Consumer Welfare Fund. | Scheme is going on and will continue till all UTs avail the benefits of the scheme. | . *Rs 0.50 crores has been proposed in this head Rs 0.25 crores has been earmarked each of for consumer club & seed money |
| 4 | 3601-Grant-in-Aid to States Govts 03- Grants for Central Plan Schemes 361-Civil Supplies Schemes 04-Consumer Helpline 04.00.31-Grant-in-Aid | To guide and counsel the Consumer to resolve their grievances. |  | 4.00 |  | - Develop alternate complaints redressal mechanism at State level. - Maximum No. of Disputes to be resolved out of court. - Early resolution of complaints. - Reach out to rural consumers. - Capacity building of state level VCOs. - State level machinery gets experience. - Companies and service providers become more active in solving consumer disputes. - Provide service in regional language in addition to English language. | More No. of complaints will be resolved out of court. | The project is for 5 years after that States will continue the project from their sources. |  |
| 5 | 3602 Grants-in –aid to UTs. Govts. 03-Grant for Central Plan Scheme 361-Civil Supplies schemes 06-Consumer helpline 06.00.31- Grant-in –Aid | To guide and counsel the Consumers to resolve their grievances. |  | 1.00 | -- | - Develop alternate complaints redressal mechanism at State level. - Maximum No. of Disputes to be resolved out of court. - Early resolution of complaints. - Reach out to rural consumers. - Capacity building of state level VCOs. - State level machinery gets experience. - Companies and service providers become more active in solving consumer disputes. - Provide service in regional language in addition to English language. | More No of complaints will resolved out of court. | For 5 years. After that UTs will continue the project from their own sources. |  |
| 6 | (i) Weights & Measures- Strengthening of weights and measures infrastructure | To Strengthen the Legal Metrology Wing of the States and Union Territories so that they may ensure correct measurement in commercial transaction and protect the interest of consumers. This objective will be met through Supply of smaller Mobile Kit for testing of weigh bridges, supply of working/secondary standards Weights and working standards capacity measures to various states/UTs | -- | 50.00 | -- | i) To supply 31 mobile kit for testing weigh bridges to States/UTs. ii) To supply 147 sets of Working Std. Capacity Measures & 2000 check Measures iii) Construction of standard laboratory/testing facility. iv) Supply of CNG/LPG Kit. | To ensure better accuracy by proper calibration weighing and measuring used in, -trade and transaction -industrial production -protection of human health and safety; To ensure accurate standards for calibration of commercial scales and weighment by State agencies and; -to ensure better enforcement | -- | -- |
|  | (ii) Strengthening RRSL and IILM, Ranchi | To augment the infrastructure of RRSLs in model approval of weighing and measuring instruments and to create new testing facility in flow measurement and to modernize training facilities at Institute at Ranchi. | 12.5 |  |  | i) To purchase testing equipments for all 5 RRSLs for conducing electrical tests. ii Creation of new Testing Facility like Flow measurement.. iii) Civil work (renovation) at IILM, Ranchi to make it as Centre for Excellence. | To ensure better accuracy by proper calibration of Weighting and Measuring instruments used in trade and transaction | -- | -- |
| 7. | Consumer Protection Cell | The Consumer Protection Cell renders secretarial assistance to the Department in administering the Consumer Protection Act, 1986 and related activities. | 0.10 | 0.40 Total: | NIL _________ 0.50 | Hold one meeting of the Central Consumer Protection Council (CCPC) during 2011-12. | - | Conti-nuous and ongoing scheme. | - |
| 8. | Strengthening infrastructure of new NCDRC Building. | To provide necessary infrastructural facilities for effective functioning of NCDRC; so as to create consumer friendly environment. | NIL | NIL Total: | NIL _______ NIL | Provision of office modules as per requirement. | To enable NCDRC to start functioning from new premises & optimise their output. | 2011-12. | New scheme |
| 9. | Computeri-zation and Computer Networking of Consumer Fora (CONFONET) | The project is being implemented through the National Informatics Centre (NIC) on turnkey basis, which would provide for computerisation of all Consumer Fora in the country. The project would enable consumers & other concerned to access information. | NIL | 9.59 | NIL | Provision of HR support through Technical Support Personnel, for eventual adoption of system by respective Consumer Fora themselves. Upgradation of skill by means of training, workshops etc. | The system would be operationalized fully. | By 31.3.2012 | - |
| 10. | Strengthening Consumer Fora | The scheme would further strengthen the infrastructure of the Consumer Fora so as to provide the minimum level of facilities required to make these Fora fully functional. The assistance to all the eligible States/UTs will strengthen the infrastructure of the Consumer Fora for their effective functioning. | NIL | 22.00 | NIL | Prioritizing the completion of the infrastructure of those Consumer Fora in 21 States, which were covered under the IPCP scheme. Consumer Fora in remaining States to be also covered subject to eligibility & availability of funds. | Better facilities at Consumer Fora would help in quicker disposal of complaints and more consumer friendly interface. | 31.3.2012 | - |
| 11. | Setting up of the National Trade Practices Regulation Authority (NTPRA) | To create an authority to address the gap in legislation on account of repeal of the Monopolies and Restrictive Trade Practices Act and the Competition Act, 2002 into force. It would also perform important functions of taking proactive measures for protection of consumer interests through training and innovative programmes. | NIL | 0.01 | NIL | The scheme would be got approved by the competent authority and the Bill would be introduced in the Parliament. | The authority would provide an alternative disputes redressal mechanism for Unfair Trade Practices. | -- | Token provision. Scheme is yet to be approved. |
| 12. | Strengthening of FMC | Efficient Regulation of the Commodity Futures Market. |  | 15.00 |  |  |  |  |  |
| (i) |  | i) Strengthening of IT. Upgradation of IT facilities |  | 1.40 |  | - i) Purchase of equipments and development of software for market monitoring and surveillance and other software, improving connectivity (intranet and internet), ii) Subscribing to Real Time News services (CRISIL, Bloomberg, Reuters, etc.) to ensure better monitoring and surveillance. iii) Connectivity with Exchanges iv) Developing the IT capacity of Regional exchanges. v) Outsourcing of IT related activities | Better surveillance of the market and the Exchanges and the trading activities of the Exchanges and their members and other intermediaries. | On going |  |
| (ii) |  | ii) Organizing capacity building programmes for policy makers. iii) Organizing training programmes for the staff of FMC and the exchanges. iv) Conducting audits of exchanges and their members. v) Awarding consultancies/studies in area of concern to the FMC and the commodity futures market and engaging professionals in necessary areas. |  | 5.06 |  | - i) Capacity building 100 programmes - Inspection of commodity exchanges and members of the exchanges - 325 members. - Consultancy assignment - as per requirement | - Building capabilities of the FMC officers, Exchange functionaries, and various categories of the stakeholders for creating efficiency in the market. - Ensuring proper functioning of the market constituents. | On going |  |
| (iii) |  | vi) Increasing the awareness level of different categories of stakeholders especially farmers to make them aware of the existence as well as the benefits of the futures markets vii) Interactions with various stakeholders in the commodity futures market to understand their difficulties, problems and their needs so as to align/design policies to meet feasible/desirable objectives. viii) Undertaking publicity measures to disseminate information about the commodity futures market. ix) Coordinating with international regulatory bodies for increased adoption of best practices. |  | 3.79 |  | Awareness Programme – 400 Meetings – 10 Advertisement in National/ Regional and NER dailies MOUs - as per requirement | Spreading awareness of the commodity futures market so as to enhance the understanding of and participation in the market and spreading the benefits of the markets to all stakeholders. Increasing interactions with the market stakeholders to facilitate better regulation of the market. Increasing interaction with international regulatory bodies to facilitate better regulation of the market. | On going |  |
| (iv) |  | x) Dissemination of spot and futures prices of commodities traded in the futures market |  | 4.05 |  | Launching of Price Dissemination Project in 1500 locations. | Better dispersal of spot and futures prices of agricultural commodities to centers accessible to farmers so as to empower them with price information and increase their bargaining power for better price realization. | On going |  |
| (v) |  | xi) Locating and moving the office into a suitable premises |  | 0.70 |  | Identification of new office premises and payment of rent for hired premises, municipal rates, taxes, etc. • All contingent expenses for running an office, such as furniture, postage, purchase and maintenance of office machines and equipments, etc. | Increasing the availability of the office premises of the FMC to facilitate the strengthening of the staff and officers of FMC. | On going |  |
| 13 (i) | Scheme for setting up of Gold Assaying & Hall-marking Centres in India with Central assistance | To protect Consumers against cheating by unscrupulous jewellers and to boost export of jewellery |  | 0.66 |  | - Setting up and recognition of Assaying & Hallmarking centres. - Organization of training Programmes for artisans and A&HM Centres personnel - Training Programme on Auditing of A & H Centres for BIS Personnel | 5 Nos. Assaying & Hallmarking centres. 9 Nos. training Programmes for artisans and two programmes for A&HM personnel. 2 Nos. Training Programme on Auditing of A & H Centres for BIS Personnel | Centres are to be set up by private/public sector organizations short-listed through advertisements in newspapers and BIS website. | There are two Schemes in operation – one with Central Assistance and other by BIS without such assistance. Under Central assistance Schemes total of 25 centres have so far been set up by public sector organizations and recognized by BIS. Due to lack of interest of entrepreneurs to set up such Centres, the achievements under the Scheme have not been up to the expected level. An agency has been enlisted to conduct an evaluation of the Scheme and make recommendations to make it more effective. The numbers of Assaying & Hallmarking Centres set up and recognized by BIS so far under the Scheme operated by it is 158. |
| (ii) | National System for Standardization | i) Development of Organizations developing standards/ R&D prioritization, etc. |  | 1.06 |  | 3 R&D projects for preparation/revision of Indian Standards | The Indian Standards so prepared/revised will be based on scientific study taking into consideration the situations prevailed in the country. If Indian standards are different from corresponding international standards, the scientific study will help in justifying in deviating from the International Standards. |  | 1 R&D project has already been initiated. 2 Training programmes have already been organized. |
|  |  | ii) Intensifying participation of stakeholders/Scientific organizations and members of BIS technical committees in International Standardization |  | 0.34 |  | Participation of 25 outside BIS delegates who are members of various technical committees of BIS in ISO, IEC meetings | Enhancing participation of technical committee members in international standardization process to safeguard national trade and consumer interest in addition to facilitating the process of harmonizing Indian standards with International standard. |  |  |
|  |  | iii) Intensifying participation at National level of representatives of Govt. organizations, Eminent Scientific organizations, IITs, NITs, Govt. Labs, Consumer organizations and Economists |  | 0.10 |  | Participation of about 40 technical committee members for attending respective BIS technical committees. | Enhanced participation of stakeholders in national standardization process would facilitate evolving comprehensive Indian Standards. |  |  |
|  |  | iv) Development of National Standards Database and National Regulatory Database Database and WTO-TBT enquiry point |  | 0.15 |  | - Software and website Development & Maintenance - Development of Database - Upgradation of network bandwidth - Software development and procurement v) 2 Nos awareness programmes of WTO | The work on portal on National Standards Database and National Regulatory Database is continuously under development. Two awareness programmes on WTO - TBT Enquiry Point and related issues will be organized in 2011-12. IR&TISD will coordinate with ITSD for software development and database for facilitating smooth functioning of WTO-TBT Enquiry Point |  |  |
|  |  | Total |  | 1.65 |  |  |  |  |  |
| (iii) | HRD & Capacity Building in Educational Institutions | i) Introduction of the process of Standardization and Standards relating to important socio-economic sectors in Professional, Technical and Higher Education Institutions ii) Enhancing the availability of trained manpower for above | -- | 0.10* | -- | For Agriculture Sector i) Working Group Meetings ii) Workshops iii) Writing Of Curriculum iv) Review Meetings & Meeting Of Experts For Technical & Management sectors i) Working Group Meetings ii) Workshops iii) Writing Of Curriculum iv) Review Meetings & Meeting Of Experts | A curriculum in Agriculture Sector A curriculum in Technical & Management Sectors | 2011-12 | The proposal for draft curriculum writing and its implementation is to be done by ICAR which has been agreed by Monitoring Committee & Standing Committee. The terms of Reference (TOR) & the financial part in developing a curriculum by ICAR is awaited. Curriculum would be developed with the help of AICTE & UGC |
| (iv) | Consumer Education & Training, HRD and Capacity Building | i) To involve Consumer of all sections and educate them on their rights in order to spread the consumer movement further. ii) To disseminate the know how about use of Standard and to promote quality culture in the country iii) To impart training to consumers in areas which affect the health and safety of consumers iv) To impart training to service providers of Central and State/UT governments and public sector undertakings to improve their services which will in turn improve customer satisfaction. | - | 4.59 |  | i) 3 Day Implementation Programme on Service Delivery (IS 15700): - 21 Programmes, 3 in each region, NITS and branch offices at Bhopal, Jaipur, Bangalore ii) 2 Day Programme on Management and Handling of Hospital waste: 8 Programmes, 1 in each region, 2 in NITS and 1 in each branch offices at Bhopal, Jaipur, Bangalore iii) 3 Day Programme on Food Safety Management Systems-8 Programmes, 1 in each region and branch offices at Bhopal, Jaipur, Bangalore and 2 at NITS iv) 2 Day Programme on Adulteration of Food Products and Food Safety for Health Inspectors- 13 Programmes, 2 in each region and branch offices at Bhopal, Jaipur, Bangalore and 1 at NITS v) 2 Day Programme on Safe Drinking Water, Sanitation and Waste Disposal for PHD and Jal Board officials- 10 Programmes, 2 in each region, 1 in NITS and branch offices at Bhopal, Jaipur, Bangalore vi) 3 Day Programme on Structural Safety and Design for Technical people of CPWD and State PWD- 8 Programmes, 1 in each region, 2 in NITS and 1 in each branch offices at Bhopal, Jaipur, Bangalore vii) Training Programmes by ATIs/SIRDs/PRIs: 2/3 Day Programme on consumer education and awareness: 70 programmes by various ATIs/SIRDs keeping average 30 participants | 160 Trained manpower of various public service delivery organizations of the Government Dept.- To help the service providers in implementing the standard for better delivery of services to consumers 160 Trained manpower for management and handling of waste and maintaining cleanliness in hospitals- To help the Govt. Hospitals and CGHS Dispensaries for improvement of cleanliness 160 Trained manpower for management of catering services- To help Govt. hotels and Indian Railways etc. for food safety and maintaining hygienic conditions 260 Trained manpower for better prevention of food adulteration 200 Trained manpower for providing safe drinking water and handling sanitation and waste disposal effectively 160 Trained manpower for intelligent and safe building design. 21500 trained and aware consumers | During 2011-12 |  |
| (v). | Scheme on conformity assessment and compliance | This is a new scheme proposed under the XI Five year Plan and is yet to be approved by the Ministry. As such no expenditure has been incurred so far on the scheme. Further no expenditure is envisaged in the current financial year ending March 2011 also. Thus the entire financial outlay of Rs.20 to 25 crores as proposed in the scheme may be taken as budget estimate for 2011-12 subject to the approval of the scheme |  |  |  |  |  |  |  |
| 14. | Consumer Awareness | Empowerment of consumer by dissemination of information regarding consumer rights and responsibilities through multi media publicity campaign “Jago Grahak Jago”. |  | 87.23 for the year 2011-12 |  | (i) Print advertisements through national and regional newspapers as per DAVP policy around 30000 insertions on about 50 themes/issues. (ii) Release of audio spots through AIR and Private FM channels on issues of consumer interest-20,000 audio spots 40 seconds each. (iii) Release of TV spots through DD Network, including regional channels of DD- Around 30,000 video spots of 30 seconds each. (iv) Release of TV spots through Private C&S channels through DAVP- Around 15,000 video spots of 30 seconds each. (v) Outdoor Publicity through channels, hoardings etc. (vi) Printing of messages on consumer issues on railway tickets/reservation charts-approximately 2 crores tickets/charts. (vii) Organisation of Nukkad Natakes in School/Colleges/Villages of spread the message of Consumer Awareness. (viii) Participation in Exhibitions/Trade Fairs etc. (ix) Distribution of publicity material such as brochures/ Leaflets ect. containing synopsis of CPA etc. |  |  |  |

# CHAPTER- III

REFORM MEASURES AND POLICY INITIATIVES

1. 	CONSUMER WELFARE FUND

i) 	 National Consumer Helpline (NCH)

The National Consumer Helpline (NCH) is a landmark project set up in collaboration with the Delhi University at a cost of Rs.3.12 cr. Total cost of the project has already been   released. Consumers from anywhere in the country can dial the toll free number 1800-11-4000 from any BSNL/MTNL telephone line and seek advice in all areas of consumer interest and sort out their grievances.  The service is available in English and Hindi.  The project has been evaluated recently and approved by an independent agency. The extension of the project for further three years has already been recommended by the Standing Committee.

ii)	  Consumer Online Research and Empowerment (CORE) Centre

Consumer Online Research and Empowerment (CORE) Centre project is an initiative taken by the Ministry towards web based consumer awareness & protection programme aimed at identification of consumer problems and their redressal through institutional approach and utilizing the vibrant information technology methods.  The project is being executed through Consumer Coordination Council (CCC), - a national coalition of more than 50 leading consumer organizations in the country and member of Consumers International – CI, (U.K.).

The main objectives of the CORE Center Project are :-

- Development of National information gathering mechanisms on consumer related issues;

- Dissemination of information on important consumer issues;

- Establishment of a Research & Documentation Centre on various consumer issues;

- Providing information and analysis of consumer related Laws and Judgments; and

- Providing online support and pursuing consumer complaints;

The project has been sanctioned with a total Budgetary outlay of Rs.3.50 crores spread over a period of five years out of which Rs.2.42cr. have been released so far.  The CORE Centre is located in the premises of the National Institute of Standardization of BIS (Bureau of Indian Standards) at NOIDA (UP).  A total of 81362 complaints have been received out of which 25034 have been resolved and 33042 transferred to Ficci Alliance on Consumer Care.

iii)	  Council for Fair Business Practice, Mumbai, Maharashtra (CFBP)

As part of new initiatives to enhance the levels and reach of consumer protection and welfare activities, the Department has considered and approved a project by Council for Fair Business Practice, Mumbai, Maharashtra (CFBP) This project is for consumer complaint handling by CFBP. Rs.6 lakhs is sanctioned for complaint handling per year for 5 years. First year grant of Rs 6 lakhs has been released to CFBP.

II    Setting up of consumer Product Testing Laboratories

i)	Centre for Comparative Testing of Products and Services  (Voice Society)

VOICE Society, New Delhi has been sanctioned a project for Comparative Testing of Consumer Products with the objective of ensuring product quality and safety.  The total approved cost of the project is Rs.2.25 cores, for a period of two years.  Total cost of the project has already been   released..  Under this project 20 products and 4 services have been tested and the reports have been published. The project has been evaluated recently.  Voice Society , New Delhi has been sanctioned an amount of Rs. 2.70 crores for IInd phase of the project.

The focus of the projects is as under

- Utilizing existing NABL accredited laboratories in India for comparative testing of various categories of products.

- Publishing and popularizing consumer magazine containing consumer related subjects in English, Hindi & other regional languages to create informed consumers.

- To facilitate in developing & up-gradation of National Standards based on scientific data and consumer preferences.

ii)	 M/s Federation of Consumer Associations, West Bengal (FCAWB) :- A project for up gradation of Food and Water Testing   organizing Laboratory with NABL Accreditation at a cost of Rs.2.08 Crore,  has  been sanctioned  specifically towards purchase of equipments for  upgrading the laboratory.

iii)	Council for Fair Business Practice, Mumbai, Maharashtra (CFBP)

As part of new initiatives to enhance the levels and reach of consumer protection and welfare activities, the Department has considered and approved a project by Council for Fair Business Practice, Mumbai, Maharashtra (CFBP) This project is for upgrading  existing Ramakrishana Bajaj testing lab in  SNDT Women’s University Mumbai. The department is partially financing the upgrading of lab at a cost of Rs.50 lacks

iv)	A project proposal from M/s Consumer Education and Research Centre (CERC) ‘Suraksha Sankool’Sarkhej-Gandinagar Highway, Thaltej, Ahmedabad for up gradation of laboratory with NABL Accreditation at a cost of Rs.1,82,34,500 has been approved by Standing Committee and sent to IFD for their concurrence and vetting up of MOU and Sanction.

III   Scheme for promoting involvement of Research Institutions/Universities /Colledges etc. in Consumer Protection and    Consumer Welfare

This scheme has been launched in 2004 with a view to sponsor research and evaluation studies in the field of consumer welfare to provide solution to the practical problems being faced by the consumers, to sponsor seminars/workshops/conferences on the consumer related topics, and to have necessary inputs for the formulation of policy/programme/scheme for protection and welfare of the consumers.  The Indian Institute of Public Administration, New Delhi, has been identified as the nodal organization to administer the scheme.  Total grants of 3.81 crores have been sanctioned to IIPA.  The total approved cost of the project has already been released; the project has been further extended for three years from July 09

IV     Creation of Chair/Centers of excellence in Institutions/Universities

i) Chair on Consumer Law an(d Practice in National Law School of India University (NLSUI), Bangalore:- A Chair on Consumer Law and Practice was sanctioned  in 2007-08 to National  Law School of India University (NLSUI), Bangalore at a cost of (Rs.90,00,000/- as an endowment grant. Rs. 15, 00,000/- was released for first year expenditure).  Total amount of grant of Rs. 1, 05, 00,000/- has already been released. The primary objectives of the Chair  is to act as a ‘’Think Tank” for the Research and Policy related issues on consumer law and Practice and also develop Consumer Affairs as a district subject of study both at Under Graduate and Post Graduate levels.

ii)     Centre of Consumer Studies in IIPA: - A Centre of Consumer Studies was sanctioned in 2007-08 to Indian Institute of Public Administration, New Delhi at an estimated cost of Rs. 850.77 lakhs spread over a period of five years for in-depth action research in the areas of consumer protection, training of personnel engaged in administration and adjudication of consumer justice in the country and the elected representatives of the local bodies etc. An amount of Rs. 3,00,19,000/- for the   first and Second year   grant has been released so far.

iii)     A Project proposal from National Law Institute University , Kerwa Dam Road, Bhopal 462 044 M.P. for  Chair on Professorship in  Consumer Protection  and Consumer welfare at the cost of Rs 94.45 lakhs  has been approved by Standing Committee

V  Training Programmes

i)    State Govt of Tamilnadu-Has been sanctioned two projects for training programmes (i) Project for conduction training programmes in the filed of consumer protection for the benefits of self Help Groups and consumers in 31 district of Tamil Nadu at the total cost of Rs.69,90,600/-. Ist phase of the project has been completed. The second phase of the project is under consideration.

ii) 	Proposal for orientation-cum-training programme for State Govt. officials and other stakeholders of consumer rights Which is having duration period for 2 years at the total cost of Rs.21.84 lakhs  funds have  been released.

iii)    A project proposal for organizing Workshop-Cum-training programme for housewives for on the spot test to detect common adulterants in foods in  eight districts of Chennai in Tamilnadu at a cost of Rs, 29,74,000/-.  was sanctioned to CONCERT. On the recommendation of the evaluation report of the pilot project carried out by Tamilnadu Government, a second phase of the project for another 11 districts VIZ, Madurai, Vellore, Villipuram, Cuddalore, Tuticorin. Tanjore Kaurur, Tiruvallu, Slem, Perambalur and Tiruvannamalai in Phase-II Rs. 33,77, 664/- has also been sanctioned. The project has now been completed and evaluated through IIPA for consideration of the third phase of the project.

VI     Information, Education and Communication programmes for consumer awareness

A project by M/S I. Land  Informatics Limited, 58/114, Prince Anwar Shah Road, Lake Garden, Kolkatta-  for promoting Consumer awareness in Rural areas in west Bengal had been sanctioned for  Rs. 27 Lakh for conducting an IEC progarmme in six blocks in each of the six Districts of  West Bengal for strengthening consumer movement at grassroots in 2008 .The project has already been completed and a second phase of the project for another six Districts of North 24 Parganas, South 24 Parganas, Nadia, Murshidabad, Paschim Medinapur and Dakhshin Dinajpur. of West Bengal  at the Cost of Rs 30 lakhs has been sanctioned for strengthening consumer movement at grassroots . First installment of Rs 15 lakh has been released and the activities report submitted by the organization has been send to IIPA for evaluation.

2	FORWARD MARKETS COMMISSION

Reform measures/policy initiatives taken by the Forward Markets Commission during April-March 2010-11 (upto December 2010).

A.	Regulatory initiatives taken by the Forward Markets Commission:

- Following grant of recognition by the Government, granted registration to the Ahmedabad Commodity Exchange, as a Nationwide Multi Commodity Exchange, on a permanent basis in respect of forward contracts in all the commodities to which Section 15 of the Forward Contracts (Regulation) Act 1952 is applicable under the nomenclature ACE Derivatives & Commodity Exchange Limited (ACE).

- With the prior approval of the Central Government, granted in-principle approval to the Universal Commodity Exchange Limited (UCX), Mumbai, on 25th August 2010 as a Nationwide Multi Commodity Exchange, subject to the fulfilling of commitments made / undertakings given to the Commission within the stipulated time.

- Amended the guidelines for granting of recognition to new Commodity Exchanges under the Forward Contracts (Regulation) Act, 1952.

- Amended the guidelines on the equity structure of Multi Commodity Exchanges to be adopted after completing five years of their operation.

- Issued directives to the Commodity Derivatives Exchanges on the regulatory framework for market access through authorized persons in the commodity futures market, as a step towards streamlining the regulation of intermediaries in the commodity futures market.

- Issued guidelines for members of the Commodity Exchanges for setting up Joint Ventures/ wholly owned subsidiaries abroad.

- Notified ‘Iron Ore’ u/s 15 of the Forward Contracts (Regulation) Act, 1952 vide notification dated 29th September, 2010.

- Renewed recognition / registration to the following entities:

- East India Jute & Hessian Exchange Ltd., Kolkata for a further period of 1st April, 2010 to 31st  March, 2011 in respect of forward contracts (TSD) in Jute Goods (Hessian & sacking) and for the period 7th April, 2010 to 6th  April, 2011 in respect of forward contracts (futures) in Raw Jute (including mesta).

- Surendranagar Cotton Oil & Oilseeds Ltd., Surendranagar for a period of three years from 1st April, 2010 to 31st March, 2013 in respect of Kapas (seed Cotton).

- National Board of Trade, Indore in respect of Rapeseed/Mustard seed for a period of one year from 1st June 2010 to 31st May 2011. The registration of the NBOT, Indore was also renewed further in respect of Soyabean Seed, Refined Soy Oil and Soy Meal for a period of 4 months from 1st July 2010 to 31st October 2010 and again from 1st November 2010 to 28th February, 2011.

- Recommended to the ministry the renewal of recognition to Central India Commercial Exchange Ltd. Gwalior and Rajdhani Oils & 		     Oilseeds Exchange Ltd., Delhi from 1st March, 2011 to 31st March 2012 in respect of forward contracts in Rape seed /Mustard seed.

- Recommended to the Ministry to renew the recognition of Bikaner Commodity Exchange Ltd., Bikaner for a period from 20th January, 2011 to 31st March, 2012 in respect of Guarseed.

9. 	Futures trading in sugar which was suspended from May, 2009 till 30th Sept., 2010 was resumed on 27th December 2010 at MCX, and NCDEX, Mumbai and ACE Derivatives and Commodities Exchange, Ahmedabad.

B. Developmental Activities:

Developmental initiatives undertaken during the year include implementation of the price Dissemination Project, conducting awareness programmes and interactive meetings to interact with various categories of stakeholders, conducting training programmes, and 
commissioning studies on various areas of relevance to the commodity futures market.

- During the year 2010-11, 324 awareness programmes were held till 31st December 2010, which included 200 programmes for farmers. The officers of the Commission also participated in discussions on commodity market in various fora and delivered lectures on the subject at various events across the country. Five programmes were organized in the North East Region.

- 5 meetings were held by the Commission with various stakeholders. Four of the meetings were held with the arbitrators and one with Producer Companies.

- The Commission has tied up with various training institutions for conducting training for various segments of the market and other stakeholders. During 2010-11, till 31st December 2010, 33 Capacity Building Programmes were conducted.

- The Price Dissemination Scheme is currently being implemented by the Forward Markets Commission in coordination with the AGMARKNET and the National Commodity Exchange to make available spot as well as futures prices of agricultural commodities to farmers and other stakeholders on price ticker boards placed at APMCs.  During 2010-11, till December 2010, 352 price ticker boards were placed in various APMCs. Among these, 324 ticker Boards have been placed under Phase – II of the Project and 28 ticker boards in the North Eastern states.

- A consultancy study was assigned to NABCONS to ascertain the percentage of small and marginal farmers that have benefited from futures trading. Another study was assigned to MITCON, Pune, to evaluate the performance under the plan Scheme “Strengthening of FMC”. Both the studies are underway.

3	NATIONAL TEST HOUSE

The National Test House (NTH), a premier scientific institution in the field of testing and calibration technology, has its headquarter at Kolkata and functions through its six regional laboratories at Kolkata, Guwahati, Ghaziabad, Jaipur, Mumbai and Chennai. NTH regularly upgrades/augments its existing testing facilities and also procures sophisticated equipments for creating new testing facilities to meet the demands of industries.

NTH has been implementing a Plan Scheme for providing services to the industries in the field of testing, calibration and quality evaluation of materials and products of all engineering branches except pharmaceuticals, arms and ammunition. The NTH XI Plan Scheme with an outlay of Rs. 74.84 crore has been approved by the competent authority in January, 2008. The objective of the Scheme is to render assistance for improving the quality of Indian engineering products so as to meet the national/international standards for their acceptability in the global market in order to keep pace with the tremendous technological changes taking place worldwide.

To achieve this goal, apart from regrouping of its activities into three major division, i.e. physico-mechanical, electro-technical and chemical, for effective utilization of scientists, NTH has initiated working groups for business development and customer care in all its regions, NTH also proposes to undertake the testing of packaged drinking water and new high value materials and products, set up a full fledged and well equipped training centre for testing & calibration (at Alipore, Kolkata), set up Centres of Excellence and develop new business segments, i.e. software testing and inspection services, et c.

Under its XI Plan Scheme, NTH shall also implement the project for interlinking all its regional laboratories through web based Management  Information System(MIS) with a view to promote faster, transparent and customer friendly services.

4		CONSUMER PROTECTION UNIT

(i)	Computerisation and Computer Networking of Consumer Fora in the Country (CONFONET):

To enhance transparency and efficiency in the functioning of consumer dispute redressal agencies (Consumer Fora) established under the Consumer Protection Act, 1986, the ‘CONFONET’ project is being implemented through the National Informatics Centre (NIC) on turnkey basis. The project would provide for computerization of all Consumer Fora in the country. This project would enable consumers & other concerned to access information.

(ii)	Strengthening Consumer Fora:

The scheme is an extension of the Tenth Plan scheme ‘Integrated Project on Consumer Protection (IPCP)’ in the Eleventh Plan period. The scheme would further strengthen the infrastructure of the Consumer Fora so as to provide the minimum level of facilities required to make these Fora fully functional. Under this scheme, assistance would primarily be extended to States to complete the infrastructure in those Consumer Fora which were covered under the IPCP scheme.

5		PUBLICITY

In the first two years of the Plan Scheme, Department has focused on core areas of its functioning i.e. standards such as ISI and Hallmarking, provisions of Weights & Measures Act and Consumer Protection Act. However, there are large no. of consumer issues in the fast growing and emerging sectors of telecom, banking, insurance, medicines, education, travel etc.

In association with other Ministries such as Department of Chemical & Fertilizers, National Pharmaceutical Products Authority (NPPA), Bureau of Energy Efficiency (BEE), Ministry of Urban Development, Ministry of Human Resources Development, Ministry of Health and Family Welfare, Reserve Bank of India etc., Department of Consumer Affairs has released various advertisements on the specific consumer related issues to educate consumers. Advertisements were released through print media as well as electronic media on the new emerging areas of consumer interest such as telecom, real estate, credit cards, financial products, pharmaceuticals, public distribution system, travel services, mediation, C.P.A. etc.

6		LEGAL METROLOGY DIVISION

New Legislative Proposal

The Legal Metrology Act, 2009 (1 of 2010) has been published in the official Gazette of India on 14.1.2010.  The new Act will replace the existing two Acts. The new Act makes system more transparent, like outsourcing of verification activities of some of the sophisticated weights and measures and for uniform enforcement across the country.  The Department has decided to implement it from 1st March, 2011.

7		Super Bazar

The Super Bazar Karmachari Dalit Sangh had filed an SLP No. 8398-99/2005 in the Supreme Court of India. On 26.02.2009, The Supreme Court finally disposed off the aforesaid SLP and directed that the order passed on 26-02-2009 be placed before the Official Liquidator and the Central Registrar, Multi cooperative Societies who will take steps to revive the Super Bazar in terms of the orders passed by it from time to time. Pending the said revival, the order of winding up of Super Bazar will remain suspended. As and when the revival scheme comes in to force, it will substitute the order of winding up dated 05-07-2002. The Administrators have been appointed under section 123 of Multi-State Cooperative Societies Act, 2002 who are managing the day to day affairs of the Super Bazar. On 13.8.2010, the Hon’ble Supreme Court directed the Administrators to hold the election of the Board of Directors within ninety days. Accordingly, the election of the Board of Directors was held and six Directors elected. Under the provision of the Multi-State Cooperative Societies Act, 2002, the Government of India has also nominated one Director on the Board of Super Bazar. The Super Bazar has redeemed share contribution amounting to Rs. 1.16 crores to the Government of India.

CHAPTER IV

# REVIEW OF PAST PERFORMANCE

Consumer Welfare Fund  (Non-Plan )

A Consumer Welfare Fund (CWF) was created in 1992 with the objective of providing financial assistance to promote and protect the welfare of the consumers, create consumer awareness and strength consumer movement in the country, particularly in rural areas.  The State Governments and Union Territory Administrations have been impressed upon to create their own Consumer Welfare Fund.

The Other activities under the Consumer Welfare Fund relates to establishment of consumer clubs promoting involvement of Research Institutions/Universities/Colleges etc. under consumer protection and welfare.

During the 2010-11 Standing Committee approved following project-

1.  A pilot project to setup mediation advisory centre (MAC) under PPP model by department of consumer affairs GTZ and FICCI was sanctioned  at a cost of Rs. 1.05 crores for a period of 1year in which department contribute 0.58 lakh, FICCI 0.29 crores and GTZ 0.17crores.

2. National Law Institute University, Kerwa Dam road, Bhopal 462 044 M.P Project involving. Chair on professorship in consumer protection and consumer welfare at the cost of Rs. 94.45 lakh

3.       M/s Consumer Education and Research Centre (CERC) ‘Suraksha Sankool’Sarkhej-Gandinagar Highway, Thaltej, Ahmedabad for up gradation of laboratory with NABL Accreditation at a cost of Rs.1,82,34,000/-

4.      M/s Centre for Consumer unity and trust society (CUTS) D-217, Bhaskar Marg , Bani Park Jaipur- 302016 for Grassroots   Reach out & Networking in India through Consumer action in 12 districts of Rajasthan through Consumer Action  (GRANICA) at the cost of Rs 69,24,400

5.	M/S I. Land  Informatics Limited, 58/114, Prince Anwar Shah Road, Lake Garden, Kolkatta  A project by M/S I. Land  Informatics Limited, 58/114, Prince Anwar Shah Road, Lake Garden, Kolkatta-  for promoting Consumer awareness in Rural areas in west Bengal had been sanctioned for  at the Cost of Rs 30 lakhs

6.	Society for Advancement of Villages Empowerment and Rehabilitation of All (SAVERA):- The project proposal  for organizing Information and Education and Communication (IEC) programme in Katihar and Kishangarh District of Bihar for strengthening Consumer Movement has grassroots and to set up a Consumer counseling committees at Village and Block level at a cost of Rs 52.02 lakhs

7.	IIPA has been sanctioned an amount of Rs. 2.98 crores spread over a period of 3 years for consultancey project for   promoting involvement of research institutions/universities/colleges etc.

- National Consumer Helpline Second phase

ii)	Mediation Advisory Centre-A joint initiative of FICCI and GTZ with the Support of Department of Consumer Affairs.

A joint initiative of FICCI and GTZ with the support of Department of Consumer Affairs for setting up a Mediation Advisory Centre (MAC) under PPP Model has been sanctioned at the total cost of Rs. 1,03,66,000 out of which DCA share will be Rs. 56.70 lakh

iii)	Project from M/s. CONCERT for setting up Consumer Products & services Testing and Evaluation Centre.

Project from M/s CONCERT Chennai for setting up of Consumer Products & Services Testing and Evaluation Centre at Chennai for two years has been sanctioned. Total cost of the project is Rs. 172 lakh. Rs. 1.29 lakh has been released.

DEVELOPMENTAL/ACTIVITIES DURING THE CURRENT YEAR 2010-2011

iv)	Project from Govt, of Kerala

Government of Kerala has been sanctioned an amount of Rs. 25,44,000 as assistance for upgrading its Gold purity Testing Laboratory at Emakulam into a Referral Assay lab for Gold in 2010.

v)	Project from Miranda Huse, University of Delhi.

A project has been approved and sanctioned to Miranda House, university of Delhi for making consumer awareness among the students at the cost of Rs. 1.50 lakh.

Protection for the benefits of self Help Groups and consumers in 31 district of Tamil nadu i) project for training programmes from State Govt. of Tamilnadu.

Two projects for training programmes sanctioned to state Govt. of Tamil Nadu at a cost of Rs. 69.91 lakhs & Rs. 21.84 lakhs.

ii)	Mediation Advisory Centre- A joint initiative of FICCI and GTZ with the Support of Department of Consumer Affairs.

A joint initiative of FICCI and GTz with the Support of Department of Consumer Affairs for setting up a Mediation Advisory Centre (MAC) under PPP Model has been approved at the total cost of Rs. 1,03,66,000 out of which DCA share will be Rs. 56.70 lakh.

iii)	Project from M/s. CONCERT for setting up Consumer Products & services Testing and Evaluation Centre.

Project from M/s CONCERT Chennai for setting up of Consumer Products & Services Testing and Evaluation Centre at Chennai for two years has been sanctioned. Total cost of the project is Rs. 172 lakh. Rs.1.29 lakh has been released.

iv)	M/s. Mounda Dunpur Kalyan Samity, Uttarkashi (Uttarakhand)

The organization was sanctioned an amount of Rs. 45 lakh out of which Department will provide Rs. 40.50 lakh as grant-in-aid and remaining 4.50. lakh will be borne by the organization. An amount of Rs. 30 lakh has already been released. The remaining amount of Rs. 10.50 lakh will be released in the next financial year (2011-12).

v)	VOICE Society

The organization was sanctioned an amount of Rs. 3 crore of which Department will provide Rs. 2.70 crore as grant-in-aid in phases and remaining 30. lakh will be borne by the organization. An amount of Rs. 90 lakh has already been released in the current year. an amount of Rs. 90 lakh will be released (II phase) in the next year i.e 2011-12.

vi)	Controller Weight Measure, Bhopal

For setting up of Standard laboratory for W&M at Indore an amount of Rs. 68 lakh is to be released in the next financial year 2011-12.

STATE  CONSUMER  HELPLINE  SCHEME (PLAN) :-

State Consumer Helpline is a new plan scheme to set up State consumer Helpline on similar lines as National Consumer Help line which will be a partnership effort between State and active VCOs of the States. These help lines will extend service in the regional language of State concerned and in Hindi and English. Eventually these State Help lines can be networked with National Consumer Helpline so as to make use of the data base and experience already available. So far 21 states/UTs have been sanctioned funds to set up Consumer Help lines.

OBJECTIVE OF THE SCHEME

State Consumer Helpline is proposed to be established with the following objective.

- Development of a resource center at States/UTs level which will be networked with national resource center.

- Develop Alternate Consumer Disputes Redressal mechanism at States/UTs level

- Maximum no. of dispute resolved out of court

- Early resolution of complaints

- Reach out to rural consumers

- Capacity building  of State/UTs level VCOs

- States/UTs level machinery gets experience

- Companies and service providers become more active in solving consumer disputes

- Provide service in regional language in addition to English language.

CONSUMER WELFARE FUND

Statement of Outlays/Outcomes/Targets 2009-2010 and Actual Achievement 2009-10

NON-PLAN

(In crores of Rs.)

| S.No. | Name of the Scheme Programme | Objective/Outcome | Outlay 2009-10 | Expenditure 2009-10 | Deliverables/ Physical Outputs | Achievement w.r.t (Col-5) | Reason for variation |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 |
| I a | Grant-in-aid Awareness Programme including training and education Consumer Online Resource & Empowerment Centre (CORE) set up by Consumer Coordination Council, Noida (UP) | Consumer Online Resource and Empowerment (CORE) Centre project is an initiative taken by the Ministry towards web-based Consumer Awareness & Protection Programme aimed at identification of Consumer problems and their redressal through institutional approach and utilizing the information technology methods. For conducting seminar | 11.19 0.50 0.05 | 10.94 0.45 0.05 | (i)Develop in Online Database (ii) Upload and update the consumer related issues on time. (iii) Make the online information available in major local languages for the benefit of a maximum number of consumers | Total complaints received 81362 out of which 25034 and 33042 transferred to Ficci Alliance & Consumer Care. | As approved by IFD |
| b. | Indian Institute of Public Administration on : IP Estate, Ring Road, New Delhi | Setting up and running a Centre for Consumer studies in IIPA. (i) Conduct/facilitate in depth research in the area of consumer protection and consumer welfare. | 1.51 | 1.51 | i) Organize seminar/training workshops/conferences/round table on the contemporary issues relating to consumer protections. ii)Sensitize trade and industry and the Net | 71 Organizations have been sanctioned grant for undertaking research study as well as for organizing consumer rights festivals. Apart from these, Several seminars have been held. |  |
| c. | National Consumer Helpline | The National Consumer Helpline (NCH) is a landmark project set up in collaboration with the Delhi University at a cost of Rs.3,12,89,420/- spread over a period of three years. Consumers from anywhere in the country can dial the toll number 1800-11-4000 from any BSNL/MTNL telephone line and seek advice in all areas of consumer interest and sort out their grievances. The service is available in English and Hindi. | 0. 34 | 0. 34 | NCH is continuously doing efforts by forwarding the complaints to respective companies as well as by organizing discussions with officials of the companies so that the complaints get resolved before going the same to consumer courts. New guideline regarding credit cards issued by RBI is a major achievement of NCH. | Average complaints are received 5000 in a month out of which around 30% resolved. |  |
|  |  | NCH 2nd phase was sanctioned at a cost of 3.78 crores spread over a period of 3 years | 1.21 | 1.21 | NCH is continuously doing efforts by forwarding the complaints to respective companies as well as by organizing discussions with officials of the companies so that the complaints get resolved before going the same to consumer courts. New guideline regarding credit cards issued by RBI is a major achievement of NCH. | Average complaints are received 5000 in a month out of which around 30% resolved |  |
| d. e. | Comparative Testing Project Consumer Education & Research Centre Ahmadabad | The Project for setting up of Consumer Voice Centre for Comparative Testing and Products and Services was sanctioned at a cost of Rs.2,25,50,000/- spread over a period of two years. Aim of the project is to spread Consumer Awareness based on scientific studies of various consumer products to make national choices. CERC has been sanctioned an amount of Rs. 1.82 crores for up gradation of testing laboratory with NABL accreditation. | 0.62 1.37 | 0.62 1.37 | (i) Scientific data to empower consumers on national choices of the products based on their overall performance. (ii) Choices of best buy products available in the competitive retail markets. (iii) Test data for NSB to verify products compliance to national standards. (iv) Verification of claims of various manufacturers for their claims on product performance, quality, safety energy consumption/efficiency, environment & consumer friendliness Steps to enhance awareness among consumer about the products they use & serve as Resource Centre for consumers seeking information guidance and testing. | Testing of 10 products viz. Chili Powders , Potato Chips, Disinfectant Fluid, Jams, Health drinks, Lipsticks, Mosquito repellant, Mono Pump set, Juicer Mixer grinder & Color TV and Two services viz. Insurance and Banking have been done and reports have also been published in Consumer Voice magazine Yet to be received | Ist installment released |
| f. | District Consumer Information Centre (DCIC) | An amount of Rs.5, 00,000/- was sanctioned for setting up of DCICs in each district spread over a period of 3 years. The DCICs are expected to disseminate information on all aspect of consumer protection i.e. legal, administrative not only to the direct users in the centre but to all local bodies and institutions, like schools, colleges, shopping centers etc., function as a library with all essential books, pamphlets, journals etc. The Centre is also expected to liaise with the District Consumer Protection Officer and other local officers and to organize all important functions relating to consumer awareness. | 0. 25 | 0.05 | Final installment to DCICs which have already set up | Effective dissemination of information and to guide more number of Consumers. | DCICs has not applied for final installment |
| g. | FICCI Alliance for Consumer Care | To facilitate prompt redressal of consumer grievances through interface between Business and the Consumer, a project has been sanctioned to FICCI at a cost of Rs.3.10 Crores spread over period of 3 years. | 0.50 | 0.47 | 1. Interface between business and the Consumer 2. Develop and introduce a voluntary code of conduct for business-consumer relationship etc. | Better public private relation will be develop and private sector will also become more responsible before consumers. | As approved by IFD |
| h. | CONCERT, 3/242, Rajendera garden, Vettuvankeni Chennai-600041 | This pilot project is planned to create awareness about prevention of food adulteration in eight selected districts of Tamilnadu among members of self-help groups/housewives by educating them regarding health hazards due to adulteration. It has been proposed to train them about methods of detection of adulterants, using the Ann am Spot Test Kit | 0.08 | 0.08 | 30 participants for each training programme to motivate to create awareness among their family members, in their workplace and neighborhood communities by demonstrating what they learn with the Annam Spot Test Kit. | 720 trained personnel will be ready to disseminate the food safety message to at least 20 persons each as mentioned above Over a period of one or two months around 15000 people known to the trained participants would have been educated on food safety. A demo CD will be made available to each trainee to be used to broadcast the message in their community, and would expect a reach of 500 per | -- |
| i. | SAVERA | To impart consumer education to create awareness. To identify and disseminate best practices in the field of consumer protection Organize seminar/ workshops conferences etc. on consumer related issue at village/block/ district levels To set up consumer counseling committee at village / block at levels | 0.20 | 0.20 | 43 Panchayat level programme 28 Block level programme 2 District level programme | 1. Formed 70 Consumer action committees and one 30 member committee at district level and these committees serve as information centers for all kinds of local queries. 2.Larger perception of participation on the part of the consumer committee members, who will serve as tem leaders and opinion perpetuators for consumer awareness. 3. About 1.8 lakh people wee directly given message of consumer awareness and consumer rights etc. 4.Direct contact encouraged a wider discussion of the issues involved between the target audience and committee members. | -- |
| j. | Indian Institute of Public Administration IP Estate, Ring Road, New Delhi Grant provided to IIPA for the extended period of the consultancy project. | Scheme on promoting involvement of research Institutions/Universities/colleges etc. in Consumer Protection and Consumer Welfare sponsor seminars/workshops/conferences on the consumer and to have necessary inputs for formulation of policy/programme/scheme for the protection and welfare of Consumer. The Indian Institute of Public Administration has been appointed as consultant under the scheme to the Department of Consumer Affairs for three years. | 0.95 0.35 | 0.95 0.35 | Sponsor seminars/workshops/conferences on the consumer and to have necessary inputs for formulation of policy/programme/scheme for the protection and welfare of Consumer. | Measure general consumer awareness among the students communi-cated through various schemes such as consumer research festivals, seminars,/ conferences/ workshops. |  |
| k. | M/s Binty | Draft a bill to help credit recoveries from various sectors like banking, telecom, insurance, pharmaceutical companies etc into the Consumer Welfare Fund in the interest of consumers. | 0.05 | 0.02 | Drafting a bill to help credit recoveries | After drafting a bill it is being proposed to make amendment in the law for making credit recoveries from segment , like trade intesting etc on account of unjust enrichment to CWF | Only first installment of Rs 2.25 lakh has been released |
| l. | Consumer Association of India | Workshop on Package Commodities Rules and Weights and Measures Act and Rules | 0. 008 | 0.008 | Workshop on Package Commodities Rules and Weights and Measures Act and Rules for custom officials in Chennai. | This was the first workshop conducted on the subject after the ACT was implemented which was tremendous success. |  |
| m | Council for Fair Business Practice, Mumbai, Maharashtra (CFBP) | for up gradation of test laboratory and for complaint handling | 0.56 | 0.53 | For consumer complaint handling by CFBP. Rs.6 lakhs is sanctioned for complaint handling per years for 5 years and Rs 50 lakh for up gradation of test laboratory |  |  |
| n | M/S I. Land Informatics Limited, 58/114, Prince Anwar Shah Road, Lake Garden, Kolkatta | To conduct an IEC programme in six blocks in each of the six Districts of North 24 Parganas, South 24 Parganas, Nadia, Murshidabad, Paschim Medinapur and Dakhshin Dinajpur. of West Bengal for strengthening consumer movement at grassroots | 0.30 | 0.15 | A baseline study for rapid appraisal of level of awareness on consumer right and laws for understanding existing mechanism for consumer education and redresses of grievances at district level | - Good reach among rural population - Campaign made people who have no idea about consumer rights more aware and ways to protect themselves - Create enthusiasm for advocacy and action to protect consumer rights. | First installment of Rs 15 lakh has been released so far |
| o. | Consumer Guidance society of India Mumbai | Organizing seminar on Consumer Awareness. | 0.02 | 0.02 | Organizing seminar on Consumer Awareness. |  |  |
| p. | Shri K.N. Chaturvedi, retired Secretary (Legal Affairs), Govt. of India to provide consultancy for revision and reformulation of the proposal to set up National Consumer Protection Authority (NCPA) and draft the Bill for creating the legislative framework for the proposed NCPA. | To provide consultancy for revision and reformulation of the proposal to set up National Consumer Protection Authority (NCPA) and draft the Bill for creating the legislative framework for the proposed NCPA. | 0.01 | 0.01 | To provide consultancy for revision and reformulation of the proposal to set up National Consumer Protection Authority (NCPA) and draft the Bill for creating the legislative framework for the proposed NCPA. |  |  |
| q. | NCDRC | For purchase of Law books/Journals/Periodicals on Consumer Awareness. | 0.25 | 0.25 | For purchase of Law books/Journals/Periodicals on Consumer Awareness. |  |  |
| r. | Centre for Consumer Unity & Trust Society (CUTS) Jaipur has been sanctioned an amount of Rs. 62,31,960/- for grass root reach out & networking in India through Consumer action in 12 districts of Rajasthan (GRANRICA) | Understanding the consumer protection issues and status of redressal mechanism and awareness generation among the common consumer especially in the rural areas. Building up of large group of grassroots activists, who in turn can mobilize and assist illiterate and helpless consumers to access consumer justice and uphold their rights. Mobilization of consumer protection groups at the grass roots in twelve selected districts in the five selected divisions. Creation of a vibrant network of small consume reorganizations groups and interested individual ex tending down up to the block level. Enhancement of the capacity of identified CSOs to handle emerging and relevant consumer issues woven around basic needs, ensure improvement in service delivery and to play the watchdog role in their respective district. Initiation and building blocks for strengthening and sustaining consumer movement at the grassroots. | 0.24 | 0.24 |  | Yet to be received | First Installment released |
| 2a. | 3601 Grant-in-aid to State Government Consumer Club | This scheme was launched in 2002, according to which a consumer club shall be set up in each Middle/High/Higher Secondary/Colleges affiliated to a government recognized Board/Universities. A grant of Rs.10,000/- per consumer club is admissible under this scheme. Main aim of the scheme are to educated children about the rights of the consumer as provided in the Consumer Protection Act, 1986, to mobilize youngsters by instilling in them the spirit of protection of Consumer Rights. | 3.00 1.00 crores* for Consumer Club and Seed Money both | 0.77 | A baseline study for rapid appraisal of level of awareness on consumer right and laws for understanding existing mechanism for consumer education and redresses of grievances at district level | Children are getting aware about the consumer rights by consumer clubs set up in the schools. | State Govt. /Uts have not applied for the fund. Reminder has been sent |
| b. | Seed Money | In order to promote the Consumer movement throughout the country the State Govt. have been impressed upon to create their own Consumer Welfare Fund. For encouraging them to do so, the amount of seed money given to the States has recently increased from 1:10 to 50:50 and 90:10 in respect of 13 special category States. | 1.00 crores* for Consumer Club and seed money both | -- | State Consumer Welfare has been set up in 20 States so far. During 2009-10 remaining 15 states /UTs will be included in this scheme. | Consumer movement will become stronger by setting up of State Consumer Welfare Fund. | Proposal not received from State despite repeated reminders |
| 3a. | 3602 Grant-in-aid to UT Governments 01.00.31 Consumer Clubs | This scheme was launched in 2002, according to which a consumer club shall be set up in each Middle/High/Higher Secondary School/Colleges affiliated to a government recognized Board/University. A grant of Rs.10,000/- per consumer club is admissible under this scheme. Main aim of the scheme are to educate children about the rights of the consumers as provided in the Consumer Protection Act, 1986, to mobilize youngsters by instilling in them the spirit of protection of Consumer Rights. | 0.50 0.47 for Consumer Club and Seed Money both | 0.05 | 50 consumer clubs has been set up on one UT ie. Govt of Chandigarh UT | Children are getting aware about the consumer rights by consumer clubs set up in the school | Proposal not received from State despite repeated reminders |
| ## b. | ## Seed Money | ## In order to promote the consumer movement throughout the country, the State Government have been impressed upon to create their own Consumer Welfare Fund. For encouraging them to do so, the amount of seed money given to the States has recently increased from 1:10 to 50:50 and 90:10 in respect of 13 special category States. | ## 0.47 for Consumer Club and Seed Money both | ## --- | ## State Consumer Welfare has been set up in three UTs Government so far. | ## Consumer movement will become stronger by setting up of State Consumer Welfare Fund. | ## Proposal not received from State despite repeated reminders |

ANNEXURE-II

The highlights covering objectives, targets and achievements in the field of consumer awareness during the year 2010-11 are tabulated as under:-

Statement of Proposed Outlays and Outcomes/Targets for 2010-11

(In crores of Rs.)

| S.No. | Name of the Scheme Programme | Objective/Outcome | Outlay 2010-11 | Expenditure During 2010-11 up to 31.12.2010 | Quantifiable Deliverables | Achievement w.r.t (Col-5) | Reason for variation |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 |
| 1.a | Grant-in-aid 04.01.31 Awareness Programme including training and education Consumer Online Resource & Empowerment Centre (CORE) set up by Consumer Coordination Council, Noida (UP) | Consumer Online Resource and Empowerment (CORE) Centre project is an initiative taken by the Ministry towards web-based Consumer Awareness & Protection Programme aimed at identification of Consumer problems and their redressal through institutional approach and utilizing the information technology methods. The estimated cost of the project is Rs.35,50,000/- (Five year project) | 8.99 0.50 | 5.74 -- | (i) Develop in Online Database (ii) Upload and update the consumer related issues on time. (iii) Make the online information available in major local languages for the benefit of a maximum number of consumers | More than 22 Thousand Complaints received form 1st January 2008 to 31st March 2009. from all parts of India and also from abroad out of which total 6698 complaints have been resolved. | Non clearance of Audit paras |
| b. | Indian Institute of Public Administration on : IP Estate, Ring Road, New Delhi IIPA- Consultancy project(2008-09) Extended period Grant provided to IIPA for the extended period of the consultancy project | Setting up and running a Centre for Consumer studies in IIPA. Conduct/facilitate in depth research in the area of consumer protection and consumer welfare. | 1.66 0.75 0.99 0.34 | 0.75 -- 0.34 | (i).Organize Seminar/training workshops/conferences/round table on the contemporary issues relating to consumer protections. (ii). Sensitize trade and industry and the Net | 71Organizat-ions have been sanctioned grant for undertaking research study as well as for organizing consumer rights festivals. Apart from these, Several seminars has been held. | To be released. This amount has been release as additional grant on account of increase in pay scale according to 6th CPC To be released. |
| c. | Comparative Testing Project i).CONCERT Chennai ii).VOICE Society iii).VOICE Society iv).CERC Consumer Education & Research Centre Ahemdabad | The Project for Comparative Testing and Products and Services . CONCERT Chennai has been sanctioned an amount of Rs. 3.34 crores for a period of 2 years for undertaking comparative testing of products & services (Interim Phase for comparative testing of Products and services. Sanctioned an amount of Grant in aid of Rs. 2.70 crores for comparative testing of products & services to 2nd phase. CERC has been sanctioned an amount an additional amount of .27 lakhs on account of variation in the cost of 2 equipment. | 1.29 0.18 0.90 0.27 | 1.29 0.18 0.90 0.27 | Undertake comparative testing/evaluation of at least 7(Seven) products and 3 (three) services per year. To further develop the existing website of the second party to more technologically superior platform that offers better facilities to the user. To decimate the test reports in four south Indian languages viz. Tamil, Kannada, Malayalam and Telugu besides Hindi and English and thereby increase awareness among consumers about the product they use. Regular Monitoring of quality of products & services through comparative testing. Publication of results in four south Indian languages, Hindi and in English to disseminate full information to the consumers in an attractive & reader friendly manner. Governments for dissemination of tests results through other regional languages specially of Northern States. Use Jago Grahak Jago Campaign for covering the Comparative Testing subject and its test results with suitable disclaimer to make impact on consumers. The Jago Grahak Jago campaign would inform public at large on the release of latest test results and their availability. Undertake comparative testing/evaluation of products and services. To provide a suitable link to www.consumer-voice.org with appropriate disclaimer clause to the web site of the First Party. To enhance the sale of the Consumer Voice Magazine and thereby gradually reduce the dependence of Govt. support to 35% of total operating expenses (covering Grant amount plus own income) at the end of 3 years. To increase awareness among consumers about the products they use. Steps to enhance awareness among consumers about the products they use & serve as Resource Centre for consumers seeking information guidance and testing. | Yet to be received Testing of products and services will not overlap by the other organization. The products/services which have been tested by one will not be tested by other organization. Additional Grant Sanction on Account of Variation in cost of to equipment. | First Installment released IInd & final Installment released Ist installment released. |
| d. | District Consumer Information Centre (DCIC) | An amount of Rs.5, 00,000/- was sanctioned for setting up of DCICs in each district spread over a period of 3 years. The DCICs are expected to disseminate information of all aspect of consumer protection i.e. legal, administrative not only to the direct users in the center but to all local bodies and institutions, like schools, colleges, shopping centers etc., function as a library with all essential books, pamphlets, journals etc. The Centre is also expected to liaise with the District Consumer Protection Officer and other local officers and to organize all important functions relating to consumer awareness. | 0.25 | --- | Final installment to DCICs which have. already set up |  | Fund could not be released due to non receipt of Inspection reports from DC/DM |
| e | FICCI Alliance for Consumer Care | To facilitate prompt redressal of consumer grievances through interface between Business and the Consumer, a project has been sanctioned to FICCI at a cost of Rs.3.10 Crores spread over period of 3 years. | 0. 57 | 0.57 | i).Interface between business and the Consumer ii).Develop and introduce a voluntary code of conduct for business-consumer relationship etc. | Better public private relation will be develop and private sector will also become more responsible before consumers. | First installment of third year released. |
| f. | I-Land Informatics Ltd. Kolkata | Awareness activities in rural areas of West Bengal | 0.15 | 0.15 | A baseline study for rapid appraisal of level of awareness on consumer right and laws for understanding existing mechanism for consumer education and redresses of grievances at district level | - Good reach among rural population - Campaign made people who have no idea about consumer rights more aware and ways to protect themselves - Create enthusiasm for advocacy and action to protect consumer rights. |  |
| g. | Binty. New Delhi | Awareness activities. | 0.02 | 0.02 | Drafting a bill to help credit recoveries | -- | Second Installment released. |
| h. | Centre for Consumer Protection Research & Awareness, Indore | Consumer awareness activities | 0.05 | 0.05 | For organizing State level workshop. Undertaking programme on Consumer awareness in educational Institutions and rural areas. |  |  |
| i. | Miranda House, University of Delhi | To create awareness among consumers, especially students, about their rights and duties. | 0.18 | 0.18 | The Consumer Awareness programme for the year 2009-10 has taken initiatives of conducting variety of activities such as logo competitions, inter colleges quiz and debate competition, a short term certificate course on consumer awareness, panes discussion and seminar on consumer affairs, screening of a documentary film on consumer development related issues, holding of a symposium of students and experts on consumer awareness and launching of an annual college consumer magazine. | College students will become aware about the consumer rights. |  |
| j. | Govt. of Tamil Nadu | Training programmes for women self help groups | 0.65 | 0.65 | The project is to for undertaking training programmes for Women Self Help Groups in three steps i.e. district level, block level and panchayat level in the 2nd phase in 260 blocks in 900 villages. | Final Report to be received |  |
| k. | M/S Vinod Kumar Memorial Trust, B-2/4, Model Town-II, New Delhi- | To upgrade and maintain the website Midguideindia.Com for strengthening consumer information on drugs and allied sectors. | 0. 10 | 0.10 | The primary objectives of the project is to take steps to enhanced consumer information on Drugs and Allied services | Web site upgraded |  |
| l. | Council for Fair Business Practice, Mumbai, Maharashtra (CFBP) | i) For Consumer grievance redressal activity by CFBP for 5 years. ii.) For up gradation of Ramakrishna Bajaj Consumer Education Testing Centre located at SNDT Women University at Mumbai. | 0.06 | -- | i).To resolve maximum number of consumer complaints outside the consumer forum ii)To take steps to enhance awareness among consumers about the products they use. ii) To provide testing facilities at a reasonable costs & serve as Resource Centre seeking information, guidance and testing. | To create awareness amongst consumers about the product they use and provide various analytical /quality testing facility for the same. Serve as a resource base for consumers seeking information, guidance and testing. | Five Years |
| m. | Govt. of Kerala | Upgrading gold purity testing laboratory at Ernakulam | 0.25 | 0.25 | Up gradation of their gold purity testing laboratory at Kakkanad, Eranakulam in to a Referral Assay Lab for Gold. | -- | -- |
| 2a. | 3601 Grant-in-aid to State Government Consumer Club | This scheme was launched in 2002, according to which a consumer club shall be set up in each Middle/High/Higher Secondary/Colleges affiliated to a government recognized Board/Universities. A grant of Rs.10,000/- per consumer club is admissible under this scheme. Main aim of the scheme are to educated children about the rights of the consumer as provided in the Consumer Protection Act, 1986, to mobilize youngsters by instilling in them the spirit of protection of Consumer Rights. | 3.00 | 0.10 | Grant released to Nagaland for 100 consumer Clubs. Children are getting aware about the consumer rights by consumer clubs set up in the school. | Report not received | Sufficient proposals were not received despite repeated reminders. |
| b. | National Law School of India University Bangalore | For conducting moot court & activities | 0.09 | 0.09 | -- | Final report yet to be read. |  |
| c. | CUTS Centre for Consumer unity and trust society D-217, Bhaskar Marg , Bani Park Jaipur- 302016 | For conducting a seminar on competitive regime on consumer jointly conducted by Department of Consumer Affairs, Competition Commission of India, Ministry of corporate Affairs & CUTS. | 0.02 | 0.02 | -- |  |  |
| d. | Consumer Association of India, Chennai | Conductive a seminar on legal meteorology & an amendment of the consumer protection Act | 0.03 | 0.03 | -- |  |  |
| e. | Mounda Dhunpur Kalyan Samiti, uttarakashi has been sanctioned Rs. 45 lakhs for conducting consumer awareness in two backward districts of Uttarakhand | 1. Prevention of exploitation of rural consumers of Hill areas of Uttarakhand by empowering them about Consumer rights using innovative consumer awareness program. 2. Conduct survey to get the actual number of senior citizen who qualify for the govt. pension and who are eligible yet not getting the pension and arrange the facility for them to get their right of pension. 3. Conduct survey of below poverty line eligible families and help them in securing the Ration card as per their financial status so that they can get their right of subsidized food grain as well as rice provided by the govt. via PDS. 4. Empowering the consumer on legal matters and their right to get the fair and unbiased trial as well as help. Special drive and awareness program for backward classes and women. | 0.30 | 0.30 | -- |  | First Installment released. |

Regional Reference Standards Laboratories (RRSLs)

The Central Government has established five Regional Reference Standards Laboratories at Ahmedabad, Bangalore, Bhubaneswar, Faridabad and Guwahati to check periodically the legal standards of weights and measures of State Government laboratories as well as to carry out calibration and testing of weights and measures of industries of the region.

The basic objectives of establishing RRSLs are as follows;

- Periodic verification of legal standards of weights or measures of States/UTs in the region.

- To conduct model approval tests of weighing and measuring instruments covered under Legal Metrology.

- Calibration of measuring instruments used by industries.

- Liason with States Weights and Measures Dept., and to conduct surveys to check effective implementation of laws in various sectors of economy.

- To conduct need based training seminars for enforcement officials of the region.

Scheme

The Department of Consumer Affairs, Government of India has formulated two Schemes during XI Plan, namely Strengthening of Legal Metrology wing of the States and Union Territories and Strengthening of Regional Reference Standards Laboratories (RRSLs) and Indian Institute of Legal Metrology (IILM), Ranchi.

  - Scheme “Strengthening of Legal Metrology wing of the States and Union Territories”.

The objective of the scheme is augmentation of State’s Legal Metrology infrastructure in holistic way by construction of laboratory building, supply of equipments and their capacity building of enforcement officials for effective implementation of weights and measures laws.

A new scheme with an outlay of Rs. 143.286 crore is being implemented during 2009-12 to strengthen the State enforcement machinery in a holistic way. Under this scheme, during 2009-10, Grant in Aid of amount Rs. 21.47 Crore was given to 17 States/UTs States for the construction of Secondary/ Working Standard Laboratories and Rs. 4.54 Cores were given to Indian Government Mumbai, for supply of Secondary/ Working Standard Weights to Sates/ UTs.  Rs.1.54 Cores has been spent to develop mass flow measurement facility in the RRSLs.

During 2010-11, the Department is providing 31 sets of smaller mobile kits for testing weighbridges to States/UTs.  India Government Mint has started the supply of Secondary/Working Standard Weights to States/UTs.  The Government has also given approval to India Government Mint, Mumbai for supplying working standard capacity measures and check measures for testing of dispensing pumps to States/ UTs.

Rs. 10.21 crore grant in aid has already been given to Govt. of Bihar, Maharastra, U.P., H.P., Kerala out RE 10.37crore and Rs.1.24 crore to Tripura for the construction of secondary/working standard laboratory.

2.  Strengthening of Regional Reference Standards Laboratories

(RRSLs) and Indian Institute of Legal Metrology (IILM), Ranchi.

The objective of scheme is to strengthen RRSLs and IILM by complimenting the existing facility in mass, volume and length measurement. The total outlay of the scheme is 23.1 crore. The scheme aims at providing better testing facilities in force, torque and flow measurement for better consumer protection.

During 2009-10, Rs. 1.53 crore had been spent to develop mass flow measurement facilities in the RRSLs.

During 2010-11, it is proposed to supply EFT, ESD, Voltage dip simulators, G-TEM equipments costing Rs.6.42 crore to RRSLS. Besides, Rs.3.5 crore is earmarked for renovation of IILM building.

Rs. 2.79 crore has been spent for supply of EFT, ESD, Voltage dip simulator to all RRSLs for testing electronic indicators of weighing and measuring instruments and balance payment for setting up of flow measurement laboratory to RRSL, Ahmedabad.  Rs 3.0 Crore has been given to CPWD, Ranchi for the renovation of IILM, Ranchi. The facility will help oil industries in the calibration of their flow meters.

The Highlights of the schemes, objectives and achievement by RRSLs during the year 2009-10 are as follows:

(Rs. In crore)

| S. No. | Name of Scheme/ Programme | Objective/Outcome | Outlay 2009-10 |  |  | Actual Expenditure |  | Quantifiable Deliverables/Physical Outputs | Achievements w.r.t col.6 | Reasons for variation |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | 2 | 3 | 4 |  |  | 5 |  | 6 | 7 | 8 |
|  |  |  | 4 (i) | 4(ii) | 4(iii) |  |  |  |  |  |
|  |  |  | Non-plan Budget | Plan Budget | Complementary Extra-Budgetary Resources | Non-Plan | Plan |  |  |  |
| 1 | Strengthening of weights & Measures infrastructure in states/Uts | To Strengthen the infrastructure Of Legal Metrology in states for better enforcement of weights &measures laws | 3.1 | 6.0 | --- | 3.00 | 1.15 | Supply of smallar Mobile kit for testing of weigh bridges, supply of working/secondary standards Weights and working standards capacity measures, Check Measures to various states/UTs | 31 sets of smaller mobile kits for testing weighbridges to States/ UTs, Grant-in- aid of Rs.1.24 Cr. to Tripura & Rs. 10.21Cr. to Bihar, Maharastra, Kerala, U.P., H.P. | Supply order Placed to India Govt. Mint for 147 sets of Working Std. Capacity Measures & 1700 check Measures costing Rs.1.84 Cr & 8.64 Cr., respectively. |
| 2 | Strengthening of RRSL &IILM Ranchi | To strengthen Infrastructure at basis better consumer protection | -- | 11.6 | -- | --- | 17 | Creation of new Testing Facility like Flow measurement etc and to provide testing equipment for conducting electrical testing equipments. . | EFT, ESD, Voltage dip simulator, G-TEM equipment provided RRSLs. Rs 3.0 Cores to CPWD, Ranchi for renovation of IILM, Ranchi. | Flow measure- ment facility has been completed at RRSL, Ahmedabad & likely to be completed at RRSL, Bhubaneswar by December, 2010 |

CONSUMER PROTECTION UNIT

REVIEW OF PAST PERFORMANCE

Review of 2009-10

(Rs. in Crores)

| Sl No | Name of the Scheme/ Programme | Objective/ Outcome | Outlay 2009-10 | Actual Expen-diture | Quantifiable Deliverables | Achievements w.r.t Col (6) | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- |
| (1) | (2) | (3) | (4) | (5) | (6) | (7) | (8) |
| 1. | Consumer Protection Cell | The Consumer Protection Cell renders secretarial assistance to the Deptt. in administering the Consumer Protection Act, 1986 and related activities. | 0.30 | 0.2726 | To hold at least one meeting of the Central Consumer Protection Council (CCPC) during the period. | One meeting of the CCPC has been held on 3rd September, 2009. | - |
| 2. | Construction of building of the National Consumer Disputes Redressal Commission (National Commission). | Construction of the office building as part of the integrated Office Complex. Availability of adequate space would enable the National Commission to function more efficiently. It will also provide more consumer friendly facilities to enable more benches to be operational for expeditious disposal of cases. | 9.90 | 9.90 | Construction of the building for the National Commission. | Construction work of the building being carried out in full swing. Building was expected to be completed by June, 2010. | - |
| 3. | Computeriza-tion and computer networking of Consumer Fora (CONFONET) | The project is being implemented through the National Informatics Centre (NIC) on turnkey basis, which would provide for computerization of all Consumer Fora in the country. The project would allow consumers & others concerned to access information. | 12.18 | 7.10 | The NIC to undertake the following activities: i) To supply computer hardware and software to all locations not covered by 31.03.2009. ii) To set up a Project Cell. iii) Setting up a Central Server at data centre. | NIC is in the process of making the system functional at locations where Computer Hardware & Software have been installed. Data is being uploaded at several of these locations. | Budgetary allocation reduced to Rs. 7.10 crores at RE stage. |
| 4. | Strengthening Consumer Fora | The scheme would further strengthen the infrastructure of the Consumer Fora so as to provide the minimum level of facilities required to make these Fora fully functional. The assistance to all the eligible States/UTs will strengthen the infrastructure of the Consumer Fora for their effective functioning. | 9.71 | 7.0050 | (i) The new scheme of ‘Strengthening Consumer Fora’ to be formulated on the basis of evaluation study of the IPCP scheme. (ii) New scheme to be appraised and approved by the competent authority (iii) Release of second instalment to States, due for buildings of consumer fora from the IPCP scheme. (iv) Release of grants to other States. | Strengthening Consumer Fora scheme formulated, appraised by the EFC and approved by the competent authority for implementation during the Eleventh Plan. | Budgetary allocation has been reduced to Rs. 5.00 crores at RE stage. |
| 5. | Setting up of the National Trade Practices Regulation Authority (NTPRA) | To create an authority to address the gap in legislation on account of repeal of the Monopolies and Restrictive Trade Practices Act and the Competition Act, 2002 into force. It would also perform important functions of taking proactive measures for protection of consumer interests through training and innovative programmes. | 0.01 | Nil | - | - | Token provision. The scheme is yet to be approved. |
|  |  | Grand Total : | 32.09 | 24.2776 |  |  |  |

Review of performance in 2010-11

(Rs. in Crores)

| Sl. No | Name of the Scheme/ Programme | Objective/ Outcome | Outlay 2010-11 | Actual Expen-diture (as on 31.12.10) | Quantifiable Deliverables | Achievements w.r.t Col (6) as on 31-12-2010 | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- |
| (1) | (2) | (3) | (4) | (5) | (6) | (7) | (8) |
| 1. | Consumer Protection Cell | The Consumer Protection Cell renders secretarial assistance to the Deptt. in administering the Consumer Protection Act, 1986 and related activities. | 0.50 | 0.0020 | Hold one meeting of the Central Consumer Protection Council (CCPC) during 2010-11. | Since the term of current CCPC has expired, action is underway for its reconstitution. Next meeting of CCPC can only take place thereafter. | - |
| 2. | Strengthening infrastructure of new NCDRC Building | To provide necessary infrastructural facilities for effective functioning of NCDRC; so as to create consumer friendly environment. | 3.44 | 2.39 | Provision of office modules as per requirement. | Rs. 2.39 Crores estimated by CPWD for the purpose, has been released to them. | New scheme |
| 3. | Computeriza-tion and computer networking of Consumer Fora (CONFONET) | The project is being implemented through the National Informatics Centre (NIC) on turnkey basis, which would provide for computerization of all Consumer Fora in the country. The project would allow consumers & others concerned to access information. | 9.00 | 8.89 | Provision of HR support through Technical Support Personnel, for eventual adoption of system by respective Consumer Fora themselves. Upgradation of skill by means of training, workshops etc. | Rs. 8.89 crores have been released to NIC for carrying out activites under the scheme | - |
| 4 | Strengthening Consumer Fora | The scheme would further strengthen the infrastructure of the Consumer Fora so as to provide the minimum level of facilities required to make these Fora fully functional. The assistance to all the eligible States/UTs will strengthen the infrastructure of the Consumer Fora for their effective functioning. | 14.91 | 8.0268 | Prioritizing the completion of the infrastructure of those Consumer Fora in 21 States, which were covered under the IPCP scheme. Consumer Fora in remaining States to be also covered subject to eligibility & availability of funds. | Rs. 8.03 crores has been sanctioned under the scheme covering the States of Punjab, Tripura, Nagaland, Kerala, Sikkim & Gujarat. | - |
| 5. | Setting up of the National Trade Practices Regulation Authority (NTPRA) | To create an authority to address the gap in legislation on account of repeal of the Monopolies and Restrictive Trade Practices Act and the Competition Act, 2002 into force. It would also perform important functions of taking proactive measures for protection of consumer interests through training and innovative programmes. | 0.01 | Nil | - | - | Token provision. The scheme is yet to be approved. |
|  |  | Grand Total : | 27.86 | 19.3088 |  |  |  |

A review of performance of Plan Scheme “Strengthening of FMC” during 2009-10.

Statement of Outlays & Outcomes/Targets (2009-10) (As per the Outcome Budget 2009-10) and achievement  as on 31st March 2010

( Rs. in crore)

| S.No. | Name of the Scheme/ Progranne | Objective Outcome | Outlay 2009-10 | Quantifiable Deliverables | Achievements |
| --- | --- | --- | --- | --- | --- |
| 1 | Strengthening of FMC | Efficient Regulation of the Commodity Futures Market. | Total Rs. 18.00 crore (BE) Rs. 8.05 crore (RE) |  |  |
|  |  | i) Strengthening of IT. | Upgradation of IT facilities Rs. 0.30 crore | - Purchase of equipments and development of software for market monitoring and surveillance and other software, improving connectivity (intranet and internet), Subscribing to Real Time News services (CRISIL, Bloomberg, Reuters, etc.) to ensure better monitoring and surveillance. iii. Connectivity with Exchanges | Process of identification of vendor for software development is on. |
|  |  | ii) Organizing capacity building programmes for policy makers. iii) Organising training programmes for the staff of FMC and the exchanges. iv) Conducting audits of exchanges and their members. v) Awarding consultancies/studies in area of interest to the FMC and the commodity futures market and engaging professionals in necessary areas for assisting in the functioning of the FMC. | Capacity Building/Training/consultancies Rs. 2.60 crore | - Capacity building - 35 programmes - Performance audit - 300 members of National Exchanges + Regional Exchanges - Consultancy assignments - 5 | - Capacity building - 63 programmes - Performance audit - 290- members of National Exchanges + 14 Regional Exchanges and 3 National Exchanges. - Consultancy assignment - 2 |
|  |  | vi) Increasing the awareness level of different categories of stakeholders especially farmers to make them aware of the existence as well as the benefits of the futures markets vii) Interactions with various stakeholders in the commodities futures market to understand their difficulties, problems and their needs so as to align/design policies to meet feasible/desirable objectives. viii) Undertaking publicity measures to disseminate information about the commodity futures market. ix) Coordinating with international regulatory bodies for increased adoption of best practices. . | Awareness and Development programme Rs. 1.68 crore | - Awareness Programmes - 250. - Meetings - 10 - Advertisement in 47 dailies + 38 dailies in the North East. - MOUs - 2 | - Awareness Programme 515 - Meetings - 8 - Advertisement in 47 dailies + 38 dailies in North East from December, 2009 - MOUs - 1 MoU with Brazil |
| 4 |  | x) Dissemination of prices through APMC s | Price Dissemination Project Rs. 3.16 crore | Launching of phase-I of the project in 180 mandis. | • 183 price ticker boards installed. |
| 5 |  | xi) Locating and moving the office into a suitable premises | Upgradation of office infrastructure Rs. 0.31 crore | i) Identification of new office premises and payment of rent for hired premises, municipal rates, taxes, etc. (Hiring of office premises) ii) All contingent expenses for running an office, such as furniture, postage, purchase and maintenance of office machines and equipments, etc. | • Process of seeking approvals from the Ministry for new office premises is under way. . |

A review of performance of Plan Scheme “Strengthening of FMC” during 2010-11.

Statement of Outlays & Outcomes/Targets (2010-11) (As per the Outcome Budget 2010-11) and Actual Achievement

(Rs. in crore)

| S.No. | Name of the Scheme/ Progranne | Objective Outcome | Outlay 2010-11 | Quantifiable Deliverables | Achievements |
| --- | --- | --- | --- | --- | --- |
| 1 | Strengthening of FMC | Efficient Regulation of the Commodity Futures Market. | BE 17.50 RE. 9.68 |  |  |
|  |  | i) Strengthening of IT. | Upgradation of IT facilities Rs. 1.45 crore | • Purchase of equipments and development of software for market monitoring and surveillance and other softwares, improving connectivity (intranet and internet), • Subscribing to Real Time News services (CRISIL, Bloomberg, Reuters , etc.) to ensure better monitoring and surveillance. • Connectivity with Exchanges • Developing the IT capacity of Regional exchanges. • Outsourcing of IT related activities | • Devlopment of software for automation of Member Registration system • Invitation of EOI and presentation held by the bidders for procurement of Market Monitoring Surveillance System Software in the month of September, 2010 • Renewal of Subscription of News Feed Services - News Wire 18" and Reuters for the use of officers at FMC |
|  |  | ii) .Organizing capacity building programmes for policy makers. iii) Organising training programmes for the staff of FMC and the exchanges. iv) Conducting audits of exchanges and their members. v) Awarding consultancies/studies in area of interest to the FMC and the commodity futures market and engaging professionals in necessary areas for assisting in the functioning of the FMC. | Capacity Building/Training/consultancies Rs. 2.82 crore | - Capacity building - 70 programmes - Performance audit - 320 - Consultancies as required | - Capacity building - 33 programmes. - Performance audit - 316 - Consultancies underway - 2 |
|  |  | vi) Increasing the awareness level of different categories of stakeholders especially farmers to make them aware of the existence as well as the benefits of the futures markets vii) Interactions with various stakeholders in the commodities futures market to understand their difficulties, problems and their needs so as to align/design policies to meet feasible/desirable objectives. viii) undertaking publicity measures to disseminate information about the commodity futures market. ix) Coordinating with international regulatory bodies for increased adoption of best practices. | Awareness and Development programme Rs. 1.75 crore | - Awareness Programme - 300 - Meetings - 10 - Advertisement in national/regional and North East Area dailies - MOUs - as per requirement | - Awareness Programme - 324 - Meetings - 5 - Proposal for Advertisement in National/ regional dailies and dailies in North East Areas sent to DAVP |
|  |  | x ) Dissemination of spot and futures prices of commodities traded in the futures market | Price Dissemination Project Rs. 2.53 crore | - Launching of Price Dissemination Project in 800 Mandis | • Price ticker boards installed at 352 APMC |
|  |  | xi) Identifying suitable office premises providing adequate infrastructure for efficient office functioning | Upgradation of office infrastructure Rs. 1.15 crore | - Identification of new office premises and payment of rent for hired premises, municipal rates, taxes, etc. - All contingent expenses for running an office, such as furniture, postage, purchase and maintenance of office machines and equipments, etc. | • Identified new office premises. Process of seeking approvals from the Ministry is under way. |

* 	Targets for Capacity Building programmes reduced from 50 to 35.

**	Targets for performance audit increased from 100 to 200.

Review of Past Performance of NTH

NTH Plan Scheme:

NTH has been implementing a Plan Scheme for providing services to the industries in the field of testing, calibration and quality evaluation of materials and products of all engineering  branches except pharmaceuticals, arms and ammunition. The objective of the NTH XI Plan Scheme is to render assistance for improving the quality of Indian engineering products so as to meet the national / international standards for their acceptability in the global market in order to keep pace with the tremendous technological changes taking place worldwide.

Achievements w.r.t. Outcome Budget 2009-10 & 2010-11( up to December'2010) in respect of NTH Plan Scheme are given in Annexures I & II.

Annexure I

Objectives of NTH Plan Scheme, targets and achievements during 2009-10

(Rs. in Crore)

| Sl No. | Name of the Scheme/ Programme | Objective/ Outcome | Outlay 2009-10 (Plan) | Actual Expdtr. Incurred | Quantifiable Deliverables | Achievements w.r.t.Col.6 | Reasons for variation in achievements w.r.t. Col 6 |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 |
|  | National Test House | To provide services to the industries in the field of testing and evaluation of materials and products of all engineering branches except pharmaceuticals, arms & ammunitions. | 15.00 (BE) 14.45(RE) 12.25( L&B and ME) 2.20 (recurring & IT) | 13.47 | Land & Building and Machinery & Equipment- Recurring Expenditure & Information Technology- | 92.98 % of RE 94.55 % of RE | i) Regarding allocation under the head Major Works ( Land & Building), allocation in RE was 5.25. NTH through DoCA had authorized entire amount to CPWD. However, CPWD could utilize 4.52 ( % utilization 86) ii) As regards to ME, allocation under RE was 7.0 and utilization was 6.87 ( % utilization 98). Hence in column 7, less achievement was due to less utilization by CPWD iii) As regards, utilization of Recurring Expenditure & Information Technology, allocation in RE under the DTE & FTE was 30.0, utilization 18.49 iv) OE allocation 1.50 under RE, utilization 1.50( full utilization) v) IT allocation 40.0 under RE, utilization 39.9( full utilization). Hence in column 7, less achievement was due to less utilization in DTE & FTE |

Annexure II

Objectives of NTH Plan Scheme, targets and achievements during 2010-2011

(Rs. in Crore)

| Sl. No. | Name of the Scheme/ Programme | Objective/Outcome | Outlay 2010-11 (Plan) | Actual Expdtr. Incurred | Quantifiable Deliverables | Achievements w.r.t. Col 6 | Reasons for variation in achievements w.r.t. Col 6 |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | National Test House | To implement the Plan schemes to be undertaken during 11th Plan Period Outcome : Construction work, augmentation and procurement of advanced equipment, training, R&D activities, extension of MIS etc. | 17.17 (BE) 17.17(RE) | 10.41 up to December'10 | Land & Building & Machinery & Equipments (9.23) Recurring Expenditure & Information Technology (1.18) | L&B (7.59) M&E (1.64)** Recurring ( 1.02) IT( 0.16) Total(10.41) which is 62.45 % of RE up to 31.12.2010 |  |

** Amount booked so far under Letter of Credit (LC) for imported equipments (M&E): 1.59 crore

CONSUMER AWARENESS SCHEME

Annexure

The highlighting covering objectives, targets and achievements in the field of consumer awareness during the year 2010-11 are tabulated as under:-

(Rs. in crore)

| S. No. | Name of the Scheme /Programme | Objective/ Outcome | Outlay 2010-11 | Expenditure during 2010-11 | Quantifiable Deliverables | Achievements w.r.t. (Col 5) |  | Reason for variation |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | 2 | 3 | 4 | 5 | 6 | 7 |  | 8 |  |
| 1 | Consumer Awareness | Empowerment of consumer by dissemination of information regarding consumer rights and responsibilities through multi media publicity campaign “Jago Grahak Jago”. | 84.02 | 67.36 Till 31.12.2010 | 1. Print advertisements through national and regional newspapers as per DAVP policy. Around 20,000 insertions on about 30 themes/issues. 2. Release of audio spots through AIR and Private FM channels on issues of consumer interest-10,000 audio spots 40 seconds each. 3. Release of TV spots through DD Network, including regional channels of DD- Around 20,000 video spots of 30 seconds each. 4. Release of TV spots through Private C&S channels through DAVP- Around 15,000 video spots of 30 seconds each. 5. Outdoor Publicity through channels, hoardings etc. 6 Printing of messages on consumer issues on railway tickets/reservation charts-approximately 50 lakhs tickets/charts. 7. Organisation of Nukkad Natak’s on consumer awareness. 8. Participation in Trade Fairs/Exhibition on consumer awareness. 9. Organisation of Poster Competition through colleges/schools in Delhi on consumer awareness. |  | As in col. 6 |  | Target achieved. |

| # CHAPTER - V |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| # FINANCIAL REVIEW |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| This chapter on financial review covers overall trends in expenditure viz-a-viz Budget Estimates and Revised Estimates since 2007-08. Data has been segregated scheme wise. Position of outstanding utilization certificates and unspent balances has also been brought out. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| TRENDS IN EXPENDITURE VIZ-A-VIZ BUDGET ESTIMATES/REVISED ESTIMATES IN RECENT YEARS. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| PLAN |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  | ( Rs. in Crore ) |  |  |  |
| No. | Scheme | Budget Estimates |  |  |  |  | Revised Estimates |  |  |  | Actual Expenditure |  |  |  |  |
|  |  | 2007-2008 | 2008-2009 | 2009-2010 | 2010-2011 | 2011-2012 | 2007-2008 | 2008-2009 | 2009-2010 | 2010-2011 | 2007-2008 | 2008-2009 | 2009-2010 | 2010-2011 |  |
| 1 | Consumer Protection and Consumer Education, Training/ HRD/Capacity Building and Consumer Awareness | 71.30 | 71.71 | 83.47 | 84.23 | 89.18 | 54.68 | 82.45 | 74.62 | 79.38 | 49.81 | 81.40 | 76.35 | 75.12 |  |
| 2 | National Test House | 22.50 | 12.60 | 13.50 | 15.45 | 19.00 | 8.15 | 10.22 | 12.95 | 15.45 | 5.39 | 9.99 | 13.47 | 10.84 |  |
| 3 | Consumer Disputes Redressal Commission | 4.50 | 11.00 | 9.90 | 3.44 | 0.00 | 0.01 | 10.00 | 9.90 | 2.39 | -- | 10.00 | 9.80 | 2.39 |  |
| 4 | Integrated Project on Consumer Protection/Strengthening Consumer Disputes Redressal Agencies, Consumer Help line. | 43.00 | 34.50 | 16.21 | 20.14 | 21.65 | 34.28 | 15.50 | 10.50 | 14.94 | 36.55 | 15.79 | 11.72 | 9.34 |  |
| 5 | Setting up of Gold Hallmarking and Assaying Centres in India/ Standardization & Quality Control | 14.40 | 21.39 | 14.62 | 2.74 | 2.17 | 10.04 | 0.63 | 1.33 | 1.32 | 1.50 | 0.66 | 1.21 | 1.03 |  |
| 6 | Weights & Measures | 16.20 | 16.20 | 34.20 | 56.25 | 58.00 | 19.71 | 21.60 | 30.20 | 54.75 | 10.12 | 21.18 | 26.89 | 38.30 |  |
| 7 | Regulation of Markets | 19.50 | 20.70 | 16.20 | 15.75 | 12.50 | 9.75 | 3.60 | 8.10 | 9.68 | 2.46 | 3.31 | 6.79 | 4.21 |  |
| 8 | Lump sum provision for schemes in NE | 21.60 | 20.90 | 20.90 | 22.00 | 22.50 | 13.38 | 16.00 | 16.40 | 20.09 | * | * | * | * |  |
|  | Total | 213.00 | 209.00 | 209.00 | 220.00 | 225.00 | 150.00 | 160.00 | 164.00 | 198.00 | 105.83 | 142.33 | 146.23 | 141.23 |  |

*Expenditure is included in relevant Functional Heads.

Note:- 1. Expenditure for the year 2010-11(upto 31.12.2010) includes amount of Rs. 58.98 crores authorized in favour of other Ministries/Departments.

2. Expenditure during 2009-10 is as booked by Pr. AO.

TRENDS IN EXPENDITURE VIS-A-VIS BUDGET ESTIMATES/REVISED ESTIMATES DURING 2009-10

## PLAN

During the financial year 2010-11 a total allocation of Rs.220.00 crore was made in BE 2010-11 which was subsequently reduced to Rs.198.00 crore at RE stage. The actual expenditure as on 31.12.2010 is Rs.141.23 crore which constitutes 71.33%  of RE of Rs.198.00 crores during 2010-11. The schemes wise and major head wise allocation and expenditure is given below.

(Rs. in Crore)

| Sr.No. | Scheme etc. | Major Head | B.E. 2010-2011 | RE 2010-2011 | Actual expenditure 2010-11 upto Dec. 10 | B.E. 2011-2012 |
| --- | --- | --- | --- | --- | --- | --- |
| 1. | National Consumer Disputes Redressal Commission | 5475 | 3.44 | 2.39 | 2.39 | 0.00 |
| 2. | Consumer Protection, Consumer Awareness and Consumer Education, Training HRD/Capacity Building. | 3456 3601 3602 | 84.23 19.39 0.75 | 79.38 14.19 0.75 | 75.12 9.34 0.00 | 89.18 20.75 0.90 |
| 3. | Weights & Measures, Establishment of Laboratories | 5475 3475 3601 3602 | 10.88 30.00 14.37 1.00 | 9.38 34.50 10.37 0.50 | 3.90 30.38 4.02 0.00 | 5.00 35.74 16.76 0.50 |
| 4. | National Test House | 3425 5425 | 1.77 13.68 | 2.27 13.18 | 1.20 9.64 | 3.00 16.00 |
| 5. | Forward Markets Commission | 3475 | 15.75 | 9.68 | 4.21 | 12.50 |
| 6 | Lumpsum provision for North East project/Scheme for the benefit of North East Region | 2552 4552 | 18.66 3.34 | 16.75 3.34 | * * | 20.04 2.46 |
| 7 | Setting up of Gold Hall Marking/Assaying Centres in India Standardization & Quality Control | 2852 | 2.74 -- | 1.32 | 1.03 | 2.17 |
|  |  |  | 220.00 | 198.00 | 141.23 | 225.00 |

*Expenditure on NER Schemes including Sikkim is included in various functional heads

Notes:- Expenditure of Rs. 141.23 crores during 20010-11 (upto 31.12.2010) includes amount of Rs. 58.98 crores authorized in favour of other Ministries/Departments.

### NON-PLAN

During the financial year 2010-11 an allocation of Rs.255.20 crore was made in BE 2010-11 which was subsequently enhanced to Rs.504.94 crore at RE stage. The actual expenditure as on 31.12.2010 is Rs.196.86 crore (net) which constitutes 38.99%        of total allocation of RE of 2010-11. The scheme wise and major head wise allocation and expenditure is given below.

(Rs. in Crore)

| Sr.No. | Scheme | Major Head | B.E. 2010-2011 | RE 2010-2011 | Actual expenditure 2010-11 upto Dec. 10 | B.E. 2011-2012 |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Secretariat Economic Services | 3451 | 16.21 | 16.19 | 11.71 | 16.42 |
| 2 | National Test House | 3425 | 21.67 | 22.24 | 17.72 | 22.26 |
| 3 | Subsidies | 2408 | 200.00 | 450.00 | 156.10 | 300.00 |
| 4 | Consumer Protection | 3456 | 6.39 | 6.34 | 4.63 | 6.57 |
| 5 | Regulation of Weights & Measures | 3475 | 4.24 | 4.06 | 2.83 | 4.02 |
| 6 | International Cooperation | 3475 | 0.10 | 0.10 | 0.08 | 0.10 |
| 7 | Regulation of Markets | 3475 | 6.59 | 6.01 | 3.79 | 6.19 |
| 8 | Project under Consumer Welfare Fund | 3456 3601 3602 | 10.30 3.00 0.50 | 13.28 3.00 0.50 | 5.99 0.10 0.00 | 16.30 3.00 0.50 |
| 9 | Deduct Refund* | 3456 | -13.80 | -16.78 | -6.09 | -19.80 |
|  | Total |  | 255.20 | 504.94 | 196.86 | 355.56 |

*The deduct entry represents the budgetary provision made under Consumer Welfare Fund which is being met out of  Reserve Fund created for this purpose. The receipt is being accounted for under Major Head 8229- Development and Welfare Funds – 123 Consumer Welfare Fund.

Scheme-wise, Major Head-wise Financial Requirements/ Budgetary Outlay

(Rs. in Crore)

| Programme |  | BE 2009-10 |  |  | RE 2009-10 |  |  | BE 2010-11 |  |  | RE 2010-11 |  |  | BE 2011-12 |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Major Head | Plan | Non-Plan | Total | Plan | Non-Plan | Total | Plan | Non-Plan | Total | Plan | Non-Plan | Total | Plan | Non-Plan | Total |
| 1. Secretariat Economic Services | 3451 | -- | 13.44 | 13.44 | -- | 15.17 | 15.17 | -- | 16.21 | 16.21 | -- | 16.19 | 16.19 | -- | 16.42 | 16.42 |
| 2. .Lump sum provision for projects /Schemes for North Eastern Region (Revenue Section) | 2552 | 18.88 | -- | 18.88 | 14.88 | -- | 14.88 | 18.66 | -- | 18.66 | 16.75 | -- | 16.75 | 20.04 | -- | 20.04 |
| 3. National Test House | 3425 | 2.75 | 26.24 | 28.99 | 2.20 | 22.96 | 25.16 | 1.77 | 21.67 | 23.44 | 2.27 | 22.24 | 24.51 | 3.00 | 22.26 | 25.26 |
| 4. Consumer Industries Bureau of Indian Standards | 2852 | 14.62 | -- | 14.62 | 1.33 | -- | 1.33 | 2.74 | -- | 2.74 | 1.32 | -- | 1.32 | 2.17 | -- | 2.17 |
| 5. (i) Consumer Cooperative (ii) Subsidies on import of Pulses | 3456 3456 | -- -- | 0.05 -- | 0.05 -- | -- -- | -- -- | -- -- | -- -- | -- -- | -- -- | -- -- | -- -- | -- -- | -- -- | -- -- | -- -- |
| 6. Subsidy for meeting losses on import of pulses | 2408 | -- | 200.00 | 200.00 | -- | 200.00 | 200.00 | -- | 200.00 | 200.00 | -- | 450.00 | 450.00 | -- | 300.00 | 300.00 |
| 7. Consumer Protection | 3456 3601 3602 | 83.47 3.00 0.50 | 5.85 -- -- | 89.32 3.00 0.50 | 74.62 5.00 1.00 | 6.16 -- -- | 80.78 5.00 1.00 | 84.23 5.00 0.50 | 6.39 -- -- | 90.62 5.00 0.50 | 79.38 2.00 0.50 | 6.34 -- -- | 85.72 2.00 0.50 | 89.18 2.00 0.50 | 6.57 -- -- | 95.75 2.00 0.50 |
| 8.Strengthening of Consumer Disputes Redressal Agencies (integrated project) | 3601 3602 | 6.71 1.00 | -- -- | 6.71 1.00 | 2.00 -- | -- -- | 2.00 -- | 13.14 -- | -- -- | 13.14 -- | 10.94 -- | -- | 10.94 -- | 17.15 -- | -- -- | 17.15 -- |
| 9. Regulation of Weights & Measures | 3475 3601 3602 | 14.72 12.00 2.00 | 3.83 -- -- | 18.55 12.00 2.00 | 14.22 12.00 2.00 | 3.90 -- -- | 18.12 12.00 2.00 | 30.00 14.37 1.00 | 4.24 -- -- | 34.24 14.37 1.00 | 34.50 10.37 0.50 | 4.06 -- -- | 38.56 10.37 0.50 | 35.74 16.76 0.50 | 4.02 -- -- | 39.76 16.76 0.50 |
| 10. International Cooperation | 3475 | -- | 0.10 | 0.10 | -- | 0.10 | 0.10 | -- | 0.10 | 0.10 | -- | 0.10 | 0.10 | -- | 0.10 | 0.10 |
| 11. Regulation of Markets | 3475 | 16.20 | 6.49 | 22.69 | 8.10 | 5.37 | 13.47 | 15.75 | 6.59 | 22.34 | 9.68 | 6.01 | 15.69 | 12.50 | 6.19 | 18.69 |
| 12. Capital outlay on General Economic services (W&M) | 5475 | 5.48 | -- | 5.48 | 1.98 | -- | 1.98 | 10.88 | -- | 10.88 | 9.38 | -- | 9.38 | 5.00 | -- | 5.00 |
| 13. Capital outlay on scientific & other Environmental Research (NTH) | 5425 | 10.75 | -- | 10.75 | 10.75 | -- | 10.75 | 13.68 | -- | 13.68 | 13.18 | -- | 13.18 | 16.00 | -- | 16.00 |
| 14. Lump sum provision for Projects/ scheme for North Eastern Region (Capital Section) | 4552 | 2.02 | -- | 2.02 | 1.52 | -- | 1.52 | 3.34 | -- | 3.34 | 3.34 | -- | 3.34 | 2.46 | -- | 2.46 |
| 15. Project under Consumer Welfare Fund | 3456 3601 3602 | -- -- -- | 10.40 3.00 0.50 | 10.40 3.00 0.50 | -- - - | 9.72 1.00 0.48 | 9.72 1.00 0.48 | -- -- -- | 10.30 3.00 0.50 | 10.30 3.00 0.50 | -- -- -- | 13.28 3.00 0.50 | 13.28 3.00 0.50 | -- -- -- | 16.30 3.00 0.50 | 16.30 3.00 0.50 |
| Deduct Refund | 3456 3601 3602 | -- -- -- | -10.40 -3.00 -0.50 | -10.40 -3.00 -0.50 | -- -- | -9.72 -1.00 -0.48 | -9.72 -1.00 -0.48 | -- -- -- | -10.30 -3.00 -0.50 | -10.30 -3.00 -0.50 | -- -- -- | -13.28 -3.00 -0.50 | -13.28 -3.00 -0.50 | -- -- -- | -16.30 -3.00 -0.50 | -16.30 -3.00 -0.50 |
| 16. Loans to Super Bazar | 7475 | -- | 2.00 | 2.00 | -- | -- | -- | -- | -- | -- | -- | -- | -- | -- | -- | -- |
| 17. Construction of building of NCDRC | 5475 | 9.90 | -- | 9.90 | 9.90 | -- | 9.90 | 3.44 | -- | 3.44 | 2.39 | -- | 2.39 | -- | -- | -- |
| 18. Consumer Helpline | 3601 3602 | 4.00 1.00 | -- -- | 4.00 1.00 | 2.00 0.50 | -- | 2.00 0.50 | 1.25 0.25 | -- | 1.25 0.25 | 1.25 0.25 | -- -- | 1.25 0.25 | 1.60 0.40 | -- -- | 1.60 0.40 |
| Total |  | 209.00 | 258.00 | 467.00 | 164.00 | 253.66 | 417.66 | 220.00 | 255.20 | 475.20 | 198.00 | 504.94 | 702.94 | 225.00 | 355.56 | 580.56 |

Object head-wise Classification

(Rs. in lakh)

| REVENUE SECTION | BE 2009-10 |  |  | RE 2009-10 |  |  | BE 2010-11 |  |  | RE 2010-11 |  |  | BE 2011-12 |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Plan | Non-Plan | Total | Plan | Non-Plan | Total | Plan | Non-Plan | Total | Plan | Non-Plan | Total | Plan | Non-Plan | Total |
| Salaries | -- | 4649.64 | 4649.64 | -- | 4473.90 | 4473.90 | -- | 4458.34 | 4458.34 | -- | 4460.83 | 4460.83 | -- | 4494.00 | 4494.00 |
| Medical Treatment | -- | 103.30 | 103.30 | -- | 93.55 | 93.55 | -- | 99.00 | 99.00 | -- | 89.15 | 89.15 | -- | 91.00 | 91.00 |
| OTA | -- | 10.93 | 10.93 | -- | 9.95 | 9.95 | -- | 11.30 | 11.30 | -- | 10.14 | 10.14 | -- | 11.25 | 11.25 |
| Wages | -- | 16.60 | 16.60 | -- | 16.85 | 16.85 | -- | 16.00 | 16.00 | -- | 15.95 | 15.95 | -- | 8.06 | 8.06 |
| Office Expenses | 300.50 | 541.92 | 842.42 | 190.50 | 506.86 | 697.36 | 160.50 | 620.60 | 781.10 | 210.50 | 592.30 | 802.80 | 250.50 | 616.40 | 866.90 |
| Rent Rates & Taxes | 360.00 | 3.80 | 363.80 | 1.00 | 3.60 | 4.60 | 100.00 | 3.80 | 103.80 | 40.00 | 10.00 | 50.00 | 10.00 | 10.00 | 20.00 |
| Domestic Travel Expenses | 110.00 | 101.72 | 211.72 | 92.00 | 92.48 | 184.48 | 95.00 | 99.60 | 194.60 | 91.00 | 96.00 | 187.00 | 135.00 | 99.78 | 234.78 |
| Foreign Travel Expenses | 110.00 | 60.10 | 170.10 | 105.00 | 45.09 | 150.09 | 105.00 | 51.00 | 156.00 | 105.00 | 48.00 | 153.00 | 105.00 | 50.30 | 155.30 |
| Publication | -- | 11.59 | 11.59 | -- | 10.43 | 10.43 | -- | 10.30 | 10.30 | -- | 10.25 | 10.25 | -- | 11.32 | 11.32 |
| Grant-in-aid General | 5825.00 | 1355.10 | 7180.10 | 3442.00 | 1097.70 | 4539.70 | 5352.00 | 1347.09 | 6699.09 | 560.55 | 1497.09 | 2057.64 | 733.00 | 1748.10 | 2481.10 |
| Grants for creation of Capital Assets | -- | -- | -- | -- | -- | -- | 19.00 | 3.01 | 22.01 | 3063.45 | 153.01 | 3216.46 | 4160.00 | 202.00 | 4362.00 |
| Subsidy | -- | 20000.00 | 20000.00 | -- | 20000.00 | 20000.00 | -- | 20000.00 | 20000.00 | -- | 45000.00 | 45000.00 | -- | 30000.00 | 30000.00 |
| Contribution | 10.00 | 15.00 | 25.00 | 8.00 | 17.00 | 25.00 | 10.00 | 20.00 | 30.00 | 10.00 | 30.00 | 40.00 | 10.00 | 30.00 | 40.00 |
| Other charges | 811.00 | 24.90 | 835.90 | 514.00 | 23.65 | 537.65 | 840.00 | 30.39 | 870.39 | 302.00 | 30.39 | 332.39 | 939.00 | 31.93 | 970.93 |
| Other Administrative Expenses | 25.00 | 21.20 | 46.20 | 15.00 | 13.82 | 28.82 | 25.00 | 15.20 | 40.20 | 25.00 | 16.20 | 41.20 | 30.00 | 16.37 | 46.37 |
| Supply & Material | -- | 13.10 | 13.10 | -- | 12.45 | 12.45 | -- | 15.00 | 15.00 | -- | 15.00 | 15.00 | -- | 15.50 | 15.50 |
| Advertising and Publicity | 7530.00 | 6.20 | 7536.20 | 7260.00 | 5.58 | 7265.58 | 7942.00 | 6.80 | 7948.80 | 7906.00 | 5.00 | 7911.00 | 8598.00 | 5.00 | 8603.00 |
| Professional Services | 103.50 | 15.75 | 119.25 | 101.60 | 14.90 | 116.50 | 120.50 | 26.30 | 146.80 | 110.50 | 26.30 | 136.80 | 240.50 | 26.38 | 266.88 |
| Secret Service Expenditure | -- | 1.00 | 1.00 | -- | 0.95 | 0.95 | -- | 0.90 | 0.90 | -- | 0.90 | 0.90 | -- | 1.00 | 1.00 |
| Machinery and Equipment | 1472.00 | 6.35 | 1478.35 | 1422.00 | 6.03 | 1428.03 | 3000.00 | 7.15 | 3007.15 | 3450.00 | 7.15 | 3457.15 | 3774.00 | 7.50 | 3781.50 |
| Minor Works | -- | 20.80 | 20.80 | -- | 31.03 | 31.03 | -- | 35.80 | 35.80 | -- | 35.80 | 35.80 | -- | 37.57 | 37.57 |
| Information Technology i) Office Expenses ii) Professional Services | 1418.00 10.00 | 11.00 -- | 1429.00 10.00 | 823.90 10.00 | 9.90 -- | 833.80 10.00 | 1087.00 10.00 | 22.40 -- | 1109.40 10.00 | 1087.00 10.00 | 22.40 -- | 1109.40 10.00 | 1159.00 10.00 | 22.54 -- | 1181.54 10.00 |
| Deduct Refund | -- | -1390.00 | -1390.00 | -- | -1119.50 | -1119.50 | -- | -1380.00 | -1380.00 | - | -1678.00 | -1678.00 | -- | -1980.00 | -1980.00 |
| Total Revenue Section | 18085.00 | 25600.00 | 43685.00 | 13985.00 | 25366.22 | 39351.22 | 18866.00 | 25519.98 | 44385.98 | 16971.00 | 50493.86 | 67464.86 | 20154.00 | 35556.00 | 55710.00 |
| CAPITAL SECTION |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Machinery and Equipments | 1100.00 | -- | 1100.00 | 720.00 | -- | 720.00 | 1620.00 | -- | 1620.00 | 1436.00 | -- | 1436.00 | 794.00 | -- | 794.00 |
| Major Works | 1715.00 | -- | 1715.00 | 1695.00 | -- | 1695.00 | 1514.00 | -- | 1514.00 | 1393.00 | -- | 1393.00 | 1552.00 | -- | 1552.00 |
| Loans to Super Bazar | -- | 200.00 | 200.00 | -- | -- | -- | -- | -- | -- | -- | -- | -- | -- | -- | -- |
| Total Capital Section | 2815.00 | 200.00 | 3015.00 | 2415.00 | -- | 24150.00 | 3134.00 | -- | 3134.00 | 2829.00 | -- | 2829.00 | 2346.00 | -- | 2346.00 |
| Grand Total | 20900.00 | 25800.00 | 46700.00 | 16400.00 | 25366.22 | 41766.22 | 22000.00 | 25519.98 | 47519.98 | 19800.00 | 50493.86 | 70293.86 | 22500.00 | 35556.00 | 58056.00 |

## Department of Consumer Affairs

## Ministry of Consumer Affairs, food and Public Distribution

UTILIZATION CERTIFICATES (U.Cs) OUTSTANDING IN RESPECT OF GRANTS/LOANS RELEASED UP TO 31ST MARCH 2009 (AS ON 1ST MARCH, 2010

| Year | No. of UC.s outstanding in respect of grants released up to March 2009 | Amount involved (in Rs. ) | No. of U.C.s received | Amount involved in respect of U.C.s received | No. of U.C.s outstanding as on 31.12.2010 | Amount involved on outstanding U.C.s (In Rs.) |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | 2 | 3 | 4 | 5 | 6 | 7 |
| 1996-97 | 8 | 3,23,500 | - | - | 8 | 3,23,500 |
| 1997-98 | 5 | 1,66,500 | - | - | 5 | 1,66,500 |
| 1998-99 | 4 | 1,35,000 | - | - | 4 | 1,35,000 |
| 1999-2000 | 1 | 22,500 | - | - | 1 | 22,500 |
| 2000-01 | 3 | 86,400 | - | - | 3 | 8,6,400 |
| 2001-02 | 2 | 90,000 | - | - | 2 | 90,000 |
| 2002-03 | - | - | - | - | - | - |
| 2003-04 | 2 | 2,79,000 | - | - | 2 | 2,79,000 |
| 2004-05 | 4 | 6,66,000 | - | - | 4 | 6,66,000 |
| 2005-06 | - | - | - | - | - | - |
| 2006-07 | 11 | 24,00,000 | - | - | 11 | 24,00,000 |
| 2007-08 | 2 | 45,8,900 | - | - | 2 | 45,8,900 |
| 2008-09 | - | - | - | - | - | - |
| Total | 42 | 46,27,800 | - | - | 42 | 46,27,800 |

Unspent Balances

The unspent balances in respect of different schemes are given below:-

- Under the Gold Hallmarking Scheme for setting up of Assaying and  Hallmarking Centres, against the total amount of Rs. 1.50 crore released to BIS so far, there is an unspent balance of Rs. 56,82,759/- as on 31st March,2009.

- Under HRD and Capacity Building in Educational Institutions, against the allocation of Rs. 50.00 lakhs so far there is an unspent balance of Rs. 48.86 lakhs at the end of March, 2009.

- Under National System for Standardization, against the allocation of Rs. 66.00 lakhs so far, there is an unspent balance of Rs. 61.23 lakhs at the end of March, 2009.

- Under Consumer Education, Training, HRD Capacity Building, against the allocation of Rs. 115.60 lakhs so far, there is an unspent balance of Rs. 26.28 lakhs at the end of March, 2009.

# CHAPTER VI

# REVIEW OF PERFORMANCE OF AUTONOMOUS BODY

This chapter reviews the performance of the autonomous body under the administrative control of Department of Consumer Affairs.

There is only one autonomous body under the Department of Consumer Affairs namely Bureau of Indian Standards (BIS).

BIS was set up on 01st April 1987 as a statutory body taking over the function of the erstwhile Indian Standards Institution (ISI). The Bureau has completed twenty three years of operation on 31st March 2010.

2.  Performance of Bureau of Indian Standards (BIS)

2.1	 As on 30th November 2010, as many as 18587 standards representing specifications, methods of test, definitions of technical terms, codes of practice, etc., covering various sectors in the industrial and agricultural fields, were in force.

2.2 Certification Marking Scheme continued to progress and as on 30th November 2010, as many as 23597 licences were in operation. The actual income through Product Certification during 2010-11 (upto 30th November 2010) is given in Table 1.

2.3 BIS is also operating the following Management System Certification Schemes.  The Schemes have progressed during the year.  The number of licenses in operation under each Scheme as on 30th November, 2010 are shown against each:

(i)  Quality Management System Certification as per ISIISO 9001 					-	  870

(ii) Environmental Management Systems Certification as per IS/ISO 14001 			-	  142

(iii) Occupational Health and Safety Management System Certification as per IS 18001  	 	 -	    48

(iv) Hazard Analysis and Critical Control Point (HACCP) integrated with Quality Management System certification for food safety    53

(v) Service Quality Management System   			- 	    04

The actual income through Management System Certification during 2010-11 (upto 30th November 2010) is given in Table 1.

2.4 	BIS also operates a Hallmarking (Gold/Silver/artifacts) Certification scheme. As on 30th November 2010, as many as 8288 licences (Gold – 7831 & Silver – 457) were in operation under the Hallmarking scheme.  The number of BIS recognized assaying and hallmarking centres has increased to 158 as on 30 November 2009.  The income from Hallmarking activity for 2010-11 (upto 30th November 2010) is given in Table 1.

Scheme for setting up of Assaying/Hallmarking Centre with central assistance.

The Scheme for setting up of Gold Assaying / Hallmarking Centres with Central assistance was introduced during the 10th Five Year Plan.  Under the scheme selected applicants will be given one time financial assistance @ 15% of cost of machinery and equipment subject to maximum of           Rs. 15 lakhs per centre except locations of North- East and special category states namely Jammu and Kashmir, Himachal Pradesh and Uttaranchal for which one time financial assistance @ 30% of cost of machinery & equipment subject to maximum of Rs. 30 lakhs per centre would be given.

Under this Scheme, 25 Centres (including 2 under 10th plan) have been set up and recognized by BIS as on 30 November 2010.

During the meeting taken by Secretary (CA) on 3 Dec. 2010 the following was decided:-

- Rate of financial assistance under the Scheme may be increased as under:-

| Area | Existing Rate | Revised Rate |  |
| --- | --- | --- | --- |
|  |  | Private Entrepreneur | PSU |
| Normal | 15% | 30% | 50% |
| NE/SCS/RA | 30% | 50% | 75% |

NE – North East States, SCS - Special Category States, RA – Rural Areas

It was decided that the benefit of increased rate of financial assistance shall be applicable only to such applicants to whom first installment of financial assistance is yet to be released.

b)	Rs 1.00 crore may be earmarked exclusively for publicity of Gold Hallmarking / Assaying through DAVP.

2.5 	A Small Scale Industries Facilitation Centre has been started to help dissemination of information relating to BIS activities in various fields, in particular the Product and Quality System Certification Schemes. This service has received appreciation of the small scale industrial units and entrepreneurs.

3.1			The physical targets and achievements of BIS during 2009-10 and 2010-11 are as given below:-

| S.No. |  | Targets 2009-10 | Achievement 2009-10 | Targets 2010-11 (upto 31 Dec 2010) | Achievement 2010-11 (upto 30 Nov 2010) |
| --- | --- | --- | --- | --- | --- |
| i) | Standards Formulated | 320 | 322 | 182 | 212 |
| ii) | Grant of New Licence |  |  |  |  |
| a. | Product Certification | 2300 | 2595 | 1950 | 2103 |
| b. | System Certification | 100 | 89 | 218 | 59 |
| c. | Hallmarking of Jewellery | 2500 | 1125 | 1050 | 824 |

  - Earnings during the year: - The Income generated by BIS during the year (upto 30th November, 2010) from various activities is as given in Table 1.

Table - 1

FINANCIAL TERMS

(Rupees in lakhs)

| S.No. |  | Targets 2010-11(B.E.) | Achievements (upto 30/11/10) |
| --- | --- | --- | --- |
| i) | Sale of Indian Standards | 792.00 | 483.99 |
| ii) | Certification Marks Income |  |  |
| a. | Product | 18500.00 | 12593.20 |
| b. | Systems Certification | 242.00 | 158.15 |
| c. | Hall Marking of Gold Jewellery | 1050.00 | 682.43 |
| d. | Conference, Consultancy & Training Fee | 130.00 | 43.31 |
| e. | Miscellaneous | 110.00 | 177.26 |
| f. | Interest Income | 1700.00 | NIL* |

3.3	The financial position of BIS for the financial year 2009-10 and for the period from 1st April 2010 to 30 November 2010 is indicated below:

| S.No. |  | 2009-10 | 2010-11(upto 30/11/2010) |
| --- | --- | --- | --- |
| 1. | Income | 22350.36 | 14138.34 |
| 2. | Expenditure |  |  |
| 2.1 | Operational Expenditure | 15338.88 | 9397.05 |
| 2.2 | Contribution towards shortfall in Pension/Gratuity Liab. Fund A/c | 7011.48 | 4741.29 |
| 3. | Surplus | NIL | NIL |

* To be finalized in the year ended Annual Accounts since it is calculated on accrual basis